## Slide 1: Interreg-IPA Cross-border Cooperation Romania-Serbia Programme
REPORTING TO
Joint Secretariat
June 2019

## Slide 2: Purpose of the verification
The Joint Secretariat will:
verify if the funds are used for the purposes for which they have been allocated;
if the terms and the conditions of the financing decision (subsidy/co-financing contract) are followed;
Identify the projects which do not fulfill their objectives;
Identify the problems on time and making suggestions for their improvement (taking preventive and/or corrective measures, as the case may be).

## Slide 3: Verification process
First Level Control (FLC)
Project Beneficiary (PB)
Joint Secretariat (JS)
Managing Authority (MA)
Lead Beneficiary (LB)
1
2
3
4
5
7
6
1 – PB submits progress report (activities + expenditures) and supporting documents to FLC RO / FLC RS, through the e-MS
2 - FLC verifies + validates expenditures and sends documents to PB, through the e-MS
3 – PB submits reports with validated expenditures to LB, through the e-MS

## Slide 4
4 – LB prepares and submits the consolidated project report (technical and financial progress) and the reimbursement claim to JS, through the e-MS
5 – JS verifies documents and submits them all to MA, through the e-MS
6 – MA makes payment of approved amount to LB and notifies him via e-MS
7 – LB distributes paid amounts to PB without delay and uploads the documentary proof in e-MS together with the following report.
First Level Control (FLC)
Project Beneficiary (PB)
Joint Secretariat (JS)
Managing Authority (MA)
Lead Beneficiary (LB)
1
2
3
4
5
7
6

## Slide 5: Project report
LB creates the global project report where all partner reports will be integrated after certification by FLC.
LB prepares the aggregated activity report at project level, based on the progress of activities provided by the partners in the partner reports.
All partners are obliged to submit a partner report for each period, even if there are no costs to be claimed during the respective time span.
LB includes in the project report FLC certificates (except those with 0 expenditures) attached to partner reports. Financial data is automatically integrated in the project report.
The project report is submitted by LB to the JS.

## Slide 6: Progress report
 | A.1. Project Progress Report Identification | 
Project Title |  | 
Project Acronym |  | 
Project Website |  | 
Project Number |  | 
Project Duration Start Date |  | 
Project Duration End Date |  | 
Project Priority |  | 
Project Priority Specific Objective |  | 
Lead Partner |  | 
Contact Person |  | 
Reporting Period |  | 

## Slide 7: Progress report
 |  | A.2. Highlights of main achievements | 
Highlights Of Main Achievements |  |  | 
A.3. Project Specific Objectives |  |  | 
Project Specific Objectives | Level of Achievement |  | Explanations

## Slide 8: Progress report
 |  | A.4. Target Groups Reached |  |  |  | 
Target Groups | Target Value | Target Groups Reached (previous periods) | Target Groups Reached (current period) | Source of Verification | Description of Target Group inv. | Target Groups Reached so far %

## Slide 9: Progress report
A.5. Work Package Preparation (preparation) |  |  |  | 
WP number | WP title | WP start date | WP end date | WP status
Partners` involvement |  |  |  | 
Abbreviation |  | Name |  | 
Summary Description Of Activities Carried Out And Contribution Of Each Partner |  |  |  | 
NA |  |  |  | 

## Slide 10: Progress report
A.5. Work Package Management (management) |  |  |  |  |  | 
WP title | WP start date | WP end date | WP status | WP expenditure current report | % of WP reported so far | 
Partners` involvement |  |  |  |  |  | 
Abbreviation |  |  | Name |  |  | 
LP |  |  |  |  |  | 
PP2 |  |  |  |  |  | 
PP3 |  |  |  |  |  | 

## Slide 11: Progress report
Please Describe The Progress In This Reporting Period And Explain How Were Partners Involved And Who Did What |  |  |  |  |  | 
Please Describe And Justify Any Problems And Deviations Including Delays From The Work Plan Presented In The Application Form And The Solutions Found |  |  |  |  |  | 
Please describe progress achieved in this reporting period |  |  |  |  |  | 
Activity Number | Activity title |  | Start month | End month | Status | 
Deliverable number | Deliverable title | Deliverable desription | Planned delivery month | Progress Report Deliverable Description | Status | Deliverable evidence

## Slide 12: Progress report
A.5. Work Package Implementation (implementation) |  |  |  |  |  | 
WP number | WP title | WP start date | WP end date | WP status | WP expenditure current report | % of WP reported so far
Partners` involvement |  |  |  |  |  | 
Abbreviation |  |  | Name |  |  | 
LB |  |  |  |  |  | 
PP2 |  |  |  |  |  | 
PP3 |  |  |  |  |  | 

## Slide 13: Progress report
Please Describe The Progress In This Reporting Period And Explain How Were Partners Involved And Who Did What |  |  |  | 
NA |  |  |  | 
Please Describe And Justify Any Problems And Deviations Including Delays From The Work Plan Presented In The Application Form And The Solutions Found |  |  |  | 
Please describe progress achieved in this reporting period |  |  |  | 
Activity Number | Activity title | Start month | End month | Status
Deliverable number | Deliverable title | Deliverable description | Planned delivery month | Progress Report Deliverable Description | Status | Deliverable evidence

## Slide 14: Progress report
A.5. Work Package Communication (communication) |  |  |  |  |  | 
WP number | WP title | WP start date | WP end date | WP status | WP expenditure current report | % of WP reported so far
Partners` involvement |  |  |  |  |  | 
Abbreviation |  |  | Name |  |  | 
LB |  |  |  |  |  | 
PP2 |  |  |  |  |  | 
PP3 |  |  |  |  |  | 

## Slide 15: Progress report
Please Describe The Progress In This Reporting Period And Explain How Were Partners Involved And Who Did What |  |  |  |  |  | 
Please Describe And Justify Any Problems And Deviations Including Delays From The Work Plan Presented In The Application Form And The Solutions Found |  |  |  |  |  | 
Communication objectives - what is the progress toward the communication objectives as defined in the application form? The level of achievement should be cumulative; however the explanation should describe achievements in this reporting period |  |  |  |  |  | 
Project specific objectives |  | Level of achievement |  | Explanations |  | 
Please describe progress achieved in this reporting period |  |  |  |  |  | 
Activity Number | Activity title |  | Start month | End month | Status | 
Deliverable number | Deliverable title | Deliverable desription | Planned delivery month | Progress Report Deliverable Description | Status | Deliverable evidence

## Slide 16
Thank you for your attention!