ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Relevant country background	2

1.4.	Current state of affairs in the relevant sector	2

1.5.	Related programmes and other donor activities:	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Consultant	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project intervention	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific activities	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Commencement date & Period of implementation of tasks	4

6.	REQUIREMENTS	4

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Consultant	6

6.4.	Equipment	6

7.	REPORTS	6

7.1.	Reporting requirements	6

7.2.	Submission & approval of reports	7

8.	MONITORING AND EVALUATION	7

8.1.	Definition of indicators	7

8.2.	Special requirements	7

# BACKGROUND INFORMATION

## Beneficiary country

Serbia

## Contracting Authority

City of Zrenjanin

## Relevant country background

N/A

## Current state of affairs in the relevant sector

N/A

## Related programmes and other donor activities:

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To contribute to improve the competitiveness of Banat region as the leader of economic development and improvement of regional economic structure trough provision of regional fair facility.

## Purpose

The purpose of this contract is as follows:

- Successful organization of promotional campaign for the “Hall of Banat Fairs” project in Zrenjanin

## Results to be achieved by the Consultant

The Consultant will be responsible for the following results:

- Development, creation and provision of Promo plan for the “Hall of Banat Fairs” promotional campaign

- Design and publication of 6 newspaper ads or articles about the project in national or regional newspapers

- Development, production and publicity of publicity of 6 TV ads or video clips about the project on national or regional TV stations

- Development, production and publicity of publicity of 14 radio clips about the project on national or regional radio stations

- Design, production and placement of 300 posters around the City and regional roads

- Design, production, printing, renting of space, and installation of 5 billboards in the city of Zrenjanin

- Design, printing and distribution of 2000 flyers thru direct mailing campaign or distribution in retail networks, bookstores, clubs, associations, partners and stakeholders

- Organization of online campaign thru social networks: Facebook, AdWords, Google+, Twitter, and Youtube

- Production of documentary film about the “Hall of Banat Fairs” project

# ASSUMPTIONS & RISKS

## Assumptions underlying the project intervention

N/A

## Risks

N/A

# SCOPE OF THE WORK

## General

### Description of the assignment

For the quality implementation of the project “Hall of Banat Fairs”, particularly its publicity actions, a well-rounded promotional campaign is planned.

The Consultant will in cooperation with our experts prepare, develop and carry out a comprehensive promotional campaign (promo plan, TV, newspapers, radio, posters and billboards, flyers, online campaign, documentary film) aimed at promotion of “Hall of Banat Fairs” project.

This activity will be implemented in close collaboration with the project team members.

### Geographical area to be covered

Zrenjanin, Serbia

### Target groups

SME’s, regional chambers of commerce, fair visitors.

## Specific activities

Promotional campaign is to be provided according to the Practical Guide of the EC, including:

The service will be contracted for a 12 days period of project implementation, and the offer is to be made for lump sum for the complete service of promotional campaign realization.

Promotional campaign info

This Promotional Campaign involves the production of: Promo plan, 6 TV ads/video clips, 6 newspaper ads/articles, 14 radio clips, 300 posters, 5 billboards, 2000 flyers, online campaign, and documentary film.  Promotional campaign, targeting the project related target groups and general public, are to address the following project related themes identified by the Contracting Authority:

1) “Hall of Banat Fairs” project activities and results

2) Promotion of new regional fair facility

The service contains:

1. Preparation of the Promo plan

The Consultant is obliged to prepare Promo plan – document which will incorporate all sub activities including clear plan for activity realization. Promo plan will describe visual identity standard for the “Hall of Banat Fairs” project including: graphic design rules for printing, web materials, project logo, video and audio materials. This document will also include media plan for broadcast of project related TV and radio ads on local and national media.

The Consultant is obliged to prepare Promo plan in accordance with the Plan of project activities and Communication and Visual Identity Manual of the Romania-Republic of Serbia IPA Cross-border Cooperation Programme. These documents will be provided to Consultant by the Contracting Authority.

The Consultant is obliged to prepare the Promo plan and all of its content, in Serbian and English language as it will serve as the official project document, and send the prepared Promo plan by e-mail to the Contracting Authority, preferably in .pdf format.

Time frame for realization: 5 days after the signing of the contract

2. Design and publication of 6 newspaper ads/articles in national or regional newspapers

This part of promotional campaign involves the design and publication of a 6 ads/articles in various national/regional newspapers in Serbian language. The ads should be produced in a form of promo articles dedicated to “Hall of Banat Fairs” project activities. The Contracting Authority will provide the Consultant with text content. However, any graphics, photos, cartoons or other illustrations have to be provided by the Consultant. It is essential that any graphics, photos, as well as any other illustrations are original.

The Consultant will be responsible for the following deliverables:

- Submit a detailed newspaper campaign plan. This is to include, for each of the two themes, the frequency when the ads/articles will feature as well as the, size of the promo text, choice of national/regional newspaper and the circulation of each of the newspaper in which the ads will be published;

- Make any changes to the newspaper campaign plan requested by the Contracting Authority. Once the newspaper campaign plan is approved by the Contracting Authority, the Consultant is to start coordinating the publication of all slots with the various newspapers. This also involves all the necessary administrative work including booking of the space for ads/articles in newspapers;

- Provide the necessary artwork for the printing of ads of an adequate size that ensures visibility;

- Design and ensure the publication of ads in newspapers;

- Forward electronic copy of the design of the ads (readable on all computer systems) to the Contracting Authority for verification and final approval before going for print;

- Cost of publication of 6 ads in local/regional newspapers will be paid by Consultant;

- Ensure that the newspaper ads are prepared in accordance to the Promo plan of the project developed under Point 1.

- Ensure that the layout of ads/articles is in line with the Visual Identity Manual of the Romania-Republic of Serbia IPA Cross-border Cooperation Programme. This document will be provided to Consultant by Contracting Authority, and can also be seen and downloaded at web link: http://www.romania-serbia.net under the information and publicity section of the web site.

Time frame for realization:

- Contracting Authority is obliged to prepare and deliver list of themes and text content for newspaper ads/articles to the Consultant in 3 days after the signing of contract;

- Consultant is obliged to prepare the newspaper campaign plan, along with draft of 6 newspaper ads, and deliver to the Contracting Authority no later than 5 days from the signing of the contract;

- If the Contracting Authority has any comments or request for changes in the newspaper campaign plan or content of the ads, the Consultant is obliged to accept the request and deliver changed version of campaign plan and/or newspaper ads in 2 days from the acceptance of request for changes from Contracting Authority;

- After the final version of 6 newspaper ads is approved by Contracting Authority, the Consultant will proceed with booking of the advert space in the newspaper, printing and publication;

- 6 newspaper ads must be published in 3 days after the approval by the Contracting Authority.

3. Development, production and publicity of 6 TV ads/clips for a public promotional campaign

The Consultant will be responsible for the following deliverables:

- Producing 6 video clips of a duration of minimum 1 (one) and maximum 3 (three) minutes each;

- Developing and providing concepts, related to the list of themes that will be prepared by Contracting Authority, for each video clip (6 in total) as approved by the Contracting Authority before the actual production is carried out;

- Creating a script and a story board for all video clips which have to be approved by the Contracting Authority;

- Minimum 4 hours of filming of video clips in various locations;

- Consultant is obliged to edit previously filmed raw material and create 4 video clips from that material with duration of minimum 1 minute and maximum 3 minutes each;

- All video clips must be sent to Contracting Authority for approval and in case of any request for changes by Contracting Authority, Consultant is obliged to make requested changes in video clips and send them again to Contracting Authority for approval;

- Developing video clips in a format that can be also uploaded on local websites, social networking sites, TV, Radio and Online Advertising on Web portals;

- The final versions of all 6 video clips must also be delivered in a HD format that is readable on all computer systems;

- Book air time and provide the necessary arrangements for broadcasting of 6 TV adverts/clips of minimum one (1) minute duration each and maximum 3 (three) minutes each;

- Provide a detailed TV campaign plan. This is to include the number of ads to be used in the publicity campaign as well as the time when the ads are scheduled to be broadcast;

- Ensure that the ads are broadcasted on at least 2 local TV stations and 1 regional TV station;

- Cost of broadcasting of 6 video clips on above mentioned TV stations will be paid by Consultant;

- Make all necessary changes to the TV campaign plan as may be requested by the Contracting Authority. Once the TV campaign plan is approved by the Contracting Authority, the Consultant is to start coordinating all slots with the various TV stations. This includes all the necessary administrative work including bookings.

Time frame for realization:

- Contracting Authority is obliged to prepare and deliver list of themes for TV ads to the Consultant in 2 days after the signing of contract;

- Consultant is obliged to start the filming no later than 2 days from the date of signing of the contract;

- First draft of filmed and produced material should be delivered by Consultant to the Contracting Authority no later than 7 days from the signing of the contract;

- If the Contracting Authority has any comments or request for changes in the video material, the Consultant is obliged to accept the request and deliver changed version of video material in 3 days from the acceptance of request for changes from Contracting Authority;

- After the final version of 6 video clips is approved by Contracting Authority, the Consultant will proceed with booking of air time on TV stations and organization of broadcast of TV ads.

- Broadcast of 6 TV ads must be realized in 3 days after the approval by the Contracting Authority.

4. Development, production and publicity of 14 radio clips for a public promotional campaign

The Consultant will be responsible for the following deliverables:

- Producing 14 audio clips of a duration of minimum 1 (one) and maximum 3 (three) minutes each;

- Developing and providing concepts, related to the list of themes that will be prepared by Contracting Authority, for each video clip (14 in total) as approved by the Contracting Authority before the actual production is carried out;

- Creating a script and a story board for all audio clips which have to be approved by the Contracting Authority;

- Minimum 2 hours of audio recording;

- Consultant is obliged to edit previously recorded raw material and create 14 audio clips from that material with duration of minimum 1 minute and maximum 3 minutes each;

- All audio clips must be sent to Contracting Authority for approval and in case of any request for changes by Contracting Authority, Consultant is obliged to make requested changes in video clips and send them again to Contracting Authority for approval;

- Developing audio clips in a format that can be also uploaded on local websites, social networking sites, TV, Radio and Online Advertising on Web portals;

- The final versions of all 14 audio clips must also be delivered in a audio format that is readable on all computer systems;

- Book air time and provide the necessary arrangements for broadcasting of 14 radio clips of minimum one (1) minute duration each and maximum 3 (three) minutes each;

- Provide a detailed Radio campaign plan. This is to include the number of ads to be used in the publicity campaign as well as the time when the ads are scheduled to be broadcast;

- Ensure that the ads are broadcasted on at least 2 local radio stations and 1 regional radio station;

- Cost of broadcasting of 14 video clips on above mentioned TV stations will be paid by Consultant;

- Make all necessary changes to the Radio campaign plan as may be requested by the Contracting Authority. Once the Radio campaign plan is approved by the Contracting Authority, the Consultant is to start coordinating all slots with the various TV stations. This includes all the necessary administrative work including bookings.

Time frame for realization:

- Contracting Authority is obliged to prepare and deliver list of themes for radio clips to the Consultant in 2 days after the signing of contract;

- Consultant is obliged to start the audio recording no later than 3 days from the date of signing of the contract;

- First draft of recorded and produced material should be delivered by Consultant to the Contracting Authority no later than 5 days from the signing of the contract;

- If the Contracting Authority has any comments or request for changes in the audio material, the Consultant is obliged to accept the request and deliver changed version of audio material in 2 days from the acceptance of request for changes from Contracting Authority;

- After the final version of 14 audio clips is approved by Contracting Authority, the Consultant will proceed with booking of air time on Radio stations and organization of broadcast of radio clips ads.

- Broadcast of 14 radio clips must be realized in 5 days after the approval by the Contracting Authority.

5. Design and preparation of 300 posters

Posters will feature project introduction and promo message regarding opening of new regional fair facility – Hall of Banat Fairs. Posters will be prepared in English and Serbian language and will be set/displayed at the most noticeable and prominent places and alongside main roads in the City of Zrenjanin.

The Consultant should produce:

- Posters - 300 pcs / minimum specification: high quality paper, 4 colours, 1 page, min. format A2

The Consultant should prepare posters in accordance with instructions given by the Contracting Authority.

The Contracting Authority is obliged to prepare all text for posters. The Contracting Authority and Consultant will work together on preparation of logos (EU logo, logo of the Cross-border program Romania-Serbia, Project logo, etc.) in accordance with standards developed under Point 1 Promo plan.

The Consultant should prepare at least two versions of the posters and send it to the Contracting Authority in electronic form, via e-mail, or on CD. The Contracting Authority will select one of the offered designs. If the Contracting Authority is not satisfied with any of offers, the Consultant is obliged to prepare new one.

The Consultant is obliged to prepare final version of design of posters at least 8 days after the start of the contract.

The Consultant should print selected design of posters and organize placement of posters at the most noticeable and prominent places and alongside main roads in the City of Zrenjanin.

Time frame for realization: 8 days after the signing of the contract

6. Design and preparation of 5 billboards

The Consultant will be responsible for the following deliverables:

- 5 Billboards (with message about the “Hall of Banat Fairs” project, organizers, donors) to be displayed at the most noticeable and prominent places and alongside main roads in the City of Zrenjanin, during the project. Billboard specifications: min. size 4 x 3 m, high quality paper, 4 colours.

The Consultant will need to cover renting space costs and provide installation services for the billboards.

Billboards must stay in place for 25 days.

The Consultant must, during the development-designing, ensure that the layout of billboards is in line with the Visual Identity Manual of the Romania-Republic of Serbia IPA Cross-border Cooperation Programme. This document will be provided to Consultant by Contracting Authority, and can also be seen and downloaded at web link: http://www.romania-serbia.net under the information and publicity section of the web site.

Time frame for realization:

- Contracting Authority is obliged to prepare and deliver the content for billboards to the Consultant in 3 days after the signing of contract;

- Consultant is obliged to prepare the draft version of billboard design, and deliver to the Contracting Authority no later than 5 days from the signing of the contract;

- If the Contracting Authority has any comments or request for changes in the billboard design, the Consultant is obliged to accept the request and deliver changed version of billboard design in 2 days from the acceptance of request for changes from Contracting Authority;

- After the final version of billboard visual design is approved by Contracting Authority, the Consultant will proceed with renting of the billboard space, printing and installation of billboards;

- 5 billboards must be placed in 5 days after the approval by the Contracting Authority

7. Design and preparation of 2000 flyers

Flyers will feature project introduction and promo message regarding opening of new regional fair facility – Hall of Banat Fairs. Flyers will be prepared in English and Serbian language and will be distributed to the target groups.

The Consultant should produce:

- Flyers - 2000 pcs / minimum specification: A4 format, printed 4 / 4, on paper 135g glossy;

The Consultant should prepare flyers in accordance with instructions given by the Contracting Authority.

The Contracting Authority is obliged to prepare all text for flyers. The Contracting Authority and Consultant will work together on preparation of logos (EU logo, logo of the Cross-border program Romania-Serbia, Project logo, etc.) in accordance with standards developed under Point 1 Promo plan.

The Consultant should prepare at least two versions of the flyers and send it to the Contracting Authority in electronic form, via e-mail, or on CD. The Contracting Authority will select one of the offered designs. If the Contracting Authority is not satisfied with any of offers, the Consultant is obliged to prepare new one.

The Consultant is obliged to prepare final version of design of flyers at least 7 days after the start of the contract.

The Consultant should print selected design of flyers and organize distribution to target groups in accordance with instructions given by the Contracting Authority.

Time frame for realization: 10 days after the signing of the contract

8. Organization of online campaign

The Consultant will be responsible for the following deliverables:

8.1 Facebook campaign including:

- Opening of the Facebook profile for “Hall of Banat Fairs” project;

- Planning of Facebook campaign with duration of 20 days

- Writing and publishing of PR texts

- Publication of photos and video clips, created in production of documentary film

- Creation and publication of ads/banners

8.2 AdWords campaign including:

- Opening of the AdWords profile for “Hall of Banat Fairs” project;

- Planning of campaign with duration of 20 days

- Creation of Google ads

- Key wording for the ads

- Publication and management of ads/banners

8.3. Google+ campaign including:

- Opening of the Google+ profile for “Hall of Banat Fairs” project;

- Planning of campaign with duration of 20 days

- Creation and publication of Google+ ads/banners

8.4. Twitter campaign including:

- Opening of the Twitter profile for “Hall of Banat Fairs” project;

- Planning of campaign with duration of 20 days

- Creation and publication of Twitter ads/banners

8.5 Youtube profile including:

- Opening of the Youtube profile for “Hall of Banat Fairs” project;

- Creation and publication of video clips

Time frame for realization: 10 days after the signing of the contract

9. Production of documentary film about the “Hall of Banat Fairs” project

This part of promotional campaign involves the production of the documentary film about the “Hall of Banat Fairs” project. Documentary film should present in detail the reconstruction and adaptation of the old sports hall in Zrenjanin into multifunctional space thru video recordings of exterior and interior of the object, before and after the reconstruction, presentation of the practicality of the new space, interviews with project and city representatives, and video footage taken on the city of Zrenjanin streets and Vojvodina region. Documentary should be synchronized in English and Serbian, 30 minutes length and will have two short versions, 3 minute and 7 minute long for promotion of the project.

Documentary film should cover:

- Filming of existing state of facilities: A look at pre adaptation, interior and exterior of buildings in the existing state, interview with the project team

- Filming of construction works during the remodelling and construction: interior and exterior of buildings in the existing situation, with footage of construction work, interviews with the project manager, designers and architects in the location

- Filming of facilities after completion of construction and adaptation: footage of interior and exterior of buildings, equipment for fair activities, interview with the Mayor of Zrenjanin, project manager and designer

- 6 interviews with competent speakers / officials selected by Contracting Authority

- Filming of scenes in Zrenjanin and Vojvodina: filming attractions of Zrenjanin and Vojvodina. This footage should be used to cover off-text that talks about the geo-strategic, economic, tourist and ethnographic characteristics of Zrenjanin and the region.

Time frame for realization: Preproduction 3 days, Production 5 days, Postproduction 3 days

## Project management

### Responsible body

The Consultant is responsible for all activities regarding this contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Željko Kevrešan, project manager.

### Facilities to be provided by the Contracting Authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

Zrenjanin, Srednje-Banatski district, Serbia.

## Commencement date & Period of implementation of tasks

The intended commencement date is date of signature of the contract by both parties and the period of implementation of the contract will be 12 days from this date. Please refer to Articles 4 and 5 of the Special Conditions for the actual commencement date and period of implementation.

# REQUIREMENTS

## Personnel

### Key experts

No key experts (those who have a crucial role in implementing the contract) are requested for this contract.

### Other experts, support staff & backstopping

The contractor will ensure sufficient number of qualified experts for quality and timely implementation of tasks planned by these Terms of References. These experts are considered as non-key experts therefore their CVs are not examined prior to the signature of the contract and should not be included in the tender.

The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Consultant.

## Facilities to be provided by the Consultant

The Consultant shall ensure any other facilities, including the transportation means, necessary for quality and timely implementation of the tasks described in these Terms of Reference.

If the Consultant is a consortium, the arrangements should allow for the maximum flexibility in project implementation. Arrangements offering each consortium member a fixed percentage of the work to be undertaken under the contract should be avoided.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority as part of this service contract.

The contractor will provide all the equipment necessary for timely and quality implementation of the tasks described in these Terms of Reference.

# REPORTS

## Reporting requirements

The consultant will submit the following reports in English language in one original and 1 copy:

The contractor will prepare final report on the implementation of the tasks, at the end of this contract. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions.

The required formats of the reports will be communicated to the Contractor by the Contracting Authority after the signature of the contract.

## Submission & approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

’Services provided in timely, quality and quantity manor, as required in these Terms of Reference’’

## Special requirements

N/A

* * *