ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania and Republic of Serbia

## Contracting Authority

Regional Office for Cross-border Cooperation Timisoara (RO CBC Timisoara)

## Country background

The Interreg-IPA Cross-Border Cooperation Romania-Serbia Programme is funded by the European Union under the framework of the new Instrument for Pre-accession Assistance (IPA II), the Cross-border Cooperation (CBC) Component and co-financed by the Partner States in the Programme. The Programme focuses on increasing the overall competitiveness of the economy in the Romania-Serbia border area and on the improvement of the quality of life for the border communities in both countries. The 2014-2020 Programme is the continuation of the Romania-Republic of Serbia IPA CBC Programme financed for the 2007-2013 period.

## Current situation in the sector

- All participating partners from Romania and Serbia use the same rules, implement projects jointly, and manage budgets together. This enables the establishment of long-lasting contacts between people, and joint cross-border activities to help economic development, support small-scale infrastructure, protect the environment, and foster research, culture, and education. It also increases the overall social cohesion along EU external borders. Furthermore, through the process of project identification, applying for funds and project implementation, partners from candidate countries gain valuable experience in management of EU funds. More information can be accessed via www.romania-serbia.net.

## Related programmes and other donor activities

NA

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

•	To support the successful implementation of the Interreg-IPA Cross-Border Cooperation Romania-Serbia Programme by ensuring an effective communication and information activity towards the potential applicants of the Programme.

## Purpose

The purpose of this contract is as follows:

- •	To create the premises for a high absorption capacity in the eligible area of Interreg-IPA CBC Romania-Serbia Programme by ensuring that all relevant information reaches the potential applicants in order for them to prepare solid project proposals for the second call for projects proposals. The Contractor needs to provide administrative and logistical support to the Joint Secretariat from the Regional Office for Cross-Border Cooperation Timisoara in launching the second call for project proposals and in the dissemination of information relating to the second call of proposals under the Interreg-IPA CBC Romania-Serbia Programme, in the Romanian and Serbian eligible area.

## Results to be achieved by the Contractor

- Organization of 4 events for potential applicants in the eligible area of the Programme (2 in Romania, 2 in Serbia), in the form of training seminars on project development.                  Indicative calendar: September 2017.

- Organization of 1 Launch event for the second call for project proposals of the Interreg-IPA Cross-border Cooperation Romania-Serbia Programme in the eligible area of the Programme.                 Indicative calendar: October 2017.

- Organization of 2 Partner Search Forum events for the second call for project proposals in the eligible are of the Programme (1 in Romania, 1 in Serbia).                                                        Indicative calendar: September – October 2017.

- Organization of 8 events for potential applicants of the second call for proposals (4 in Romania, 4 in Serbia) in the eligible area of the Programme, on the Guidelines for Applicants, rules etc. Indicative calendar: October – December 2017.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

•	It is important to have a smooth cooperation between the RO CBC Timisoara staff the Contractor. The Contactor must provide the administrative and logistic support for the development and execution of the events. The visibility requirements of all documents provided during the events will be closely verified by the Contracting Authority.

•	The staff of the contractor and the RO CBC Timisoara will communicate well in advance related to any changes in scheduling or location.

## Risks

•	Delays/changes in providing the appropriate venue and setting the dates for the events.

# SCOPE OF THE WORK

## General

### Description of the assignment

In order to ensure both the promotion of the new call for proposals and the information required to access this type of funding to potential applicants, it is necessary to organize events in the eligible area of the Programme which are close to potential applicants. With these events, the applicants will have the opportunity to find out about the second call of the Programme, clarify certain aspects related to the development and implementation of such projects and ensure networking with other potential applicants.

During the first series of events, RO CBC Timisoara consultants will provide the information required by an applicant to develop and submit a project proposal and request financing under the programme.

The information events and the launch, dedicated to the potential applicants of the second call for proposals, are designed to meet their information needs related to the rules of the Guidelines for applicants and the implementation of their projects, therefore the topics will concern the requirements for projects financed under the Interreg-IPA CBC Romania-Serbia Programme.

The partner search forum events are suitable for those potential applicants who have not yet found a cross-border partner or want to extend their partnership.

The Contractor will ensure external expertise in delivering the administrative and logistical organization of events for potential applicants, for the successful implementation of the Programme.

### Geographical area to be covered

•	Activities that will be delivered in the present service contract can be found in the eligible area of the Interreg-IPA CBC Romania – Serbia Programme: in Romania – Timis, Caras-Severin and Mehedinti counties and in Republic of Serbia – North Banat, Central Banat, South Banat, Borski, Branicevski and Podunavski districts.

### Target groups

•	Romanian and Serbian potential applicants, beneficiaries, stakeholders of the Interreg-IPA CBC Romania – Serbia Programme.

## Specific work

Activity 1 – Ensuring the necessary administrative and logistical support for the organization of 4 events for potential applicants in the eligible area of the Programme (2 in Romania, 2 in Serbia), in the form of training seminars on project development.

The aim is the organization of 4 events for potential applicants of the second call for proposals (2 in Romania, 2 in Serbia) in the eligible area of the Programme.

The tasks required to be performed for this activity in order to achieve the contract results are the following:

- the Contractor will provide appropriate location and facilities: conference room facilities, arranging the materials and the identification paper cards on tables, installing and verifying the equipment – laptop, projector, projector screen etc.

- the Contractor will provide light catering during one coffee break per event (coffee/ tea, juice, light sweet and sandwiches) and sparkling/ still water for all participants during the meeting.

- the Contractor will provide the administrative and logistical support to the consultants from the Contracting Authority, according to the JS/JS Antenna request.

Activity 2 – Ensuring the necessary administrative and logistical support for the organization of 1 Launch event for the second call for project proposals of the Interreg-IPA Cross-border Cooperation Romania-Serbia Programme in the eligible area of the Programme.

- The aim of the activity is the organization of 1 event for the launch of the second call for proposals in the eligible area of the Programme, addressed to potential applicants, stakeholders, journalists, institutional partners etc.

The tasks required to be performed for this activity in order to achieve the contract results are the following:

- the Contractor will provide appropriate location and facilities: conference room facilities, arranging the materials and the identification paper cards on tables, installing and verifying the equipment – laptop, projector, projector screen etc.

- the Contractor will provide light catering during one coffee break per event (coffee/ tea, juice, light sweet and sandwiches) and sparkling/ still water for all participants during the meeting.

- the Contractor will provide the administrative and logistical support to the consultants from the Contracting Authority, according to the JS/JS Antenna request.

Activity 3 – Ensuring the necessary administrative and logistical support for the organization of 2 Partner Search Forum events for the second call for project proposals in the eligible are of the Programme (1 in Romania, 1 in Serbia).

- The aim of the activity is the organization of 2 PSF events in the eligible area of the Programme.

The tasks required to be performed for this activity in order to achieve the contract results are the following:

- the Contractor will provide appropriate location and facilities for approximatively 120 persons in the eligible area of the Programme. The facility should be located in an accessible place and should have all the facilities for organization of such event: audio system, headphones for translation, chairs, tables, a place where to received participants, video projector, projection screen, laptop, etc.

- the Contractor will provide light catering services for the participants to the each event: coffee, juices, mineral and still water, sweets and salted snacks.

- the Contractor will provide lunch meal for all participants.

- the Contractor will assist RO CBC Timisoara team during the event from a logistics point of view – handling the projection and sound system equipment, etc.

- the Contractor will provide the administrative and logistical support to the consultants from the Contracting Authority, according to the JS/JS Antenna request.

- the Contractor will ensure stationary for the events and other materials necessary for organising the events (badges, folders etc.), according to the JS/JS Antenna request.

- the Contractor will provide 10 interpreters during each event (for Serbian and Romanian languages), the Contractor will provide the transport, meal and accommodation for translators if necessary.

Activity 4 – Ensuring the necessary administrative and logistical support for the organization of 8 events for potential applicants of the second call for proposals (4 in Romania, 4 in Serbia) in the eligible area of the Programme, on the Guidelines for Applicants, rules etc.

- The aim of the activity is the organization of 8 events in the eligible area of the Programme (workshops/ seminars/ trainings etc).

The tasks required to be performed for this activity in order to achieve the contract results are the following:

- the Contractor will provide appropriate location and facilities: conference room facilities, arranging the materials and the identification paper cards on tables, installing and verifying the equipment – laptop, projector, projector screen etc.

- the Contractor will provide light catering during one coffee break per event (coffee/ tea, juice, light sweet and sandwiches) and sparkling/ still water for all participants during the meeting.

- the Contractor will provide the administrative and logistical support to the consultants from the Contracting Authority, according to the JS/JS Antenna request.

General rules:

For all events, the Contractor and the Contracting Authority team will work together in order to provide efficient events and supply the necessary information for developing projects under the second call for proposals of the Interreg-IPA CBC Romania-Serbia Programme, to all participants. The indicative number of participants per event: average of 55 for events dedicated to potential applicants and an average of 120 people / event for PSF events. This is subject to change therefore, for every occasion, the Contracting Authority will inform the Contractor on this matter.

Consultants from the Contracting Authority team will lead the events and define the content of the events while the Contractor will effectively organize the events.

The location, facilities and dates for each event will be agreed upon between the Contractor and the Contracting Authority in advance and any changes will be communicated as soon as possible in order not to jeopardize the organization of the events.

## Project management

### Responsible body

The Joint Secretariat, Human Resources and Communication Office and the Financial, Accounting and Administrative Department within the Regional Office for Cross-Border Cooperation Timisoara will be responsible for managing the contract.

### Management structure

The management structure of the Regional Office for Cross-Border Cooperation Timisoara is:

-Executive Director;

-Internal audit;

-Economic Director;

-Joint Secretariat Department;

-First Level Control Unit;

-Human Resources and Communication Office;

-Financial, Accounting and Administrative Department;

-Promotion and Cooperation Department.

### Facilities to be provided by the Contracting Authority and/or other parties

NA

# LOGISTICS AND TIMING

## Location

The location of the operational base for the project will be in Timisoara, Romania.

## Start date & Period of implementation of tasks

The intended start date is 06.09.2017 (the estimated date of signing the contract) and the period of implementation of the contract will be 16 months from this date, no later than 31st of December 2018. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Team Leader

Qualifications and skills

- Adequate working experience in client oriented activities;

- Good knowledge of English.

- Computer skills – Knowledge of Microsoft Office and Internet.

General professional experience

- Participation as team leader/equivalent position in one other project/contract.

Specific professional experience

- Participation in organising and ensuring the logistics for at least one event.

Key expert 2: Assistant

Qualifications and skills

- Adequate working experience in client oriented activities;

- Good knowledge of English.

- Computer skills - basic.

General/Specific professional experience

- Participation in one other project/contract in the field of organising events.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office and accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and one copy:

- Inception Report of maximum 12 pages to be produced after maximum two weeks from the start of implementation. In the report the Contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The Contractor should proceed with his/her work unless the Contracting Authority sends comments on the inception report.

- Interim Technical Reports regarding the delivery of the activities according to the Orders issued by the Contracting Authority.

- The Contractor will prepare these interim reports after providing the services according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments.

- Draft final report of maximum 12 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on the services provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference”.

## Special requirements

Not applicable.