ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania

## Contracting Authority

Intercultural Institute Timișoara

## Country background

The Interreg - IPA CBC Romania – Serbia Programme is a continuation of previous CBC programmes, under the framework of the new Instrument for Pre-accession Assistance (IPA II). The Programme is the result of a co-operative effort by the Romanian and Serbian national, regional and local authorities.

## Current situation in the sector

In September 2016 Timisoara was selected as European Capital of Culture. The Bid Book was based on cultural development strategy for the period 2014-2024 developed under a project implemented in the years 2013/14 by the Contracting Authority. That project was Poles of Cultures - Cultural Policy as a Tool for Community and Regional and involved five project partners: three local public administrations (Timisoara, Pancevo and Zrenjanin) and two civil society organizations (Intercultural Institute Timisoara and Civic Parliament Vrsac).

The project of which this contract will be a part is titled InclusiveArt – Access to Culture for Disadvantaged Children and Youth and it involves It implies a dynamic partnership formed by two NGO (Intercultural Institute Timisoara and Nevo Parudimos from Resita), one local Public Authority (City of Zrenjanin) and one Public cultural institution (Center for Fine and Applied Arts Terra, Kikinda).

Now the cultural sector in Timisoara is under construction, creative entrepreneurship and cross border cooperation, contributes to its development.

## Related programmes and other donor activities

Not Applicable

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To increase the potential of the local communities and disadvantaged groups for innovative inclusive social practices by using art and culture to create inclusive contexts for integration and creative growth.

## Purpose

The purposes of this contract are as follows:

- To develop entrepreneurial and marketing competences of young creative people from Romania – Serbia CBC region.

- to develop a favourable frame for learning by ensuring adequate location, spaces, materials and equipment, meals, accommodation and covering transportation of participants.

## Results to be achieved by the Contractor

- Organisation of Training in cultural entrepreneurship for min. 40 young people from the selected communities and programme area. Organised in two training groups with 6 training days per group. The training will be delivered by contractors’ trainers and by trainers from IIT.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The Contractor will receive the relevant information – content and visibility – from the Contracting Authority and the staff involvement will be ensured.

## Risks

Risk 1: Probability that some activities are delayed because the subcontractor do not keep the terms. Measure:  Firm contracts with service provider that include penalties for delays, according to the law

Risk 2: Low quality of project products/outputs, due to the unsatisfactory performance of the subcontractor. Measure: Clearly defining the obligations of the service provider, both in the TOR and in the contract; constant monitoring of the activities undertaken by the service provider; approval of proposed materials; mentioning of the penalties for delays in the contracts with the subcontractor.

Risk 3: Maladjustment of some beneficiaries to the training activities. Measure: Ensuring reserve lists to replace beneficiaries who might drop out; ensuring alternative work methods in the mentoring period, which stimulate them to participate. Partners commit to supporting and mobilizing participants from their areas.

# SCOPE OF THE WORK

## General

### Description of the assignment

To organise a training in cultural entrepreneurship for 2 groups of 20 participants (20x2=40 participants)

### Geographical area to be covered

The trainings should take place in the area of the Interreg - IPA CBC Romania – Serbia Programme

### Target groups

40 young people from the selected communities and programme area

## Specific work

The consultant will organise and deliver a 6 day training seminar in cultural entrepreneurship and art market orientation for 2 groups of minimum 20 young people (per group) from the communities involved in the project and programme area. The working language of the training will be English.

Indicative curricula will propose: business legislation, setting up a company, business plan, project management, IT, marketing of arts, financial management; communication in professional setting, portfolio design and presentation, teamwork and personality types, introduction to labour market and guidance. The consultant will cooperate with CA in the process of preparation of training delivery. After a needs analysis, these modules may have different shares in the teaching process or will be replaced/ supplemented with others.

In order to achieve the best learning environment the 40 participants will be organised in two mixed groups, 20 participants / group. The training module should be delivered to each group by min. 3 trainers from the subcontractor during a period of minimum 4 days per training module and 2 trainers from the Contracting Authority during a minimum 2 days /module. The CA trainers will prepare an introductive training in Project management and an introductive training in Creative entrepreneurship with good practice examples. For the part of the training delivered by subcontracted trainers the materials are to be developed and agreed in consultation with the CA at least two weeks before the delivery of the training.

In the evenings the Consultant is to provide team building and recreational activities that will challenge the participants and will create a good working environment. The number of activities and the theme will be established together with the CA and will be included in the Training Agenda for improving team cohesion and facilitation of good communication, during the event.

The Consultant is to provide:

- means to ensure proper organisation of the training, the training room with natural light and all the facilities needed for a good learning process

- training materials (hand-outs) and teaching equipment needed

- means to cover the costs of all meals including 2 coffee breaks per day (water, tea, coffee, fruit and pastry), the costs of accommodation for participants and trainers at min. two stars hotel or pension in decent rooms with max. 3 beds per room;

- means to cover the costs of transportation of the participants by car, train or bus.

- Means to ensure participation of the trainers from CA and Inclusive Art project staff during the whole event (max 4 persons).

The consultant will assist CA in selection of participant, need assessment, and promotion of the training opportunity. The criteria for selecting participants and their final list for the training sessions will be established in consultations within the Inclusive Art project partnership and it will be delivered in advance to the Consultant.

At the end of the training The Consultant will carry out an evaluation module and will deliver a report. After the training the Consultant will assist the trainees and CA, via internet, in preparation of at least 10 draft entrepreneurial plans (started during the training) by the young persons trained in a framework of a two month mentoring period conducted by the CA. During the mentoring period meetings with successful young entrepreneurs will be organised. At least 3 good practices examples of young entrepreneurs should be presented in mentoring context.

We believe that the practices developed by this project and its outcomes can be sustained and transferred in a context which will in near future invest more in the development of culture and inclusion of disadvantaged groups and this is the context created by Timisoara European Capital of Culture and European Social Fund.

The Contractor must also comply with the latest Communication and Visibility Manual of the Interreg - IPA CBC Romania – Serbia Programme. All communication materials will follow the visual identity from the Manual and receive feedback from CA.

## Project management

### Responsible body

The team of “InclusiveArt – Access to Culture for Disadvantaged Children and Youth” project from the Intercultural Institute of Timisoara is responsible for managing the contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Calin Rus -Training Manager. Corina Raceanu, the Project Director, and Marcel Bajka, the Project Coordinator, will assist it step by step.

### Facilities to be provided by the Contracting Authority and/or other parties

The Contracting Authority will provide its staff (team) that will hold a part of the trainings, lectures and presentations. The Contracting Authority will be represented by the Training Director together with the Project Director and the Project Coordinator of the Inclusive Art project.

# LOGISTICS AND TIMING

## Location

The Contracting Authority is located in Timisoara.

The location of the training venue will be agreed with the CA.

## Start date & Period of implementation of tasks

The intended start date is the date of contract signature and the period of implementation of the contract will be 5 (five) months from this date. According to Articles 19.1 and 19.2 of the Special Conditions, the actual start date and period of implementation will be defined by the Contracting Authority at the signing of the contract.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key expert 1: Team Leader entrepreneurship trainer

Qualifications and skills

- University degree in economics and / or social sciences and / or technical sciences or equivalent

- Adequate working experience in training activities;

- Ability to deliver training in English.

- Computer skills - Knowledge of MS Office and Internet.

- Proven entrepreneurship competence

General professional experience

- Participation as team leader/equivalent position in one other project/contract.

Specific professional experience

- Participation in organising and ensuring the logistics for at least one training event.

- Participation in one other project/contract as a trainer.

Key expert 2: Trainer in marketing

Qualifications and skills

- University degree in economics and / or arts and / or social sciences or equivalent

- Adequate working experience in training activities;

- Ability to deliver training in English.

- Computer skills - Knowledge of Microsoft Office and Internet.

- Familiarity with marketing online tools

General professional experience

- Professional experience related to marketing trainings

Specific professional experience

- Participation in one other project/contract as a trainer.

Key expert 3: Trainer business plan preparation

Qualifications and skills

- University degree in economics and / or social sciences or equivalent

- Adequate working experience in training activities;

- Ability to deliver training in English.

- Computer skills - Knowledge of Microsoft Office and Internet.

General professional experience

- Professional experience related to company start up, development and management

Specific professional experience

- Participation in one other project/contract as a trainer.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language in one original and one copy:

- Interim reports (if it is the case). The contractor can prepare interim reports after providing the services, or a part of the services, according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments as indicated in the Special Conditions.

- Draft final report of maximum 12 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 4 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on services provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality and quantity manor, as required in these Terms of Reference.

## Special requirements

Not applicable