ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

CHAMBER OF COMMERCE AND INDUSTRY OF SERBIA

Regional chamber of commerce and industry of the South Banat administrative district

## Country background

Area targeted by project activities, Tamis (Timis) river valley, is a “backbone” of the Banat region because it runs through middle of the area. This is unique opportunity to the partners to develop and improve new touristic product on the whole territory of the Tamis (Timis) river valley. Also, data previously provided by series of CBC project give the partners excellent base that their mission is feasible, socio-economically rationale and environmentally acceptable. Number of targeted area inhabitants and number of potential touristic and visitors give the partners another support for the planning of the engaged stakeholders and investment that could realise such a challenge and established something new that will be sustainable and serve as an example for others.

## Current situation in the sector

- Project with encompass Tamis (Timis) river valley. The Timis or Tamis is a 359km long river originating from Semenic Mountains, southern Carpathian Mountains, Caras-Severin Country, Romania. It follows through the Banat region and flows into the Danube near Pancevo, in northern cultural and sport spots dispersed in its valley represent potential touristic jewel. In this surrounding there are several towns (Timisoara, Lugoj, Caransebes, Resita, Zrenjanin and Pancevo) and about 100 other smaller settlements with about 700.000 inhabitants. Also, this area is very good connected with Danube waterway (EU corridor 10) and the Serbian Capital Belgrade.

- All of these potentials are highly suitable for the creation of new touristic product “Eco Tamis (Timis)” which encompasses five eco elements: hike, bike, canoe, sport fishing and bird watching. Also, the territory of the new touristic product is compact and in previous CBC projects (“Eco status of the Tamis (Timis) river” and “Measures for protection of the Tamis river “STEP 2”) all aspects of socio-economic and ecological development were analysed in details. Tourism, beside agriculture, was mentioned as one of the main opportunity and challenge for development. Proposed project will take into consideration these conclusions and through project activities will develop and realised new touristic product in the whole area of the Tamis (Timis) river valley. On that way new jobs will be created and income generated in the target area and in same time environment will be used in ecologically sage way as touristic resource.

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project is to contribute to the economic and social development in the Tamis (Timis) river valley, backbone of Banat region, through the development of a new joint tourism product.

The overall project objective will directly contribute to the Programme specific objective 4-1. ”Investments for the growth of the demand of local tourism networks and promotion of innovative tourism activities”.

## Purpose

The purpose of this contract is to organize various trainings in order to raise capacities of the tourism stakeholders from sites in the Tamiš (Timiš) river valley. Four different trainings will be organized:

- Trainings for representatives of local-self governments

- Trainings for animators in tourism

- Trainings for promote local micro businesses

- Trainings of accessory stakeholders in tourism

## Results to be achieved by the Contractor

            - Two two-day trainings for representatives of local-self-government organized, 40 representatives trained, training material produced;

            - Three three-day trainings for animators in tourism organized, 60 animators trained, training material produced;

            - Four  three-day trainings for promote local micro business organized, 80 stakeholders trained, training material produced;

            - One two-day training of accessory stakeholders in tourism organized, 20 stakeholders trained, training material produced.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

N/A

## Risks

N/A

# SCOPE OF THE WORK

## General

### Description of the assignment

Contractor will prepare, organize and realize various trainings for the targeted area (Serbian part of Tamiš river valley) key stakeholders interesting in take part in tourism offer according to the objectives of the project “Eco Tamiš (Timiş) – new tourism product”. The preparation and development of training plan (methodology) and material will be done in close cooperation with the project team. After obtaining approval on prepared plan and material from Contracting Authority, the Contractor will organize the trainings. The Contracting Authority will provide the Contractor with trainings schedule. The Contractor is obliged to respect the schedule.

### Geographical area to be covered

Serbia, Serbian part of the Tamiš river valley

### Target groups

Key stakeholders interested in development of micro business connected with tourism

## Specific work

1. Trainings for representatives of local-self governments

Contractor will provide all managerial, organization, logistic, visibility and protocol activities according to description in the list of specific activities. For every activity Contractor will achieve parameter of acceptability mentioned in relevant column of the list, especially ones connected with time limits and quantities and qualities of goods and services.

The representatives of local-self governments will be trained how to support other stakeholders who have ideas to be engaged in new touristic product and how to work with the small infrastructural objects due to their maintenance and sustainability. Themes will be, among all, route management, marketing and promotion skills and product placement as characteristics of the area, partnership and clusters, etc. The Contractor will organize two trainings. Trainings will last two days with average number of participants of 20.

For each training:

The Contractor will provide venue in accordance with the approved training plan. The hall/room must be able to accommodate at least 20 persons and have to be equipped with video beam, Wi-Fi internet connection, sound system, etc.

- Trainings preparation

Contractor will prepare methodology for trainings in line with the identified training needs.

Developed training will be approved by Contracting Authority representative. On the basis of approved trainings, Contractor will prepare training materials and will engage two lecturers and adequate number of interpreters (translators).

- Logistic support.

1. Accommodation of participants

- Hotels (double or single) rooms for one night equipped with bathroom for 20 participants. Buffet breakfast included.

- Food for participants. Two meals per day/per participant (lunch and dinner) with possibilities that meals would be served in the training space out of hotel (hostel). Also, 20% of meals would be for vegetarians.

In the case that lunch will be served out of hotel (hostel) Consultant will provide a list of foods that will include:

  - At least 10 different finger foods,

  - At least 2 different sweets,

  - At least 2 vegetarian finger foods

  - All necessary equipment (plastic cups, forks, knives, serviettes and similar)

- Refreshment for training participants (mineral water, tea, coffee and juices) in the training space.

2. Standard workshop logistics

| # | Task | Description | Time | Quality parameters and acceptability criteria |
| --- | --- | --- | --- | --- |
| 1. | List of participants | Preparation of the list of participants in accordance with project coordinator suggestions | 5 days before training | List completely made. On time. Accepted by project coordinator. |
| 2. | Training materials | Preparation of training materials in close cooperation with project coordinator suggestions. It includes printed presentation, notebook, pen and plastic folder for each participant | 5 days before training | Materials completely made. On time. Accepted by project coordinator. |
| 3. | Making and distribution of agenda | Contractor will prepare agenda for training in close consultation with project coordinator and distribute it to participants | 5 days before training | Agenda completely made. On time. Accepted by project coordinator. |
| 4. | Making and distribution of official invitation | Contractor will prepare invitation for training in close consultation with project coordinator and distribute it to participants together with agenda. The invitation will be dispatched by electronic mail, except in case where the electronic mail address doesn’t exist. In such case, the invitation will be sent by post. | 5 days before training | Invitation completely made. On time. Accepted by project coordinator. |
| 5. | Communication with participants | Once established list of participants will serve as base for communication between Consultant and participants in regard to logistics | From 5 days before training to the end of training | Every question will have adequate answer |
| 6. | Provide space and equipment | Booking of adequate space and equipment at least five days before the event. Space will be equipped with enough seats for at least 20 persons, tables for equipment and lecturers. Space will be adequate tempered (20-22 0C) due to season of training performance. Consultant will provide space for coffee break, catering and for work of logistic staff | 1 day before training and during the training | Space provided On time. Accepted by Project coordinator |
| 7. | Equipment installation | Consultant will decorate the provided space with visibility material (rollups, banners, posters, photos) if such is provided by Project team. Consultant will install and proof all necessary equipment for work (video projecting system, lights, computers, tables and seats). | 1 day before training | On time Accepted by project manager and project administrator |
| 8. | Logistic staff | Consultant will provide one person for training as technical assistance (to install and prepare the video beam, operate the Dictaphones and take care of the functioning of the equipment during workshop, as administrator (to take care of the hand-outs, lists of attendance etc.) and host (to help with catering, coffee, grouping etc.) | 1 day before training and during the training | On time |
| 9.. | Coffee break and catering | Consultant will provide coffee and refreshment on breaks and catering and non-alcoholic beverages for coffee breaks | At the training | On time (coffee break per day: 1 coffee and 0,5l of refreshment drinks per person; Catering per day: 400g of food and 0,5l of refreshment drinks per person) |
| 10 | Collecting the workshop products | Consultant will organize collection of all products created during workshop (photos, sound and video records, papers, flip-chart notice and similar) and deliver them to project administrator for project archive | At the end of training | Immediately after meeting |

Contractor will communicate with the project team members in accordance with agreement of Project coordinator.

2. Trainings for animators in tourism

Contractor will provide all managerial, organization, logistic, visibility and protocol activities according to description in the list of specific activities. For every activity Contractor will achieve parameter of acceptability mentioned in relevant column of the list, especially ones connected with time limits and quantities and qualities of goods and services.

The training will enhance the capacities of organizers and animators to improve their way of presenting their activities (basic characteristics of the area, orienteering, bird-watching, photo-safari organizations, canoeing) and especial focus will be given to their inter relation with the tourists. The Contractor will organize three trainings. Trainings will last three days with average number of participants of 20.

For each training:

The Contractor will provide venue in accordance with the approved training plan. The hall/room must be able to accommodate at least 20 persons and have to be equipped with video beam, Wi-Fi internet connection, sound system, etc.

- Trainings preparation

Contractor will prepare methodology for trainings in line with the identified training needs.

Developed training will be approved by Contracting Authority representative. On the basis of approved trainings, Contractor will prepare training materials and will engage two lecturers and adequate number of interpreters (translators).

- Logistic support.

1. Accommodation of participants

- Hotels (double or single) rooms for two nights equipped with bathroom for 20 participants. Buffet breakfast included.

- Food for participants. Two meals per day/per participant (lunch and dinner) with possibilities that meals would be served in the training space out of hotel (hostel). Also, 20% of meals would be for vegetarians.

In the case that lunch will be served out of hotel (hostel) Consultant will provide a list of foods that will include:

  - At least 10 different finger foods,

  - At least 2 different sweets,

  - At least 2 vegetarian finger foods

  - All necessary equipment (plastic cups, forks, knives, serviettes and similar)

- Refreshment for training participants (mineral water, tea, coffee and juices) in the training space.

2. Standard workshop logistics

| # | Task | Description | Time | Quality parameters and acceptability criteria |
| --- | --- | --- | --- | --- |
| 1. | List of participants | Preparation of the list of participants in accordance with project coordinator suggestions | 5 days before training | List completely made. On time. Accepted by project coordinator. |
| 2. | Training materials | Preparation of training materials in close cooperation with project coordinator suggestions. It includes printed presentation, notebook, pen and plastic folder for each participant | 5 days before training | Materials completely made. On time. Accepted by project coordinator. |
| 3. | Making and distribution of agenda | Contractor will prepare agenda for training in close consultation with project coordinator and distribute it to participants | 5 days before training | Agenda completely made. On time. Accepted by project coordinator. |
| 4. | Making and distribution of official invitation | Contractor will prepare invitation for training in close consultation with project coordinator and distribute it to participants together with agenda. The invitation will be dispatched by electronic mail, except in case where the electronic mail address doesn’t exist. In such case, the invitation will be sent by post. | 5 days before training | Invitation completely made. On time. Accepted by project coordinator. |
| 5. | Communication with participants | Once established list of participants will serve as base for communication between Consultant and participants in regard to logistics | From 5 days before training to the end of training | Every question will have adequate answer |
| 6. | Provide space and equipment | Booking of adequate space and equipment at least five days before the event. Space will be equipped with enough seats for at least 20 persons, tables for equipment and lecturers. Space will be adequate tempered (20-22 0C) due to season of training performance. Consultant will provide space for coffee break, catering and for work of logistic staff | 1 day before training and during the training | Space provided On time. Accepted by Project coordinator |
| 7. | Equipment installation | Consultant will decorate the provided space with visibility material (rollups, banners, posters, photos) if such is provided by Project team. Consultant will install and proof all necessary equipment for work (video projecting system, lights, computers, tables and seats). | 1 day before training | On time Accepted by project manager and project administrator |
| 8. | Logistic staff | Consultant will provide one person for training as technical assistance (to install and prepare the video beam, operate the Dictaphones and take care of the functioning of the equipment during workshop, as administrator (to take care of the hand-outs, lists of attendance etc.) and host (to help with catering, coffee, grouping etc.) | 1 day before training and during the training | On time |
| 9.. | Coffee break and catering | Consultant will provide coffee and refreshment on breaks and catering and non-alcoholic beverages for coffee breaks | At the training | On time (coffee break per day: 1 coffee and 0,5l of refreshment drinks per person; Catering per day: 400g of food and 0,5l of refreshment drinks per person) |
| 10 | Collecting the workshop products | Consultant will organize collection of all products created during workshop (photos, sound and video records, papers, flip-chart notice and similar) and deliver them to project administrator for project archive | At the end of training | Immediately after meeting |

Contractor will communicate with the project team members in accordance with agreement of Project coordinator.

3. Trainings for promote local micro businesses

Contractor will provide all managerial, organization, logistic, visibility and protocol activities according to description in the list of specific activities. For every activity Contractor will achieve parameter of acceptability mentioned in relevant column of the list, especially ones connected with time limits and quantities and qualities of goods and services.

Trainings for promote local micro businesses in the Tamiš (Timiš) river valley as a means of enhancing the tourist experience while providing needed income to the predominantly rural population. It will be held for different categories of such stakeholders. The contractor will organize four trainings. Trainings will last three days with average number of participants of 20.

For each training:

The Contractor will provide venue in accordance with the approved training plan. The hall/room must be able to accommodate at least 20 persons and have to be equipped with video beam, Wi-Fi internet connection, sound system, etc.

- Trainings preparation

Contractor will prepare methodology for trainings in line with the identified training needs.

Developed training will be approved by Contracting Authority representative. On the basis of approved trainings, Contractor will prepare training materials and will engage two lecturers and adequate number of interpreters (translators).

- Logistic support.

1. Accommodation of participants

- Hotels (double or single) rooms for two nights equipped with bathroom for 20 participants. Buffet breakfast included.

- Food for participants. Two meals per day/per participant (lunch and dinner) with possibilities that meals would be served in the training space out of hotel (hostel). Also, 20% of meals would be for vegetarians.

In the case that lunch will be served out of hotel (hostel) Consultant will provide a list of foods that will include:

  - At least 10 different finger foods,

  - At least 2 different sweets,

  - At least 2 vegetarian finger foods

  - All necessary equipment (plastic cups, forks, knives, serviettes and similar)

- Refreshment for training participants (mineral water, tea, coffee and juices) in the training space.

2. Standard workshop logistics

| # | Task | Description | Time | Quality parameters and acceptability criteria |
| --- | --- | --- | --- | --- |
| 1. | List of participants | Preparation of the list of participants in accordance with project coordinator suggestions | 5 days before training | List completely made. On time. Accepted by project coordinator. |
| 2. | Training materials | Preparation of training materials in close cooperation with project coordinator suggestions. It includes printed presentation, notebook, pen and plastic folder for each participant | 5 days before training | Materials completely made. On time. Accepted by project coordinator. |
| 3. | Making and distribution of agenda | Contractor will prepare agenda for training in close consultation with project coordinator and distribute it to participants | 5 days before training | Agenda completely made. On time. Accepted by project coordinator. |
| 4. | Making and distribution of official invitation | Contractor will prepare invitation for training in close consultation with project coordinator and distribute it to participants together with agenda. The invitation will be dispatched by electronic mail, except in case where the electronic mail address doesn’t exist. In such case, the invitation will be sent by post. | 5 days before training | Invitation completely made. On time. Accepted by project coordinator. |
| 5. | Communication with participants | Once established list of participants will serve as base for communication between Consultant and participants in regard to logistics | From 5 days before training to the end of training | Every question will have adequate answer |
| 6. | Provide space and equipment | Booking of adequate space and equipment at least five days before the event. Space will be equipped with enough seats for at least 20 persons, tables for equipment and lecturers. Space will be adequate tempered (20-22 0C) due to season of training performance. Consultant will provide space for coffee break, catering and for work of logistic staff | 1 day before training and during the training | Space provided On time. Accepted by Project coordinator |
| 7. | Equipment installation | Consultant will decorate the provided space with visibility material (rollups, banners, posters, photos) if such is provided by Project team. Consultant will install and proof all necessary equipment for work (video projecting system, lights, computers, tables and seats). | 1 day before training | On time Accepted by project manager and project administrator |
| 8. | Logistic staff | Consultant will provide one person for training as technical assistance (to install and prepare the video beam, operate the Dictaphones and take care of the functioning of the equipment during workshop, as administrator (to take care of the hand-outs, lists of attendance etc.) and host (to help with catering, coffee, grouping etc.) | 1 day before training and during the training | On time |
| 9.. | Coffee break and catering | Consultant will provide coffee and refreshment on breaks and catering and non-alcoholic beverages for coffee breaks | At the training | On time (coffee break per day: 1 coffee and 0,5l of refreshment drinks per person; Catering per day: 400g of food and 0,5l of refreshment drinks per person) |
| 10 | Collecting the workshop products | Consultant will organize collection of all products created during workshop (photos, sound and video records, papers, flip-chart notice and similar) and deliver them to project administrator for project archive | At the end of training | Immediately after meeting |

Contractor will communicate with the project team members in accordance with agreement of Project coordinator.

4 Training of accessory stakeholders in tourism

Contractor will provide all managerial, organization, logistic, visibility and protocol activities according to description in the list of specific activities. For every activity Contractor will achieve parameter of acceptability mentioned in relevant column of the list, especially ones connected with time limits and quantities and qualities of goods and services.

The training will be held to educate stakeholders who are interesting in transportation, health care and safety of tourists and visitor. The Contractor will organize one training. Training will last two days with average number of participants of 20.

For each training:

The Contractor will provide venue in accordance with the approved training plan. The hall/room must be able to accommodate at least 20 persons and have to be equipped with video beam, Wi-Fi internet connection, sound system, etc.

- Trainings preparation

Contractor will prepare methodology for trainings in line with the identified training needs.

Developed training will be approved by Contracting Authority representative. On the basis of approved trainings, Contractor will prepare training materials and will engage two lecturers and adequate number of interpreters (translators).

- Logistic support.

1. Accommodation of participants

- Hotels (double or single) rooms for one night equipped with bathroom for 20 participants. Buffet breakfast included.

- Food for participants. Two meals per day/per participant (lunch and dinner) with possibilities that meals would be served in the training space out of hotel (hostel). Also, 20% of meals would be for vegetarians.

In the case that lunch will be served out of hotel (hostel) Consultant will provide a list of foods that will include:

  - At least 10 different finger foods,

  - At least 2 different sweets,

  - At least 2 vegetarian finger foods

  - All necessary equipment (plastic cups, forks, knives, serviettes and similar)

- Refreshment for training participants (mineral water, tea, coffee and juices) in the training space.

2. Standard workshop logistics

| # | Task | Description | Time | Quality parameters and acceptability criteria |
| --- | --- | --- | --- | --- |
| 1. | List of participants | Preparation of the list of participants in accordance with project coordinator suggestions | 5 days before training | List completely made. On time. Accepted by project coordinator. |
| 2. | Training materials | Preparation of training materials in close cooperation with project coordinator suggestions. It includes printed presentation, notebook, pen and plastic folder for each participant | 5 days before training | Materials completely made. On time. Accepted by project coordinator. |
| 3. | Making and distribution of agenda | Contractor will prepare agenda for training in close consultation with project coordinator and distribute it to participants | 5 days before training | Agenda completely made. On time. Accepted by project coordinator. |
| 4. | Making and distribution of official invitation | Contractor will prepare invitation for training in close consultation with project coordinator and distribute it to participants together with agenda. The invitation will be dispatched by electronic mail, except in case where the electronic mail address doesn’t exist. In such case, the invitation will be sent by post. | 5 days before training | Invitation completely made. On time. Accepted by project coordinator. |
| 5. | Communication with participants | Once established list of participants will serve as base for communication between Consultant and participants in regard to logistics | From 5 days before training to the end of training | Every question will have adequate answer |
| 6. | Provide space and equipment | Booking of adequate space and equipment at least five days before the event. Space will be equipped with enough seats for at least 20 persons, tables for equipment and lecturers. Space will be adequate tempered (20-22 0C) due to season of training performance. Consultant will provide space for coffee break, catering and for work of logistic staff | 1 day before training and during the training | Space provided On time. Accepted by Project coordinator |
| 7. | Equipment installation | Consultant will decorate the provided space with visibility material (rollups, banners, posters, photos) if such is provided by Project team. Consultant will install and proof all necessary equipment for work (video projecting system, lights, computers, tables and seats). | 1 day before training | On time Accepted by project manager and project administrator |
| 8. | Logistic staff | Consultant will provide one person for training as technical assistance (to install and prepare the video beam, operate the Dictaphones and take care of the functioning of the equipment during workshop, as administrator (to take care of the hand-outs, lists of attendance etc.) and host (to help with catering, coffee, grouping etc.) | 1 day before training and during the training | On time |
| 9.. | Coffee break and catering | Consultant will provide coffee and refreshment on breaks and catering and non-alcoholic beverages for coffee breaks | At the training | On time (coffee break per day: 1 coffee and 0,5l of refreshment drinks per person; Catering per day: 400g of food and 0,5l of refreshment drinks per person) |
| 10 | Collecting the workshop products | Consultant will organize collection of all products created during workshop (photos, sound and video records, papers, flip-chart notice and similar) and deliver them to project administrator for project archive | At the end of training | Immediately after meeting |

Contractor will communicate with the project team members in accordance with agreement of Project coordinator.

## Project management

### Responsible body

The Project coordinator for training is responsible for all activities regarding this contract.

### Management structure

Project coordinator for training is responsible alone for all contract procedure

### Facilities to be provided by the Contracting Authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

Serbia, South Banat

## Start date & Period of implementation of tasks

The intended commencement date is date of signature of the contract by both parties and the period of implementation of the contract will be 12 months from this date. Please refer to Articles 4 and 5 of the Special Conditions for the actual commencement date and period of implementation.

# REQUIREMENTS

## Staff

The contractor will ensure sufficient number of qualified experts for quality and timely implementation of tasks planned by these Terms of References. These experts are considered as non-key experts therefore their CVs will not be submitted with the application. Office accommodation

## Office accommodation

The costs of office accommodation will be included in the global price.

## Facilities to be provided by the Contractor

The Contractor shall ensure any other facilities, including the transportation means, necessary for quality and timely implementation of the tasks described in these Terms of Reference.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

- The contractor will submit the following reports in English in one original and 1 copy:

- The contractor will prepare 3 interim and final reports with all necessary details in coordination with Project coordinator. The approval of Interim and Final reports will be the basis for issuing respective payment as indicated in the Special Conditions.

- The required formats of the report will be communicated to the Contractor by the Contracting Authority after the signature of the contract.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

N/A

## Special requirements

N/A