ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

General Hospital Požarevac, Bratstva jedinstva 135, 12000 Požarevac, Republic of Serbia

## Country background

Decline of population - the population in the border area on the Serbian territories declined by more than 10% in the last decade;

- Serious aging of the population as a consequence of emigration and natural decline, especially in the rural areas;

- Natural demographic trend is negative in most areas;

Health is one of the strongest aspirations of today and is closely and inextricably linked to the concept of economic and social development. It is an inalienable right of all people and must be understood as "a complete welfare of physically, mentally and socially" and not just the absence of disease or infirmity. One of the common territorial challenges shared by the border region of ROM-SRB Programme area is the prevalence of cancer among the population as one of the leading causes of death, especially when we consider the aging of the population, which is an additional factor of high prevalence of malignant diseases.

This project aims to tackle the challenge of better cancer diagnosis and treatment through improved medical research supported by cross-border networking, improved IT technologies and modernized hospital facilities.

## Current situation in the sector

In Serbia the age standardized cancer incidence rates (W) for both sexes were 224.2 and 269.7, respectively, as compared with 247.0 for the entire WHO Europe Region. In terms of mortality, the rates were 147.8 in Serbia and 114.0 in Europe. These data show the incidence of cancer in the two countries is close to the European average (higher in Serbia). However, a noteworthy difference in the number of cancer deaths can be seen, with both countries having higher mortality rates (29% higher in Serbia) than the European average. The risk of getting cancer before age 75 is 27.1% in Serbian population, with the European average being 25.1%. Again, the real issue is the risk of dying from cancer before the age of 75 years, which is higher in Serbia (16.3%) than in Europe.

## Related programmes and other donor activities

Similar tele-medical partnership/network has been accomplished between South Banat District and Caras-Severin County and Branicevo District - Caras-Severin County as a result of previous Calls of the IPA ROM-SRB CBC Programme.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

“To foster collaboration in the field of oncology between medical institutions on the two sides of the border in order to provide access to modern and efficient specific health care services for all oncologic patients resident in the Region, with the aim to improve their lifespan/survival/life expectancy and quality of life.”

## Purpose

The purpose of this contract is to provide professional promotional services and event organization for strategic project „Romania-Serbia joint initiative against cancer in cross-border region: improved diagnosis and treatment of malignant tumors - ROSECAN” in order to provide professional representation and visibility for the project.

## Results to be achieved by the Contractor

- Result 1: Design and production of project promotional jingle and video.

- Result 2: Design and printing of project promotional materials.

- Result 3: Organization of Project Promotion Conference in Požarevac.

- Result 4: Organization of 8 Project Press Conferences in Požarevac.

- Result 5: Organization of 10 professional medical seminars in Požarevac.

- Result 6: Provide media coverage and collect published data about the project periodically.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- For all promotional activities and event organization, the Contractor must be informed about promotional requirements of EU funded projects in order to comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en.

## Risks

Continuous and close cooperation with the Contracting Authority should be respected during contract implementation in order to avoid possible issues resulting from miscommunication regarding the promotional goals or event objectives of project ROSECAN.

# SCOPE OF THE WORK

## General

### Description of the assignment

Professional services for promotional activities and event organization will be acquired in order to provide professional representation and visibility for strategic project „Romania-Serbia joint initiative against cancer in cross-border region: improved diagnosis and treatment of malignant tumors - ROSECAN”.

### Geographical area to be covered

City of Požarevac, Braničevski District, Serbia

### Target groups

- Patients benefiting from the services of health institutions included in the network on both sides of the border.

- Population living in the border area that will experience the improvement of quality of life as a result of the efforts of the project.

- Health care personnel and health units in the border area.

- Medical society.

- Policy makers.

## Specific work

Assignment:

Provide professional services for promotional activities and event organization in order to provide professional representation and visibility for strategic project „Romania-Serbia joint initiative against cancer in cross-border region: improved diagnosis and treatment of malignant tumors - ROSECAN”.

- All results achieved by the Contractor must comply with the INTERREG IPA Cross-border Cooperation Programme ROMANIA-SERBIA visibility requirements.

Results should be achieved in the following chronological order:

- Design and production of project promotional jingle and video.

- Design and printing of project promotional materials.

- Organization of Project Promotion Conference with Project Press Conference in Požarevac.

- Organization of remaining 7 Project Press Conferences in Požarevac.

- Organization of 10 professional medical seminars in Požarevac.

- Provide media coverage and collect published data about the project periodically.

List of tasks to be completed by the Contractor:

1. Design and production of project promotional jingle and video.

As a first step, visual identity of project ROSECAN should be developed and created in close cooperation with Contracting Authority and in accordance with the Visual Identity Manual of the INTERREG IPA ROMANIA-SERBIA Cross-border Cooperation Programme (See: http://www.romania-serbia.net/?page_id=212&lang=en_GB ).

Approved visual identity elements of the project should be used for all promotional activities and materials, including the promotional jingle and video.

With the intention to promote the project objectives and the project results, one HD promotional short movie should be designed and produced ready for broadcasting. Length of the movie should be minimum 10 minutes. Additionally, a min. 15 second long project jingle should be produced ready for broadcasting.

The video and jingle will serve the purpose to promote project ROSECAN and inform the final beneficiaries of the project results.

2. Design and printing of project promotional materials

In order to promote the project objectives and the project results, the Contractor should design, print and distribute promotional materials. All promotional materials should be printed three lingual: Serbian, Romanian and English. Also, the design should match the previously approved visual identity elements of project ROSECAN. The following promotional materials should be provided by the Contractor:

- Leaflets (4000 units) – design and print 3-lingual promotional leaflets about project ROSECAN in color. Leaflets should be distributed at project events to media representatives and stakeholders. Minimum format of the print: A5 (folded); paper type: “kunstdruk” paper minimum 110 grams, full color on both sides.

- Brochures (2000 units) - design and print 3-lingual promotional brochures about project ROSECAN in color. Brochures should be distributed at project events to media representatives and stakeholders. Minimum format of the print: A5; paper type: “kunstdruk” paper minimum 110 grams with hard covers, number of pages: minimum 8, full color on both sides.

- Roll-up (2 pcs) - design and print 3-lingual promotional roll-ups about project ROSECAN in color. Roll-ups should be displayed at various project events. Format, min. conference (85mm x 2000mm); Print: Full colour 4/4.

- Promotional materials for persons attending the conferences and seminars (600 sets):

Special promotional materials will be prepared for persons attending project events. A total of 600 ROSECAN promotional sets should be prepared and distributed. The promotional sets should contain the following elements: Paper bag, folder, pen, notebook and nametags. Each element should be designed with visual identity details of project ROSECAN.

Information about the project will be provided by the Contracting Authority. Texts included on the promotional material will be subject of approval by the Contracting Authority.

3. Organization of Project Promotion Conference with Project Press Conference in Požarevac.

Contractor should organize a one-day Project Promotion Conference in Požarevac for min. 50 people. The purpose of the event is to inform medical experts, general public and media representatives of ROSECAN project objectives, expected results and plan of activities and provide visibility for the project. The Contractor is expected to handle logistics:

- Invitation of participants and media representatives,

- Providing a moderator for the event in order to provide participants with guidance throughout the event and provide organisational support.

- Appropriate venue: An adequate conference room with min. 55 chairs for (sufficient number of chairs for the participants and for reserves – project management, interpreters, etc.). The room should be heated/air-conditioned with good lighting.

- Technical support; supporting equipment should include:  laptop, projector, conference desk, video beam, sound system and equipment for simultaneous translation.

- Visibility elements developed for the project should be displayed and promotional materials should be distributed.

- Catering; a lunch type menu should be served:

  - Catering with lunch type menu served in a smorgasbord/buffet style for minimum 50 people. Soup and salad, as well as min. 2 choices of main course and dessert choices should be served. For refreshments, non-alcoholic beverages such are carbonated and non-carbonated drinks, mineral water, coffee and tea should be provided (2 servings per person).

Program of the event and list of participants should be developed in close cooperation with Contracting Authority.

- 4. Organization of additional 7 Project Press Conferences in Požarevac.

During the project implementation period, Contractor should organize 7 more (8 in total) press conferences in Požarevac. Project Press Conferences will be organized with the aim to secure quality visibility of all project activities implemented and all project results achieved. Local, regional and national media will be invited to take a part in press conferences.

The timing of press conferences will depend on the dynamics of project implementation, and will be decided jointly with the Contracting Authority. For each press conference, the Contractor is expected to handle logistics: invitation of media representatives, providing a moderator, appropriate venue, technical support and visibility elements. Material presented at the event and list of participants should be developed in close cooperation with Contracting Authority.

5. Organization of 10 professional medical seminars in Požarevac.

Ten one-day Professional Medical Seminars (with minimum 50 participants each) on improving surgical and non-surgical treatment methods and capacities for malignant diseases and health care system in general should be organized in Požarevac. Health workers from the region should take part in these seminars. The seminars will serve the purpose of raising the level of health care in the border region, inform and educate on common challenges in the fight againts cancer.

The Contractor is expected to handle logistics, while project partners will be in charge of professional content. Program of the event and list of participants should be developed in close cooperation with Contracting Authority. Professional content, lecturers and presentations will be provided by the Contracting Authority

The following should be provided by the Consultant:

- Invitation of participants based on the list of invitees provided by the Contracting Authority,

- Provide a moderator for the event in order to provide participants with guidance throughout the event and provide organisational support.

- Appropriate venue: Adequate conference room with min. 55 chairs for (sufficient number of chairs for the participants and for reserves – project management, interpreters, etc.). The room should be heated/air-conditioned with good lighting.

- Technical support; supporting equipment should include:  laptop, projector, conference desk, video beam, sound system and equipment for simultaneous translation.

- Visibility elements developed for the project should be displayed and promotional materials should be distributed.

- Catering; breakfast and lunch type menu should be served:

  - Coffee break for 30 minutes should be provided: Min. 2-2 choices of sweet and salty pastry type food with at least one choice of fruit should be served for 50 people for each seminar (10 in total). For refreshments, non-alcoholic beverages such are carbonated and non-carbonated drinks, mineral water, milk, yoghurt, coffee and tea should be provided (min. 2 servings per person).

  - Lunch-break should be provided for min. 60 minutes. During lunch break a lunch type menu should be served in a smorgasbord/buffet style for minimum 50 people for each seminar (10 in total). Soup and salad, as well as min. 2 choices of main course and dessert choices should be served. For refreshments, non-alcoholic beverages such are carbonated and non-carbonated drinks, mineral water, coffee and tea should be provided (2 servings per person).

- 6. Provide media coverage and collect published data about the project periodically.

Provide media coverage and press-clipping, i.e. collect and systematize published data about the project periodically in print media, electronic media, links, etc., and submit regular press-clipping reports as requested by the Contracting Authority.

The service will be contracted for a 38 months period of project implementation, as a part time job (10% working time) and the offer is to be made for lump sum for the complete service of technical support.

The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en.

## Project management

### Responsible body

The Consultant is responsible for all the activities regarding this contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Danko Nikolić, Project Manager.

### Facilities to be provided by the Contracting Authority and/or other parties

Not applicable.

# LOGISTICS AND TIMING

## Location

City of Požarevac, Braničevski District, Serbia.

## Start date & Period of implementation of tasks

The intended start date is the date of signature of the contract by both parties and the period of implementation of the contract will be 38 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability.

Key expert 1: PR Manager

Qualifications and skills:

• High school degree, university degree will be an asset;

• Computer skills – Windows, Office and Internet;

• Serbian and English language fluency, Romanian language will be an asset.

General professional experience:

• Experience in organizing promotional events.

• Good narrative writing skills.

• Communication and interpersonal skills.

Specific professional experience:

• Experience in managing promotional activities (engagement in at least 1 EU funded project will be an asset).

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and one copy:

The contractor will prepare final report on the implementation of the tasks, at the end of this contract. It should be submitted at the end of 38th month. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions. The final report must be provided along with the corresponding invoice.

The contractor will prepare brief interim reports by the end of 1st , 6th , 14th , 22nd and 30th months. The approval of interim report will be the basis for issuing respective interim payment as indicated in the Special Conditions. The interim report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

“Services provided in timely, quality and quantity manor, as required in these Terms of Reference”.

## Special requirements

Not applicable.