PART A: INFORMATION FOR THE TENDERER

Name and address of the contracting authority: Ministry of Interior of the Republic of Serbia, Kneza Milosa 103, Belgrade, Republic of Serbia Title of the tender: Organization of trainings, joint field exercise and public awareness workshop Reference number: RORS 27 –TD02 Date of launching: 29/12/2017

- INFORMATION ON SUBMISSION OF THE TENDERS

Subject of the contract:

The subject of this tender is:

Implementation of services as indicated in the technical information in the point 2 of these information.

Deadline for submission of the tenders:

The deadline for submission of tenders is 15/01/2018 at 15:00 hours. Any tender received after this deadline will be automatically rejected.

Financial information:

The tenderers are reminded that the maximum available value of the contract is 16.000 EUR.

The Financial offer must be presented as an amount in EUR / RSD and must be submitted using the template for the global-price version of PART C: FORMAT OF FINANCIAL OFFER.

In case when the offers are submitted in national currencies, the exchange rate to be used for checking financial compliance with available budget (during financial evaluation), shall be InforEuro exchange rate for the month when the tender is launched.

The applicable tax and customs arrangements are specified in the draft contract in Part A of this tender dossier.

Variant solutions:

Tenderers are not authorised to tender for a variant in addition to this tender.

Subcontracting:

Subcontracting is not allowed.

Award criteria:

In case more than one offer received: best value for money, weighting 80% technical quality, 20% price.

Evaluation criteria for technical offer:

- Organization and methodology: 40 points

- Proposed inputs: 40 points

- Time frame: 20 points

TOTAL: 100 points

In case one offer received: the Contracting Authority shall check whether the offer is administratively, technically and financially compliant with the requirements set by this tender documentation.

Interviews:

No interviews are foreseen.

Award notification:

The successful tenderer will be informed of the results of the evaluation procedure in written form.

Contract award notice will be published on the programme web site. The estimated time of publishing is 7 days from the deadline for submission of tenders.

Address and meanings for submission of the tenders:

The tenderers will submit their tenders using the standard set of submission forms available in the Part B – Technical offer and the Part C - Financial offer. Any other document supporting this invitation is sent for informational purposes only and is not to be modified nor submitted by the tenderer. The tender will be submitted in 1 original. Any tenders not using the prescribed form may be rejected by the contracting authority.

In addition to the offer the tenderer is required to provide the following supporting documentation:

- Copy of legal registration

- Reference list (List of similar contracts with short description where the tenderer has worked successfully in past three years)

The tenders will be submitted in sealed envelopes, containing the following information:

- Name and address of the tenderer

- Title of the tender: Organization of trainings, joint field exercise and public awareness workshop

- Reference number: RORS 27-TD 02

- The words: ‘’Not to be opened before the tender opening session’’ and “Ne otvarati pre sastanka za otvaranje ponuda’’

Tenders must be submitted using double envelope system, in an outer parcel or envelope containing two separate, sealed envelopes, one bearing the words "Technical offer”- part B and "Financial offer" - Part C.  Any infringement of this rule (e.g. unsealed envelopes or references to price in the technical offer) is to be considered a breach of the rule, and will lead to rejection of the tender.

The tenders will be submitted in person, by post or courier service to the following address:

Ministry of Interior of the Republic of Serbia,

Attn: Sector for Emergency Management

Bulevar Zorana Đindića 104, 11070 Novi Beograd

Contact person: Dragan Dončevski

The tenderers are reminded that in order to be eligible the tenders need to be received by the contracting authority by the deadline indicated above.

- TECHNICAL INFORMATION

The tenderers are required to provide services as indicated below. In the tenderer’s technical offer, the tenderers might indicate more details on the deliveries, referring back to the requirements below.

  - Transportation service

Description of expected outputs / results to be achieved:

- Two-day workshop regarding protection in case of floods and earthquake in Romania (Mehedinți county)

- The Contractor should provide transportation for 12 people from Serbia (around 600 km in total).

- Two-day training for protection and rescue teams in Serbia (Central Banat district)

- The Contractor should provide transportation for 32 people from Serbia and Romania (around 850 km in total).

- Three-day training and joint field exercise for protection and rescue teams in Serbia (South Banat district)

- The Contractor should provide transportation for 32 people from Serbia and Romania (around 600 km in total).

Required inputs:

- The Contractor has to prove previous experience in providing similar activities. It should have at least 2 staff members currently working within the fields related to this contract.

- The Contractor should use suitable mini bus in a good condition, not older than 10 years, with an air conditions, experienced driver and all necessary documents and approvals for crossing the border.

Required time frame:

Estimated period: March 2018 – June 2019.

  - Accommodation service

Description of expected outputs / results to be achieved:

- Two-day seminar for local authorities regarding joint intervention in case of floods and earthquake in Romania (Mehedinți County)

- The Contractor should provide one night accommodation for 15 people.

- Two-day training for protection and rescue teams in Serbia (Central Banat district)

- The Contractor should provide one night accommodation for 32 people.

- Three-day training and joint field exercise for protection and rescue teams in Serbia (South Banat district)

- The Contractor should provide two nights accommodation for 32 people.

The Contractor should provide accommodation in standard single rooms, in at least 3 stars hotel. The accommodation will include breakfast with coffee,water and soft drinks. The hotel will not be more than 500 m away from the conference room, and it should have free Wi-Fi Internet and parking for participants. The selected hotel must be approved by the Contracting Authority before the event.

Required inputs:

- The Contractor has to prove previous experience in providing similar activities. It should have at least 2 staff members currently working within the fields related to this contract.

- The Contractor should ensure the participation of at least one representative at each event who will guarantee the timely and qualitative conduction of activities.

Required time frame:

Estimated period: March 2018 – June 2019

  - Catering service

Description of expected outputs / results to be achieved:

- Two-day seminar for local authorities regarding joint intervention in case of floods and earthquake in Romania (Mehedinți County)

- The Contractor should provide refreshment and dinner for 15 people.

- Two-day training for protection and rescue teams in Serbia (Central Banat district)

- The Contractor should provide meals (two lunches and one dinner) for 32 people.

- Three-day training and joint field exercise for protection and rescue teams in Serbia (South Banat district)

- The Contractor should provide meals (three lunches and two dinners) for 32 people.

- One-day public awareness workshops for young pupils from schools

- The Contractor should provide refreshment and snacks for pupils from schools (360 pupils in total) and meals for trainers (6 lunches for two trainers).

The meals can be provided in the hotel or in the restaurant, within the targeted districts. The selected hotel or restaurant must be approved by the Contracting Authority before the event.

The lunch will include at least the following (per person): soup, main course (meat and vegetables), salad, bread, dessert, sparkling and still mineral water, soft drink and coffee/tea. The dinner will include at least the following (per person): cold starter, main course, bread, salad, dessert, sparkling and still mineral water, soft drink, coffee/tea.

All meals have to be good quality and standard quantity. If some participants have special dietary needs, Contractor will be inform about it 2 days before events.

Required inputs:

- The Contractor has to prove previous experience in providing similar activities. It should have at least 2 staff members currently working within the fields related to this contract.

- The Contractor should ensure the participation of at least one representative at each event who will guarantee the timely and qualitative conduction of activities.

Required time frame:

Estimated period: March 2018 – June 2019

  - Organization of conference room

Description of expected outputs / results to be achieved:

- Two-day training for protection and rescue teams in Serbia (Central Banat district)

The Contractor should provide a conference room for 2 days (approximately 8 hours/day) for at least 32 people.

The Contractor should provide two coffee breaks per day (two days), which includes sufficiant amount of sparkling and still mineral water, soft drink, coffee/tea with milk and sugar, snacks or cookies.

Conference room must be equipped with the necessary technical equipment (air condition, internet connection, sound system, video projector, laptop, projection screen, flipchart).

The Contractor should arrange the room according to instructions given by Contracting Authority.

- Three-day training and joint field exercise for protection and rescue teams in Serbia (South Banat district)

The Contractor should provide a conference room for 2 days (approximately 8 hours/day) for at least 32 people.

Contractor should provide two coffee breaks per day (three days), which includes sufficiant amount of sparkling and still mineral water, soft drink, coffee/tea with milk and sugar, snacks or cookies.

Conference room must be equipped with the necessary technical equipment (air condition, internet connection, sound system, video projector, laptop, projection screen, flipchart).

The Contractor should arrange the room accoriding to instructions given by Contracting Authority.

- One-day public awareness workshops for young pupils from school

Presentation room in schools must be equipped with the necessary technical equipment (video projector, laptop, projection screen, flipchart). The Contractor should arrange presentation room accoriding to instructions given by Contracting Authority.

For all events the Contractor is oblige to organize registration of participants, distribution of promotion materials to participants and decoration of room in accordance with Visual Identity Manual of the Interreg-IPA Cross-border Cooperation Romania-Serbia Programme. Promotional materials will be provided by the Contracting Authority. Consultant should also provide photos of all events (hard copy and electronic).

Required inputs:

- The Contractor has to prove previous experience in providing similar activities. It should have at least 2 staff members currently working within the fields related to this contract.

- The Contractor should ensure the participation of at least one representative at each event who will guarantee the timely and qualitative conduction of activities.

Required time frame:

Estimated period: March 2018 – June 2019

- ADDITIONAL INFORMATION

The unsuccessful/successful tenderers will be informed of the results of the evaluation procedure.  In this sense the CA shall send a notification to the successful tenderer and post an announcement on the website with the name of the successful tenderer followed by the mentioning that “all other tenders were not administratively /technically/ financially compliant”

Confidentiality

The entire evaluation procedure is confidential, subject to the Contracting Authority’s legislation on access to documents. The Evaluation Committee’s decisions are collective and its deliberations are held in closed session. The members of the Evaluation Committee are bound to secrecy. The evaluation reports and written records are for official use only and may be communicated neither to the tenderers nor to any party other than the Contracting Authority, the European Commission, the European Anti-Fraud Office and the European Court of Auditors.

NOT TO BE FILED IN BEFORE CONTRACT SIGNING NOT TO BE SUBMITTED WITHIN THE OFFER!!!

FORMAT OF THE CONTRACT BETWEEN THE CONTRACTOR AND THE CONTRACTING AUTHORITY

CONTRACT TITLE: Organization of trainings, joint field exercise and public awareness workshop

REF: RORS 27 –TD02

Concluded between:

Ministry of Interior of the Republic of Serbia

Kneza Milosa 103, Belgrade, Serbia

(Contracting Authority)

AND

<Title>

<Address of the contractor>

<Official registration number/VAT number>

(Contractor)

Article 1: Subject of the contract

The subject of the contract is the service “Organization of trainings, joint field exercise and public awareness workshop” as indicated in the contractor’s offer – ‘’Part B: Format of offer to be provided by the tenderer’’

Article 2: Contract value

The total contract value for implementation of services indicated in the Article 1 is: <XXX EUR/RSD, (including VAT for Romania partners)>.

For Serbian partners:

The contract shall be exempt from all duties and taxes, including VAT.

For Romanian Partners:

In accordance with IPA implementing regulation, for Romanian partners VAT can be an eligible expenditure. The Contracting Authority will pay the unit prices, as stated in the Financial Offer, and will pay the VAT if the VAT is clearly identified on the invoices.

Article 3: Contracting documents

The documents which form the part of this contract are (by the order of precedence):

- Contract agreement

- Contractor’s offer as provided in the tendering phase – ‘’Part B: Format of offer to be provided by the tenderer’’

- Contractor’s financial offer –“ Part C:Format of financial offer”

- Any other supporting documentation if applicable (* - in case of asking for registration of company or other information)

For any issues not defined in this contract agreement the rules of General conditions will be applied (Annex B8d  of PRAG b8d_annexigc_en.pdf)

http://ec.europa.eu/europeaid/prag/previousVersions/annex.do?num=2015.0&lang=en

Article 4: Deliveries and payments

The contractor will deliver without reservation the services indicated in the contractor’s offer ‘’Part B: Format of offer to be provided by the tenderer’’. The deliveries will be implemented within the indicated dates.

The contracting authority will pay to the contractor for the services in the amount indicated in the Article 2 of this contract document.

In case the contract is concluded in EUR, and payments are made in RSD, applicable exchange rate must be InforEuro exchange rate for the month of the issuing of invoice or pre-invoice in case of VAT exemption.

The payments will be issued by the following time schedule.

| Month |  | EUR/RSD |
| --- | --- | --- |
| 6 | Interim payment | 30 % of the contract value |
| 12 | Interim payment | 35 % of the contract value |
| 17 | Balance final payment | 35 % of the contract value |
|  | Total | 100% |

* - The contractor will provide contracting authority with the brief report on execution of the services, which will represent the basis for issuing interim and balance final payment

Article 5: Duration of the contract

The duration of the contract is 17 months (but not later than 6.7.2019)

.

Commencement date is date of signature of the contract by both parties.

Article 6: Resolving of disputes

Any disputes arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the Republic of Serbia in accordance with the national legislation of the state of the Contracting Authority.

| For the Contractor |  | For the Contracting Authority |  |
| --- | --- | --- | --- |
| Name: |  | Name: |  |
| Title: |  | Title: |  |
| Signature: |  | Signature: |  |
| Date: |  | Date: |  |

Where applicable. For individuals, mention their ID card or passport or equivalent document - number