# B.	DRAFT CONTRACT AND SPECIAL CONDITIONS, INCLUDING ANNEXES

# DRAFT CONTRACT

SUPPLY CONTRACT FOR EUROPEAN

UNION EXTERNAL ACTIONS

No RORS92/City of Pozarevac /T4

financed from the EU General Budget

Name of the Contracting Authority: City of Požarevac

Address of the Contracting Authority:

Drinska Street no2, 12000 Požarevac,

Republic of Serbia.

VAT:

("The Contracting Authority"),

of the one part,

and

<Full official name of Contractor>

[<Legal status/title>]

[<Official registration number>]

<Full official address>

[<VAT number>], (“the Contractor”)

of the other part,

have agreed as follows:

- PROJECT Cultural connection in purpose of touristic attractiveness strengthening of the Region, RORS92

- CONTRACT TITLE Purchasing of Balloon, Stage and Wooden Info Desk

- Identification number RORS92/City of Pozarevac /T4

- Article 1	Subject

  - The subject of the contract shall be the delivery, installation of the following supplies:

Lot 1:

Prefabricated structure – Balloon – 1 pc with total dimensions of 50x24x10 meters, with turnkey system which includes designing, purchase and setting up of the balloon, as it was specified in the Instructions to tenderers.

Lot 2:

Prefabricated structure – Stage dimensions  - 1pc with total dimensions of 10x8 meters, with all the following audio equipment and lighting as it was specified in the Instructions to tenderers.

Lot 3:

Wooden info-desk – 20 pcs with total dimensions of 100x200x80 centimeters (W x L x H) at  the lower part and the height of two-sided roof-canopy of 200 to 220 centimeters for each info-desk, as it was specified in the Instructions to tenderers.

The place of acceptance of the supplies shall be Pozarevac, the time limits for delivery shall be:

|  |  | Time limit for delievery: |
| --- | --- | --- |
| LOT 1 | Prefabricated stucture - balloon | 2 months |
| LOT 2 | Prefabricated structure – stage | 50 days |
| LOT 3 | Wooden info desks | 30 days |

and the Incoterm applicable shall be DDP. The implementation period of tasks shall run from date of signature of the contract by all lots to date for provisional acceptance.

1.2	The Contractor shall comply strictly with the terms of the Special Conditions and the technical annex.

- Article 2	Origin

The rules of origin of the goods are defined in Article 10 of the Special Conditions.

A certificate of origin for the goods must be provided by the Contractor at the latest when it requests provisional acceptance of the goods. Failure to comply with this condition may result in the termination of the contract.

- Article 3	Price

3.1	The price of the supplies shall be that shown on the financial offer (specimen in Annex IV). The total maximum contract price shall be:

|  |  | Maximum contract price: |
| --- | --- | --- |
| LOT 1 | Prefabricated stucture - balloon | EUR/RSD |
| LOT 2 | Prefabricated structure – stage | EUR/RSD |
| LOT 3 | Wooden info desks | EUR/RSD |

3.2 	Payments shall be made in accordance with the General and/or Special Conditions (Articles 26 to 28).

- Article 4	Order of precedence of contract documents

The contract is made up of the following documents, in order of precedence:

- the contract agreement;

- the Special Conditions

- the General Conditions (Annex I);

- the Technical Specifications (Annex II [including clarifications before the deadline for submission of tenders and minutes from the information meeting/site visit];

- the Technical Offer (Annex III [including clarifications from the tenderer provided during tender evaluation]);

- the budget breakdown (Annex IV);

- specified forms and other relevant documents (Annex V);

- The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above.

Done in English in two originals: one original being for the Contracting Authority, one original being for the European Commission, and one original being for the Contractor.

| For the Contractor |  | For the Contracting Authority |  |  |
| --- | --- | --- | --- | --- |
| Name: |  | Name: |  |  |
| Title: |  | Title: |  |  |
| Signature: |  | Signature: |  |  |
| Date: |  | Date: |  |  |

Where the contracting party is an individual.

Where applicable. For individuals, mention their ID card or passport or equivalent document - number

Except where the contracting party is not VAT registered.

Each offerer fills time limits for delievery only for the lot that he competes for

Each offerer fills maximum contract price only for the lot that he competes for