ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania

## Contracting Authority

Intercultural Institute Timișoara

## Country background

The Interreg - IPA CBC Romania – Serbia Programme is a continuation of previous CBC programmes, under the framework of the new Instrument for Pre-accession Assistance (IPA II). The Programme is the result of a co-operative effort by the Romanian and Serbian national, regional and local authorities.

## Current situation in the sector

Intercultural Institute Timisoara as Lead beneficiary is implementing project InclusiveArt – Access to Culture for Disadvantaged Children and Youth together with Nevo Parudimos, City of Zrenjanin and Center for Fine and Applied Arts Terra, Kikinda.

## Related programmes and other donor activities

In September 2016 Timisoara was selected as European Capital of Culture. Now the cultural sector in Timisoara is under construction, creative sector and cross border cooperation, contributes to its development.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To increase the potential of the local communities and disadvantaged groups for innovative inclusive social practices by using art and culture to create inclusive contexts for integration and creative growth.

## Purpose

The purposes of this contract are as follows:

- Organisation of 4 cultural/artistic interventions in selected communities

- Organisation of Cultural Passport activities

## Results to be achieved by the Contractor

- 4 cultural/artistic interventions in 4 selected disadvantaged communities in Timiș county with the involvement of 8 artists and at least 30 children and young people / intervention

- Cultural Passport activities in Timișoara for migrant children and youth - 30 children and youth from migrant communities, accompanied by 30 adults (family members) will receive tickets to participate in minimum three cultural events.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The Contractor will receive the relevant information – content and visibility – from the Contracting Authority and the project staff involvement will be ensured. Any information related to the project, the content of cultural interventions, artists and communities will be provided to the media or transmitted in virtual spaces only with the prior consent of the Contracting Authority. The virtual channels used will be those of the Project and / or Contractor used jointly. From the information transmitted it will be clear that the Cultural Interventions activity is organized by the Intercultural Institute Timisoara within the InclusiveArt project, the contractor being the service provider.

## Risks

Risks to the project in question can be structured into four broad categories of risks: technical risks, financial, institutional and legal risks.

Technical Risks:

- The risk of an unexpected event during project implementation, event that would be leading to the impossibility of meeting its estimated costs and time;

- The risk that resources needed for the investment will cost more than expected;

- A poor quality of service technically.

Financial risks:

- The risk that the financier will not provide sufficient amounts of necessary resources and in time;

- The amount of investment and operating costs are understated;

Institutional risks:

- The risk that during the project, the general tax regime will change in investor’s detriment;

- If a facility is based on complementary support, the stakeholder may withdraw this support and the project can be adversely affected.

Legal risks:

- The risk policy and legislative changes to governmental authorities that are not anticipated and are addressed directly, specifically and exclusively designed for the project, which can lead to additional operational costs or capital.

The Contractor will ensure that they will take all the necessary measures to overcome all these risks. Close collaboration with the Contracting Authority will be ensured throughout the implementation of the interventions

# SCOPE OF THE WORK

## General

### Description of the assignment

Provide adequate services necessary for the organisation – production of four (4) cultural – artistic interventions in selected disadvantaged communities, two in Timișoara (Kuntz and Iosefin neighbourhoods) and two in other localities in Timiș County (Banloc and Lugoj – Maguri neighbourhood);

Provide adequate services necessary for the organisation of cultural passport in Timisoara for minimum 30 children and youth from migrant communities, accompanied by 30 adults (family members).

### Geographical area to be covered

Timișoara and Timiș County

### Target groups

120 children and youth from disadvantaged communities (minimum 30 per intervention)

60 members of migrant communities – 30 children and youth, accompanied by 30 adults (family members)

## Specific work

Under this contract two categories of activities are to be organised

4.2.1. Cultural – artistic interventions in 4 disadvantaged communities. Maximum available budget - 22,700.00 EUR

The Contractor will set up conditions for min. 4 artistic interventions to take place: two in Timișoara - Kunz and Iosefini 2 in other localities in Timiș county: Banloc, Lugoj - Măguri.

The contractor will provide adequate services necessary for the organisation – production of min. four (4) cultural – artistic interventions in the above mentioned communities. The four interventions are going to be proposed by maximum (8) young artists in collaboration with the local stakeholders and young Roma, all of them trained in the context of InclusveArt project.

The contractor will cover allowances for the maximum 8 artists implementing the interventions in the quantum of maximum 700 EUR total remunerations per artist (contract on authors’ rights) for a minimum of 14 days’ work. Also the contractor will cover accommodation, meals and transport costs for the young artists, the production costs of the interventions and small catering costs for the intervention participants (children and youth) – juice, water, sweet and salted patisserie for each work day.

Depending on the complexity, the interventions will be carried out in a maximum period of 4 months, with the duration of 14 to 21 days’ effective work of the artists in community. Days of artists' presence in the community will be proven through documents, presence list, photos other accounting documents. The quality of artists' work will be monitored by the Contractor together with the AC through joint or separate visits. At the end of the intervention artists will have to make a short report detailing their work by analyzing the way they perform. The information from this Report will be used in the Socio-Educational Animation Manual that the Institute will publish at the end of the project.

The project aims for an authentic interaction between young artists on one hand and the community on the other. The purpose is to improve the quality of life of children, young people and of community in general by providing a framework for their participation in new ways of cultural expression at local level. In this sense they will engage in a participatory cultural activity in their community that invites to active involvement by expression through attractive cultural means.

In the communities, interdisciplinary cultural activities will take place, using intervention means such as theatre, visual arts, music, literature, street art, film, video, photography, immaterial cultural heritage, handicrafts, performance, etc. depending on the professional structure of the young artists and on the specific of the communities, based on the artistic projects previously developed within the project InclusiveArt.

At the end of each intervention, an artistic – cultural event will be realised and presented in the communities (4 events in total). At least one live streaming will be realised – a live transmission, in real time, of one of the events. The most suitable event to be transmitted live will be selected by the Contracting Authority after consultations with the artists. The necessary equipment will be included by the artist in the intervention costs.

After the intervention the Contractor will organize in Timisoara an exhibition presenting the interventions (photo/video materials) with a public opening and an open discussion in the framework of the InclusiveArt project final Conference. Transport costs/fuel or tickets for selected participants from communities will be cover by Contractor.

These interventions may be realised together with the schools and they may be made permanent by setting up or realizing: mural art, permanent exhibitions, theatre groups, clubs, cenacles, workshops, artistic bands, instrumental bands etc., which will be active within schools and/or cultural/community centres. The necessary expenses will be covered by the Contactor in consultations with the artists and Contracting authority, within the limit of 5.000 EUR/ interventions/community (all cost included).

4.2.2. Cultural passport - Maximum available budget – 1,300.00 EUR

Cultural passport activities for minimum 30 children and youth from migrant communities, accompanied by 30 adults (family members) will take place in Timisoara. They are to receive tickets to participate in minimum three cultural events such as: theatre play for children, visiting a museum, musical event, book release etc., selected by the Contracting Authority at the proposal of the Contractor, depending on the cultural offer in Timisoara. The access to the target group will be facilitated together with Intercultural Institute staff. Their exposure to the cultural offer will contribute to a better knowledge of the cultural values and landmarks of the community where they live, and it will also contribute to socialisation with other children and parents.

Before or after the event the Contractor will organise minimum three debates – opportunities to discuss about for the events different topics such as: gender equality, protection of the environment, non-discrimination, cultural orientation, in accordance with the cultural activity to be attended. These discussions will be organised in such a manner that they are attractive for children and small catering costs – juice/ water, sweet and salted patisserie will be covered by Contractor.

The Contractor shall document each working day of every intervention and the Cultural passport activities using means like: attendance lists, photos, movies, media appearances, other materials, documents, etc.

## Project management

### Responsible body

The team of “InclusiveArt – Access to Culture for Disadvantaged Children and Youth” project from the Intercultural Institute of Timisoara is responsible for managing the contract.

### Management structure

The responsible persons for implementation of the tasks related to this contract, in the Contracting Authority are “InclusiveArt – Access to Culture for Disadvantaged Children and Youth” project staff and they will assist it step by step.

### Facilities to be provided by the Contracting Authority and/or other parties

The Contracting Authority will provide its staff (team) that will facilitate access to the communities and stakeholders and will nominate the artists and projects for each community.

# LOGISTICS AND TIMING

## Location

The Contracting Authority is located in Timisoara.

The locations of the Interventions will be: Timișoara (neighbourhood Kunz and Iosefin), Banloc, Lugoj -  Măguri.

## Start date & Period of implementation of tasks

The intended start date is the date of contract signature by both parties and the period of implementation of the contract will be 5 months from this date but not later than 01.11.2018. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Team Leader

Qualifications and skills

- University degree

- Knowledge of English language

General professional experience

- Experience in event organising

- Specific professional experience

- Experience in production of cultural artistic events is preferred or equivalent.

- Participation as team leader/equivalent position in one other project in the fields of this contract is considered an advantage.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular, it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language in one original and one copy:

- Interim reports (if it is the case). The contractor can prepare interim reports after providing the services, or a part of the services, according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments as indicated in the Special Conditions.

- Draft final report. This report shall be submitted at the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 4 working days after receipt of comments on the draft final report.  The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports after the consultation for each intervention with the project responsible for cultural activities and the PR responsible.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality and quantity manor, as required in these Terms of Reference.

## Special requirements

Not applicable