# VOLUME 3

# TECHNICAL SPECIFICATIONS

Purpose of this present procedure is the assignment of the public acquisition contract for the elaboration of the technical-economical documentation   (PT+CS, DE, P.A.C,P.O.E), technical verification of the project including the technical assistance for projection and execution of the mounting construction works, and for the investment objective “Putting under safety of the Sanmihaiul Roman knot” component part of the project IPA CBC Romania-Serbia “The repairing of the navigation infrastructure on Bega Canal”.

GENERALE DATE:

Contracting authority:  National Administration „APELE  ROMÂNE ” - Banat River Basin Administration with the headquarters on Timisoara, Mihai Viteazu, no.32, Postal Code 300200

Correspondence address: Timisoara, Bd. 16 decembrie 1989 nr.2

Funding Source:

Co – funding IPA CBC Romania-Serbia (85%) +State Budget (13%) +Own contribution (2%)

Maine location of the works:

The position of the works that are the subject of this investment are placed in the hydrographical area Bega-Timis- Caras on Bega water channel, downstream  Timisoara City, in the administrative- territorial area of the Sanmihaiul Roman village, at  approximately 950 m upstream from Sinmihai Bridge over the canal, in front of the Km 28+200 on the dike left bank measured from Serbian border.

The juridical status of the lead that is going to be occupied:

The investment does not foresee new constructions, the most of the proposed work beeing for repairing, consolidation and replacement of the some constructive elements that are damaged or being in a advanced degradated status. The location where the works will be executed is under the administration of the National Adinistration “Apele romane” – Banat River Basin Administration.

State of final land occupation

For the realisation of the investment it is not necessary the final extra land occupation, but temporary will be occupied a surface of aproximately 5000 mp for the technological access roads and the access ramps. The occupied lands will be returned, at the finalization of the works to the initial purpose.

Period for accomplished the investment objectives:

Execution period of the works is estimated at 28 months (from the beginning of  signing the contract and from the issuing of the order of the commencement).

GENERAL INFORMATION REGARDING OF THE INVESTMENT OBJECTIVE FOR WHICH IT IS REQUESTED THE OFFER OF THE TECHNICAL ASSISTANCE FOR PROJECTION AND EXECUTION OF THE MOUNTING CONSTRUCTION WORKS

The navigable Bega, arranged almost 250 years ago is hydro-technically seen as a construction including special technical arrangements, and especially of historical significance,   significant works which focus on the concept  and execution progress in this field.

The navigable way Timisoara (Romania) – Klek (Serbia) has a total length of 114.5 km (71.5 mls), of which 44.5 km (27.8 mls) on Romanian territory and 70 km (43.7 mls) on Serbian territory.

The navigation on the canal on Romanian territory was closed down, due to the evolution of political situation in the year 1958, situation which is maintained up till present. On Serbian territory, the navigable sector of the Bega canal connects with the navigation and hydro –ameliorative system Danube-Tisa-Danube. This is the reason why the Bega canal has a strategic position and facilitates the connection between the western part of Romania with the North Sea and with the Black Sea through the Rhine-Main-Danube Canal.

On Romanian territory the navigation   water races are created  by Hydro-knot Sanmihaiu Roman and Sinmartinu Maghiar (Uivar).The water race UHE Timisoara-NH Sanmihaiu Roman is vital for the city of Timisoara, considering the functions of this work:

At present the hydro-knot ensures:

-maintaining a minimum level in the upstream water race to ensure the supply  with drinking water, industrial and fire- fighting water of economic companies in the city of Timisoara;

-realising a constant level in the water race to maintain aquatic life and ecological demands and health of the population;

-possibility to evacuate the flood without causing flooding in the water race, as well as evacuating the ice between  21st December-21st March. In the meantime it ensures the maintaining of the transited flows during the limits established by the Romanian-Yugoslav Agreement, regarding the operating regime of the Bega Canal (minimum and maximum);

-realising the level to ensure the navigation in the navigation water race.

In this project, the objective is to accomplished a large part from the works of the “Putting under safety of the Sanmihaiul Roman knot”, Timis County, with the technical-economical guide approved by HG 281/13.04.2016. Fromm reasons to fit into allocating funds of project financed by IPA CBC Romania – Serbia, in this program the design works will be financed (PT+CS, DE, P.A.C.,P.O.E) for the rest of the execution (the steps 2,3,4,5) and work execution regarding the rehabilitation of the barrage dam  and lock (including the machinery and the  hydromecanical equipments and assembling them), the rest of the works regarding step 5 (landscaping of the island and exploitation constructions) will be realised from different finance sources.

The objective of the investment is to accomplish the works regarding the “Putting under safety of the Sanmihaiul Roman knot”

PRESENTATION OF THE INVESTMENT

Necessity and opportunity of the investment

Along the years there have been many attempts of works’ restoring and placing under safe conditions. In 1988 the investment for capital repairs of the knot has been promoted. In the first stage there have been designed, confectioned and procured the hydro-mechanical equipments and the necessary embedded parts, but later, due to  lack of funds, the investment has been ceased.

In 2011 the hydro-knot has been the object of a new investment, financed by the World Bank, the main result being the deviation of waters through the locks and placing the objective to dry, in order to expertise and evaluate the necessary works. (stage 1)

Taking in consideration the entire lack of the funds and even lack of the current maintenance and missing the hydro mechanical equipment, at  present the objective is in an advanced degradation condition.

- The advanced degradation status of the water evacuation systems and equipments affect the general safety of the hydro-technical arrangement and connected with the foresees of the Romanian-Yugoslav foresees on the Canal  operating   system -   make the risk of stopping the functioning of the hydro-knot to be unacceptable.

-The damage of the hydro-technical knot might lead to water level decreasing below the minimum level for assuring the utilities (drinking and industrial water supply), with negative impact on population and economy on one side and direct impact on the environment on the other side.

Not least, preserving the actual situation (the blocking of the cylindrical weir and deviation of water through the locks, without any possibilities of operating and dredging) leads to an increasing degradation of the upstream water race and hence reducing the transport capacity of the canal (rapid silting), reducing the flood protection below the admitted limit respectively.

Moreover, besides the above mentioned facts, the Sanmihaiu Roman hydro-knot  is classified as a B class monument of national interest, situated at position 276 –TM II-m-B-06283 on the historical monuments list.

CONSTRUCTIVE ELEMENTS OF THE HYDROTECHNICAL KNOT

The weir dam – is located on the right bank of the Bega Canal, being a construction of concrete founded on wooden piles.

It has 3 openings:

- One equipped     with a double plane weir for regulating the navigation levels – 5.0x4.5/4.5

- One equipped with a cylindrical weir for transitions of maximum flows – 15.0x3.45/3.5

- One equipped with plane weir to evacuate the floating and ice – 1.6x4.5/4.5

In longitudinal section the weir dam is formed of:

-an antefloodbed of simple concrete with the length of 10 m and width of 20 m;

-the general flood bed of concrete with the length of aprox. 18 m and a width of 21 m;

-apron basin with the length of 20 m;

-rear of stones

Both banks are protected by a peree of  rough stone of 30 cm.

The weir suprastructure is made of concrete and stone masonry presenting following dimensions:

-the right bank pile has o length of 12.0 m, the flood bed height 5.35 m and a width of 2.0 m;

-the left bank pile has a length of 13.6 m, an apron flood bed of 7.0 m and a width of 3.1 m;

-the abutments of left and right dike present  a trapeze shape in   cross section with the coping width of 1.5 m and at the contact with the flood bed of aprox. 2.5 m.

Part of the dam constructions assembly is also the chamber or house of maneuver and represents a building included in the technical and historical patrimony of Romania, realized of materials and presenting an architecture specific for the beginning of last century.

The chamber is realized of molons made of masonry with a roof framing four slopes and a covering of ceramic tiles.

The wooden works is made of metallic profiles and the interior finishes are simple: smattering of lime plaster on walls and floor of ceramic tiles.

Operational constructions - The complex is located on the left bank of the lock and was realised at the same time with the constructions that form the Sanmihaiu Roman hydro-knot and was destinated for the personnel operating the arrangement.

The complex includes the operation post, building included in the technical historical patrimony of Romania, the double operating building used for hosting the operational and surveying personnel and some household annexes (stables, storage houses, workshops).

The post is a construction with basement and ground floor with the dimensions of 9.20x10.00 m with a small decra on the northern façade and is made of brick masonry and slope roof with ceramic tile cover. The joinery is of wood. The floors are made of wood in rooms, mosaic in the rest of chambers at the ground floor and of cement at the basement.

The double operational building is a construction with ground floor and basement, with the dimensions of 9.20x10.00 m and is made of brick masonry, slope roof and ceramic tiles cover. The joinery is of wood. The floors are made of wood in rooms, mosaic in the rest of chambers at the ground floor and of cement at the basement.

The surrounding is made of brick base and piles and metal panels.

Due to the almost total absence of interventions or of usual maintaining works, the constructions and hydro-mechanical equipments are in an advanced state of degradation.

The lock – is located on the left bank of the weirs and is connected to the canal by 2 access canals (waiting harbours).

The upstream access canal has a length of aprox.22.0 m and the downstream one of aprox. 150.0 The taluses of the canals are protected with stone peree.

The lock has a total length of 115.0 m and is formed of:

-connection zones to the upstream and downstream canals protected with stone peree;

- the lock chamber with a total length of 70.0 m has an opening of 10.0 m in cross section;

-the lock walls are of brick masonry protected at exterior with concrete, in cross section presenting a trapeze shape with a coping width of 1.0 m, at the base of 3.2 m and a height of 5.7 m;

-the upstream and downstream  lock ends have a length of 10.0 m each, are executed of stone masonry plus concrete and foreseen with  niches for gates and  acicular cofferdam.

-The lock flood bed is of concrete, founded on wooden piles and presents a width of 2.0 m.

In order to fill and empty the lock two side galleries are foreseen, with a total length of aprox. 90.0 m each and a section of 1.5m2.The galleries are equipped with valves at each ending for filling –emptying.

The mechanical equipments of the lock are operated manually and consist of:

- The upstream and downstream lock gates with mechanical control on the rack;

- Valves for filling and emptying the lock (4), 2 upstream and 2 downstream, located in chambers located at the ends of side galleries;

The valves handling is also manually.

* Technical expertise established that actual technical situation of the hydromecanical equipment of the new Hydrotechnical knot, is no longer updated being necessary to new projection and producing of new equipment conforming to actual technical rules.

WORK DESCRIPTIONS

The designed works are foreseen to be executed in 5 stages, including the land restorations after works finishing.

Phase 1: Deviation of waters through the lock and putting the weir dam to dry*

Phase 2: Rehabilitation of weir dam**;

Phase 3: Placing the lock to dry

Phase 4: Rehabilitation lock

Phase 5: Island restoration***

*The proposed works to be realized in the first stage  were realized and receptioned.

These consisted of realizing a discharge sill in order to assure the transit in good conditions for the entire operating flows through the lock canal during the entire period of dam rehabilitation works. In the meantime a part of the necessary accesses were realized, the temporary bridge over the lock to permit the access to the island and the access road on the island to realize the works of placing the lock to dry. These are going to be subsequently decommissioned during this program.

** Rehabilitation of the dam and exploitation constructions is projected in this program and will be executed in other financing program.

*** Restoration of the island landscape will be designed in this program and will be executed in other financing program

Execution phases:

Phase1 Works regarding the water deviation (realized and reception) are going to be subsequently decommissioned (demolition of the existing weir box on the upstream of the dam, the demolition of the landfills of the lock and the decommissioning of the rod bridge). This works will be executed during this project.

Phase 2  Is represented by the rehabilitation of the dam and exploitation constructions **

As preliminary works regarding rehabilitation of the dam will be executed unsilt up and downstream from this, because in the present are massive bank deposits.

2.1 Repairing and rehabilitation of the dam weir are presuming the following works:

- The anteflood bed rehabilitation. Will be realized by rehabilitating the  surface concrete; - breaking the degraded concrete, washing, bush hammering, brushing, air cleaning,  hole drilling, mounting and fixing anchors, net mounting and pouring a 50 cm thick concrete layer.To reduce the infiltrations and pressures  below the anteflood bed sole in front of it, along its section till the bank embedment a screen of metallic piles will be foreseen. The screen depth will be of 4.00 m   measured from the concrete wear.In front of the screen a 1 m deep rock filling will be realized.Because along the flood bed the peree  is  degraded,  it will be rebuilt again, according to its degradation. The peree rebuilding solution will be identical to that initially designed.

- Rehabilitation of apron basin.Will be realized by rehabilitating the surface concrete, the same way as in the previous case. There are concrete surfaces which will be rehabilitated by applying special mortar. The degraded peree will be  refurbished or newly rebuild.

- Rehabilitation of the rocks rear. This will be entirely rebuilt along the river bed section on a length of 72.50 m till its connection with the island  downstream area.

- Rehabilitation of dam  abutment and piles. Their rehabilitation takes into account the technical monument aspect of the building. Intervention such as general cleaning, completion gaps with mortar, replacing destroyed slabs with other of same form and dimension. The concrete area will be rehabilitated by applying special mortar. The pedestrian bridge will be also rehabilitated. Demolition and rebuilding works for hydro-mechanical equipments  concrete will be foreseen.

- Mechanism house The rehabilitation works’ main purpose is to rebuild architectural and functional the space for cylindrical weir functioning and dam double weir, which might be considered minimum interventions by their nature, for preserving the exterior and interior architectural aspect, this being a B class monument, situated at position 276 – TM – II m – B – 06283 on the historical monuments list.

Following works are proposed:

  - Sloop roof repairs by replacing the degraded element, preserving its form

  - Rebuilding the roof ceramic tiles cover and its accessories

  - Cleaning exterior masonry and replacing the degraded elements

  - Disaffecting the existing metallic joinery, the access door and windows and replacing it with a special metallic joinery, preserving its original aspect

  - Interior refurbishment of walls, by cleaning and applying a new layer of emulsion paint

  - Cleaning and refurbishing the protection paint at exiting metallic works

  - Replacing the existing floor with a new identical one

  - Entirely replacing of electric equipments (interior lightning,  earth connections, lightning rod)

  - Repairing the degradated elements, cleaning and applying a protection painting at wrought iron fence

  - New layer with metallic piles placed at 2.5 m and Buzau net panels (2.0 m width)

  - Rebuilding the exterior slab platform

- Rehabilitation of hydro-mechanical equipment

The expertise to establish the actual technical status of hydro-mechanical equipments for serving the hydro-knot has revealed the fact that they do not correspond anymore , thus designing and producing new ones according to the present technical norms should be considered. Considering this and the fact that the dam is an historical monument preserving the same type of hydro-mechanical equipments is desired, the rehabilitation works consist in their complete replacing   with new ones.

- Cylindrical weir 15.0x3.45/3.5 – 1 piece

-the embedded parts will be replaced except for the racks.

-the weir metallic construction as well as the sluice valve will be completely replaced, together with the wooden   sealing    elements

-the handling mechanism is manual, only rehabilitation works will be realized consisting in replacing the depreciated ones (chain,   bush etc) and repairing their functionality

b)   Double plane weir 5.0x4.5/4.5 – 1 piece

- the embedded parts will be replaced

-the weir panels will be rebuilt, preserving the initial model

-the handling mechanism will be rehabilitated and preserved within its original form adding   electrical handlings

-two cofferdams of 5.0x4.5/4.5 will be executed and mounted including their elements for placing to dry the double plane weir

c)  - the plane weir 1.6x4.5/4.5 – 1 piece

-the embedded pieces will be replaced

- producing and installation a new weir panel

- execution of handling grid Md 1.6/1.6 necessary to handle the plane weir

- rehabilitation and completion with missing parts from the weir handling mechanism

-execution and installation of a cofferdam 1.6x4.5/4.5 and  embbeded parts.

d) different metallic confections, consisting in rehabilitation and replacing access stairs, lids, frames etc.

All the new equipments that will be installed will present the same technical and functional features with the ones existing at the location.

- The access roads and platforms.  This road will be rehabilitated on a length of 1,025.00 m, of which 770.00 within the settlement.

The rehabilitated road will preserve the actual   route within the settlement street and on the rest of 325.00 m will preserve the actual island access road.

The geometrical elements of the rehabilitated road sector:

-Platform width lp = 5.00 m

-Traffic way width lc = 3.5 m

-Side roads 2 x 0.75 m

Earth moving works will be done consisting of diggings, compactions and transport of excavated material.

In order to realize the road foundation  flatworks and road platform preparing on an surface of 3,600 m2 will be realized.

The access road supra-structure will be realized of 20 cm of ballast, after compaction, 20 cm of cement concrete C25/30 and 4 cm of asphalt concrete Ba 16. A layer of 10 cm ballast is foreseen on the side roads after compaction.

On the access road the proposed traffic system is needed to take over the foreseen heavy traffic during the Sanmihaiu Roman Hydro-knot rehabilitation works.

After ending  the Hydro-knot  works the road will be marked using white paint.

2.2 Operational buildings ** :

For the efficient use of the Hydro-knot, the post (operational main building) and the buildings inside the complex need following intervention works:

The post

- Rehabilitation the wooden roof slope by replacing the degraded ones

- Rehabilitation the ceramic tile cover and roof accessories, (water pipes) installed on a layer of coating and water proofing foil

- Constructing   a partial  penthouse  in the existing attic    with partition walls of gypsum cardboard           RF of 15 cm,  with mineral wool mats insulation and ceilings of gypsum cardboard RF fixed on rafters with a 15 thick  mineral wool mat insulation inbetween

- Installing  Velux lighters to lighten the penthouse area

- Realizing a thermal insulation of 15 thick mineral wool mats, installed in the attic area in order to realize an efficient insulation of the interior ground floor  area.

- repairing damaged exterior plasters, plating the external picket with a layer of polystyrene of 10 cm, over which a thermo-system is applied

- refurbishing the exterior finishes with structured plasters, preserving the initial exterior aspect

- Local repairs at interior plasters and cleaning existing finishes at walls and ground floor ceiling

- Installing a suspended ceiling at the ground floor at 50 cm from the existing ceiling, to reduce the height

- Cleaning the existing finishes at the basement and applying a hydro-insulation protection mortar to stop infiltrations into the building

- Replacing the exterior wooden joinery (doors, windows) with wood joinery and insulating glass, preserving the initial aspect

- Remaking the interior finishes at walls and ceiling by applying a new plaster layer and finish layers with emulsion paint in rooms and a faience plating at a height of 210 cm in bathrooms and kitchen

- Replacing the existing floor by  restoration mortar screed support and installing a new laminate floor in rooms and tiles in the remaining space

- Repairing the access stairs to the basement and penthouse using skid tiles

- Repairs at electrical installations, including: interior lightning installations, exterior electrical connections, earth plate and lightning rod

- Installing interior sanitary appliances, building sanitary groups inside at ground floor and penthouse and connection  to the  water-meter manhole

- Replacing the wood stove heating system with gas heating and execution of a thermic power interior installation

- Replacing the existing brick alley and pouring a new alley of reinforced concrete with net STM

Double operational building

- A layer of 10 cm thick polystiren over which a net reinforced plaster (thermosystem) will be applied;Rehabilitation of wooden slope on chairs by replacing the degradated elements; repairing damaged exterior plasters

- Rehabilitation the ceramic tile cover and roof accessories, installed on a layer of coating and water proofing foil; (fascia board, eaves, downspouts);

- Realizing a thermal insulation of 15 thick mineral wool mats, installed in the attic area in order to realize an efficient insulation of the interior ground floor  area

- Repairing of the degradated exterior plasters, platting  the external picket with a layer of polystyrene of 10 cm, over which a thermo-system is applied

- Repairing the exterior finishes with structural plasters, preserving the initial exterior aspect.

- Local repairs at interior plasters and cleaning existing finish at walls and ground floor ceiling

- partition  of walls with gypsum cardboard   of RF of 10 cm, in order to  build 2 sanitary groups

- Cleaning the existing finish at the basement and applying a hydro-insulation protection mortar to stop infiltrations into the building

- Replacing the exterior wooden joinery (doors, windows) with wood joinery and insulating glass, preserving the initial aspect

- Remaking the interior finishes at walls and ceiling by applying a new plaster layer and finish layers with emulsion paint in rooms and a faience plating at a height of 210 cm in bathrooms and kitchen

- Replacing the existing floor by  restoration mortar screed support and installing a new laminate floor in rooms and tiles in the remaining space

- Repairing the access stairs to the basement and penthouse using skid tiles

- Total repairs at electrical installations, including: interior lightning installations, exterior electrical connections, earth plate and lightning rod

- Installing interior sanitary appliances, building sanitary groups inside at ground floor and penthouse and connection  to the  water-meter manhole

- Execution of an interior thermic installation and connecting it to the thermic heating installation existing in the post.

- Replacing the existing brick alley and pouring a new alley of reinforced concrete with net STM

Households annexes

- Rehabilitation of annexes by carrying out sanitation works, exterior and interior plastering works, cleaning existing finishes and refurbishing them using emulsion paint, repairs and painting the joinery, repairs at roof slopes and ceramic tile covers

Technological annex

- It is proposed the execution of new technological annexes, of 6.00x11.00, that will include a workshop and a deposit room

- The annex will be of brick masonry GVP, with piles, belts and reinforced concrete plate, slope roof with ceramic tile cover, structured plaster at the façade and emulsion paintings at interior, cement washed concrete floor, PVC profile joinery, earth plate an alley of plain poured concrete

- The annex will be equipped with interior electrical lightning installations, exterior electrical connections, earth plate and lightning rod.

Connection to utilities

- A sewerage system will be realized inside the complex, the  discharge of waters will be directed into a monobloc waste water reset

- A connection to the commune existing gas network will be established, its length being of aprox. 100 m

- The existing electrical power connection will be rehabilitated.

Enclosure arrangements and fencing

- Vertical systematization of the enclosure and rehabilitation of rain waters collection

- Access road and work concrete platform will be executed and the existing alley will be rehabilitated

- The existing fencing will be rehabilitated with frame work and plated piles and metallic panels, including the access gates

- The landscaping will be rehabilitated by planting sod, shrubs and trees.

Close circuit TV system (CCTV)

- To protect from unauthorized entrance to the objectives as well as signalizing these attempts video monitoring and theft preventing signalizing for main points has been foreseen

- Video monitoring will be realized by exterior video cameras   for maximum 50 m distances, PAL system, including lens, infrared and during the night, IP minimum 65 on  rotating supports that will be supplied and connected for data transmission from watch case.

- The energy supplying and data transmission cables will be protected with a flexible metallic tube against vandalizing, fixed on construction elements on which it is posted

- At dispatch CCTV system control elements have been foreseen:

- A command desk with a recorder and a shareable monitor, the recorder has the possibility to  store the images for 30 days.

- The theft preventing signalizing will be for each protected objective as well as at the dispatch office. Thus, each video camera located in the risk area will have a movement detector that will survey   the enclosure and will be connected to the respective   watch case and will transmit via a special channel signals to the dispatch office. Additional, detectors will be installed in the dispatch area for preventing   unauthorized entrance within the authorized personnel area. The station will collect these signals and according to the program will transmit to the indicated destinations or will start the alarms at the dispatch office or the local ones.

- The dispatch stations is foreseen with a redundant system, being operable by 2 DVR storing equipments  with memory for events storing, self -diagnoses,  own supply source with accumulator/battery, and for deactivating the alarms a separate keyboard with reconfigurable code for CCTV systems.

- Starting with offer submission, the equipment and system compatibility with the project will be considered a complete integrated system.

- Rebuilding access road from the county road DJ 591to the hydrotechnical knot

- The access road from the county road will be realized  using a traffic concrete layer.

** During this program will be accomplished only the projection of the works for the Operational buildings, execution will be part from a different project funds.

Phase 3  - foresees works for placing the lock to dry

3.1 Works for placing the lock to dry.:

- the works consisted in demolishing the earth cofferdams necessary to place the dam to dry,

- extracting the metallic piles and moving them upstream and downstream the lock

3.2  The access road from left bank

This road will be rehabilitated on a total length of 235.00 m, ensuring the access on the left bank, parallel with the lock and the related canal.

The geometrical elements for the rehabilitated road sector will be:

- Platform width lp = 5.00 m

- Traffic way width lc = 3.5 m

- Side roads 2 x 0.75 m

Earth moving works will be done consisting of diggings, compactions and transport of excavated material.

In order to realize the road foundation  flatworks and road platform preparing on an surface of 940 m2 will be realized.

The access road supra-structure will be realized of 20 cm of ballast, after compaction and  10 cm macadam after compaction, the side roads being of earth.

This proposed  traffic system is sufficient for the left bank road, it being mainly an operational and intervention road.

3.3 Disaffecting and transportation of the temporary bridge  After realizing all the rehabilitation and arrangement works at the Sanmihaiu Roman hydro-knot and of existing island, the temporary bridge for the island access, situated on the left bank will be disaffected and transported outside the hydro-knot perimeter.

Phase 4  - includes lock rehabilitation works and A part of the works were realized in phase 1.

The works in this stage consist of:

4.1 Hydro-mechanical equipment - At present, at location the lock gates are deposited on the coping. The cassation of the existing equipments is wished and their replacement with new ones.

a) lock gate 10x5.3 upstream with 2 canals – 1 piece

- replacement of embedded parts

-execution metallic construction for the 2 canals

-replacement for the mechanical parts and valves equipment (2 pieces)

-replacement of manual handling mechanism (2 pieces)

-execution and installing a cofferdam 10x5.3 and its embedded parts.

b) lock gate 10x5.3 upstream with 2 canals – 1 piece

-replacement of embedded parts

-execution metallic construction for the 2 canals

-replacement for the mechanical parts and valves equipment (2 pieces)

-replacement of manual handling mechanism (2 pieces)

-execution and installing a cofferdam 10x5.3 and its embedded parts.

c) plane valve 0.85x1.225/5.6 – 4 pieces.:

- replacement embedded parts

-procurement and installing rolling  plane valve 0.85x1.225/5.6 with manual handling

-executing and installing a cofferdam necessary to place the valve to dry

d) different metallic confection, consisting in rehabilitating or replacing the access stairs, lids, frames etc.

4.2 Unsiltings, peree rehabilitations, slabs and deteriorated molons replacement  will be realized.

4.3 Realizing of  boarding and landing stocking in the waiting area, upstream the existing  discharge sill that will be demolished at works finalizing.

4.4 Demolishing and rebuilding  of mounting concrete works afferent to hydro-mechanical equipments

Phase 5 includes island landscaping works

Within the rehabilitation works at the Sanmihaiu hydro-knot the arrangement of a recreation spot on the island between the lock and Bega river bed is proposed.

The arrangement consist of a surrounding alley and connection middle alleys foreseen with benches at a distances of 10 m from each other.

The works will be completed by landscaping works at the green area between the alleys, by planting trees, shrubs, flowers and sod sowing.

To ensure the objective protection and its safety around the hydro-knot a fence of net on metallic piles is foreseen.

Also on the island shore  the realizing of a stone peree is proposed, the solution is identical to the perees existing in the dam area.

*** The island landscaping works will be projected during this program and will be executed  in a different project.

GENERAL INFORMATION

1. DESIGN ACTIVITY: - developing the technical-economical documentation (phase P.T+C.S., D.E., P.A.C,P.O.E) for the investment objective above mentioned.

The design activity includes the technical-economical documentation (phases: - project for obtaining the authorization for execution of the constructing- installing works; project for set up work execution; technical project for work execution for the hydromecanical equipment constructing-installing) in accordance with: HG no. 907 from 29 of December 2016, regarding the steps for elaboration and frame content, of the technical-economical documentation, associated with the investment objectives financed by public funds.

The design is executed for all phases of execution presented (phases 2,3,4,5) with the mention that will be presented separated in distinct way :

-  Putting under safety of the Sanmihaiul Roman knot (phases 2.1 , 3 , 4)

-  Island landscaping works (phase 5)

-  Reabilitation of the exploitation constructions (phase 2.2)

The design activity will consist in elaboration of the following documentation:

• The technical-economical documentation (phases: - project for obtaining the authorization for execution of the constructing- installing works; project for set up work execution; technical project for work execution for the hydromecanical equipment constructing-installing, technical project for hydromecanical equipment installing ) according with technical-economic approved indicators  by the  Water and Forestry Ministry no. 1341/06.07.2016.

• All necessary studies (topography, geotechnical, hydrological studies, expertise, and evaluation study over the environmental impact).

•  Preparing the technical documentation and to obtaine all the necessary permits, approvals and authorizations requested by the Urban Planing Certificate, including technical documentation for building permit (DTAC), and obtaining the building permits.

• Providing the cadaster maps (scale 1: 1000) on the projected works location, in according with STEREO 70 coordinate, approved by the O.C.P.I., that are in conformity with Romanian legislation for the investment objective above mentioned; Overlapping with land register of the plan limits of the proposed works.

- Provideing the location plan and delimitation of the construction from the field, with the present situation of the works

• Inventory of the existing support network, necessary works to extend the support network for all utilities;

• Verifying the technical-economical documentations (phases: - project for obtaining the authorization for execution of the constructing; project for set up work execution; technical project for work execution, technical project for hydromecanical equipment installing ) and drawing the verification report that will be made by the economic operators or authorized physical persons, certified for the following demands:

A1- “Resistance required and stability for constructions with the structure of reinforced concrete, masonry or equivalent

A7 – “Resistance and stability for constructions and hydrotechnical improvements”, or equivalent

B5- “Construction safety and hydrotechnical improvements”, or equivalent

D- “Hygiene, people’s health, restoration and environmental protection” or equivalent, in conformity with the H.G. NO.925/1995 and M.L.P.T.L Order 777/2003, with the modification and further additions;

Af - Mechanical resistance and stability of earth masses, foundation ground and interaction with buried structures

Ie –“Internal / external electrical installations related to the construction” or equivalent

It- “thermal indoor installations” or equivalent

Is- “interior plumbing installations” or equivalent

Technical verifier certified by the Ministry of Culture in the fields 1_______________ architectural restoration and 4 - consolidation and restoration of historical structures, for the rehabilitation of the maneuver  building.

• Development of the exploitation instructions;

• Drawing the draft presentation regarding the way of work execution, necessary to the reception of the objective;

• Updating the general estimate, any time the buyer is requested, until the end of the works.

• Including in documentations of Plan for security and health for works at investment objectives, according to HG 300/2006 foresees, with additional modifications and completions and of PSI necessary measures at works execution.

• Developing any study or documentation (regarding to the investment objective, above mentioned) requested by the beneficiary during the work executions for the objective above mentioned.

•Including the environmental protection require documentation, in conformity with the evaluation documentation of the impact over the environmental factors.

•When developing the technical-economical documentation, the the Medium and Long Term National Strategy on floods will be taken in to account (in accordance with H.G. nr.846/2010 and any legislative updates).

With the submission of the Technical Project for execution, documents will be presented to highlight the current situation of the constructions resulting from the investment, and technical data from showing the area occupied by the newly created good investment with its technical and constructive features (areas related to the work, lengths, dykes, heights, insurances etc. – data from technical sheets).

The designer will provide specialized technical assistance throughout the execution of construction works and installation of hydromechanical equipment for the investment objectives mentioned above;

1.1 Documentation requirements:

The design documentation verified and endorsed by a certified project verifier will be provided in term of maxim 2 (two) months from the moment the contract will be signed, as follows:

- Field studies: 2 copies per paper and one CD;

- Technical documentation of approvals / agreements / land according to the annexed CU - 2 copies per paper format and one CD copy;

- The project for the authorization of the execution of the construction works - P.A.C. - 2 copies per paper format and one CD copy;

- Project for the organization of the works  execution- P.O.E. - 2 copies per paper format and one CD copy;

- Projects: the interior plumbing, thermal and electrical installations – 2 copies per paper format and one CD copy;

- Technical execution project: 4 copies per paper format and one CD

The CD will contain written and drawn pieces, type [* .doc] for written pieces, type [* .pdf] for drawings. The [* .pdf] files will have the appropriate resolution to be viewed in detail, or printed in the original format, while preserving the original drawing features.

-The project desig will be presented in Romanian and English language

- The technical project will be presented as a technical memoire to the project team in term of one monts from contract signing, before obtaining all the necesary permits.

1.2 Aspects presented in the technical offer

a) Methodology for designing services

The bidder will present how he / she understands:

- the objectives of the contract and the tasks set out in the technical specifications;

- the approach followed in performing services, including the description of the concept used to achieve the objectives of the contract;

- the methodology of carrying out the activities in order to obtain the expected results.

At least the following information should be provided here:

- the legal provisions in the field of activity related to the object of the contract to be awarded, which may have an impact on its development / implementation;

- identifying and explaining the key aspects of achieving the objectives of the contract and achieving the expected results;

- the way of approaching the activities corresponding to the final result of the contract and the related interim results, in relation to the established services and responsibilities.

The described activities must be presented as duration, within the working plan.

b) Work plan for services

The tenderer will provide the following information:

- the name and duration of activities and package activities of the contract, as they are presented in the "Methodology" chapter;

- the succession and interrelation of these activities;

- key control points.

The proposed work plan should be:

- in line with the proposed approach and methodology

- to demonstrate:

-   understanding the project's provisions;

-   the ability to translate the provisions into a feasible work plan;

-   timing of activities so as to ensure that services are completed in due time.

3. to be achieved using time planning software.

c) Organization and staff used to deliver services

At least the following information should be provided here:

-  the structure of the proposed team for contract management;

- way of approaching the reporting activity regarding the progress of services, on the progress of services, including the final documents in relation to the technical specifications;

- a description of the infrastructure that the contractor uses to perform the proposed activities to fulfill the object of the contract. This infrastructure must be appropriate to the purpose of the contract and fulfill all the requirements required by the legislation in force.

-  the approach for identifying the risks that may arise during the course of the contract and risk mitigation measures

-  the approach for prevention / mitigation / elimination or minimization of the effects, if the case, of the risks identified in the specifications;

-  the approach to the requirements on health and safety at work including how the tenderer will ensure that during the execution of the contract the legal obligations relating to the conditions of work and protection of labour are respected (if applicable)

- the approach in the relationship with subcontractors, in relation to the nature of the activities subcontracted (if applicable).

- evaluation of the use of resources in terms of man-days of work, staff travel and the use of equipment allocated to all organizations(including the contracting authority) whose efforts are necessary for contract drafting

- ACTIVITY OF EXECUTION CONSTRUCTION-ASSEMBLING WORKS:

The tenderer is obliged to make proof of respecting the compliance of works execution proposal with quality and quantity requirements of the project and foreseen in the  normatives in force which regulate the work executions.

The technical proposal will contain:

- quality programe that concretizes the system for assuring and leading of quality to works particularity, object of tender, approved by specialists or abilitated bodies;The quality programe has to contain:

- the quality system description, applied to the work, including the lists of procedures afferent to quality system

- Lists of technical execution procedures for main categories of works regarding the realizing the objective and quality, verifying and testing control plan

- The laboratories used and authorized according to the works degree

- Works execution schedule

- Lists of works quantities completed on chapters, afferent to works categories,  entirely respecting  of quality and quantity requests contained in the project, tender books and other applicable laws that regulate the works execution.

- Technical papers afferent to tillages quantities and technological equuipments, with assembling and independent, including endowments afferent to the work,  part of the public procurement contract to be executed

- Price tender for hiring or analyses for prices used for issuing the tender, corresponding to all the  the tillages necessarry for  the works execution

- The price tender  for hiring or analyses for the prices used for issuing the tender, corresponding to all the transports necessarry for the works execution

- Technical features and analyses documents afferent to the stone quarry, issued by an attested laboratory according to the legal foresees in force.

For the own tranportation means and tillages or hired afferent technical documents and transport licences will be presented, according to the legislation in force.

In order to justify the material prices offers from the suppliers will be attached,  these will cover entirely the works categories afferent to the objective.

In order to avoid underevaluation for some works categories or offers , these will include:

- ferm offers for the material prices, signed by suppliers, for all categories of materials afferent the objective.

-value for total consumes of material resources

-value for total consumes with labour

-value for total consumes regarding construction tillages

-price analyses/offers for hiring for construction tillages and means of transportation respectively

- value of total consumes regarding transports

-value for tillages and  hydro-mechanical and technological equipments, with assembling and independent, including the works afferent endowments, whose gain is object of public aquisition

-the sum of indirect expenses ( expressed in % from Total direct expenses) and of profit (expressed in % from Total direct expenses+indirect expenses).

-The building site organization is compulsory and will be justified by a building site organization project according to the  present legislation and measures established in the documentation of evaluating the impact on the environment throughout the construction period. The construction site organization value will be expressed in an estimate.

- The afferent expenses for the assurance throughout the execution period will include all the risks that might appear concerning the executed works, tillages, working installations, equipments, materials on stock, own personnel and entitled representatives to verify, to test or to receptionate works, as well as damages and prejudices brought to third  phisic or legal parties.The assurance will be closed after  contract assingment by the winning tenderer.

The guarantee period for the executed works is  36 months from signing the reception at works ending minute, according art. 7 line (3) from Law 10/1995 regarding the quality in construction updated :

’’The guarantee period is foreseen in contracts signed between parties, according to the importance categories established according to the law and will last at least:

- 3 years for constructions classified into the C category of importance”

2.1.Requirements regarding the way of presenting the technical proposal

The Technical proposal will contain all the information and prooves the tenderer considers necessarry in order to motivate his tender. The tender must persuade the contracting authority in case of assingment, the tenderer has enough resources and necessarry experience to  realize the contract afferent the present public aquisition.

In order to evaluate the respecting of requested demands for the design services the list

of main design services realized in the last 3 years will be presented, indicating the values, data and public or private beneficiaries, resulting that similar services have been realized (services for designing hydro-technical works and mechanism) with those who make the object of the present tender book, at the level of at least 1 contract, in the last 3 years, their  value/cumulate value has been the minimum estimated value of the services component afferent to present contract, attached will be certificate/documents issued or signed by the authority or the client/beneficiary.

In order to evaluate the respecting of the requested demands for the works execution a  list of works executed over the last 5 years will be presented in order to result  that works have been executed at the level of least one contract – maximum 3 contracts (works in the field of hydro-technical constructions) similar as complexity and utility;their value/cumulate value has been the minimum estimated value of the works component afferent to present contract, respectivee the sum of 4,220,165.61 euro (excludingVAT) .The constructor has executed at least 3 works in the field of hydro-technical constructions

The constructor has executed at least one works in the field of hydro-technical constructions including hydro-mechanical equipments mounting, similar regarding  complexity and utility.

The Contracting Authority has the right to request the economic operator situated on the first place after applying the award criteria on accepted offers, to make proof of fullfilling the request of similar experience by presenting reception minutes issued according to the legal documents that regulate the works reception :

-final reception minute/reception minute at works finalizing, minute on object to attest the works have been executed according to legal norms in the field and they have been finalized and/or other documents to reveal : the beneficiary, the quantity (technical indicators for the works object), period (including contract signing date) and the works execution location.

The economic operator has to make proof he has executed at least one work in the field of hydro-technical constructions with assembling of hydro-mechanical equipments, similar as complexity and utility.

The Contracting Authority has the right to request the economic operator on the first place after applying the award criteria on accepted offers, to make proof of fullfilling the request of similar experience by pressenting reception minutes, issued according to the legal documents that regulate the works reception, respectively :

-the final reception minute/the reception minute at works finalizing, minute on object to attest the fact works have been executed according to the legal norms in the field and that they have been finalized and/or other documentd to reveal the beneficiary, the quantity (technical indicators specific  to the works object), period (including contract signing date) and place of works execution.

The period of the last 3 years for experience regarding the design services will be reported to the deadline for offers submitting !

The period of the last 5 years for experience regarding works execution will be reported to deadline for offer submitting.

The technical proposal will beissued so that during the evaluation process the included information to allow the easy identification of correspondence with technical specification.

The data provided in third chapter represent ferm engagements in case the offer is declared succesfull, after contract signing, disobeying these engagementd throughout the contract progress, leads to applying clauses reffering to cancellation and/or penalties.

The economic operators will indicate in the offer that at issuing it they respected the relevant obligations in the environment field, social field, work relations that must be respected throughout the public aquisition contract, according to following legal regulations :

- Law 265/2006 refferring to the approval of OUG 195/2005 regarding the environment protection ;

- HG 1017/2015 regarding the establishing the gross minimum   guaranteed  in payment salary for a foreseen complete working programme

- Law 319/2006 regarding the labour protection and  security

Technical proposal will contain :

-     List of works quantities on works categories

-     List containing total consumes of material resources

-     List containing total consumes with labour

-     List containing total consumes of functioning hours for construction tillages

-     List containing total costs regarding transports

-      List containing quantities of tillages and technological equipments, including endowments

-     Technical sheets (will be completed for each tillage, equipments etc)

-      Information on impact of realization the execution of the investment objective on people’s health and environment.

-  Programme on quality proposed to realize the execution of the investment objective

-   Other information considered significant for the proper evaluation of the technical proposal

- Description of the works that will be executed will include  description of the used technology within the working process and the list with the equipments  used  to realize it will be presented

-   The graphic for the works progress on  detail execution stages (Gantt graphic, critical way others) correlated with the cash flow for the project Graficul de derulare a lucrarii pe faze de executie de detaliu

-The tenderer will present reasonably and realistically the description of the  work applied quality system , lists of quality system afferent procedures and a programme of realizing of the contract in terms of understanding the sequence of main types of works according to technical specifications, their schedule, coordination and alloted personnel as well as lists containing technical  execution procedures  of    all the work categories   for the contract realizing, quality control plan,verifyings and testings.

-  Works effective execution plan,  working methods, the stages throughout the entire execution period.  (work categories, including graphs).

-  Tender  needed time period for works execution realization for the  above mentioned investment objective.

-Main types of works according to technical specifications, their programming, coordination and alloted personnel as well as lists containing technical procedures, coordination and alloted personnel as well as lists containing execution technical specificatios for contrac t realization,  quality control plan, verifyings and testings.  The tenderer will present  the  procedure of assuring the necessarry laboratories to be used within  the contract list of specialized laboratories for sampling, determinations and testings of proper degree for the works execution or will present and engagement which reveals the fact the tenderer will assure the necessarry laboratories for the contract fulfilling.

Any other information considered to be significant for the proper evaluation of the technical proposal will be provided.

In case the technical proposal does not contain all the elements above mentioned, the technical documentation will be considered not compliant.

Works organizing

Adapting to physical constraints imposed by the  location (constraints due to terrain conditions). The tenderer will demonstrate  his tender is suitable to the phisycal imposed constraints, by elaborating a poster that will represent following : the limits of ocupying the road sectors (if it is the case), regarding the area constraints : the construction limits’ the construction limits, depositation areas, building site access, temporary works (mounting and removal – the land will be brought to its initial quotes and utilities).The poster will include  eloquent dimensions and logos.

Accomodation, meals, transport, rents and other  such are the tenderers concern and will be included into the tender price.

THE CONTRACTING AUTHORITY REQUIREMENTS REGARDING THE TECHNICAL OFFER ISSUING

In order to demonstrate the professional capacity it is necessarry to present following:

FOR DESIGN SERVICES

Key personnel necessarry for design:

- 1 project coordinator – to fulfiling the task of technical assistance

General requirements:

- Higher education graduated with a technical university degree in the field of construction

Specific requirements:

- Beig part of a design team /Participation at an least one project/contract at a similar activity  level, in the field of hydrotechnical construction

- -1 design engineer

General requirements:

-Higher education graduated with a university degree in the field of hydrotechnical constructions or similar

- At least 5 years  general professional experience

Specifict requirements:

-Beig part of a design team /Participation at an least one project as design engineer in the field of hydrotechnical constructions in the last 3 years.

FOR WORKS EXECUTION

Key personnel for execution:

- Responsable with technical execution

General requirements:

- Attested MLPAT or equivalent according to Order 777/2003 for domain V – Hydrotechnical Constructions and Arrangements valid at deadline established for offers submitting.

Specific requirements:

- Being part of a similar project in the last 5 (five) years

- 1 Building site chief

General requirements:

- Higher education graduated with a university degree in the field of hydrotechnical constructions or similar

- At least 5 years  general professional experience

Specific requirements:

- Being part of a similar project in the last 5 (five) years

- 1 responsible with labour security and health

General requirements:

- higher education – technical university degree

- having in the field of SSM, respecting HG 1425/2006, a certificate or a diploma

Specific requirements:

- Being part of a similar project in the last 5 (five) years

For the key personnel it is compulsory to present:

- CV-s and availability declarations for persons responsible for contract fulfilling

- Copies of graduation documents and/or training in the field/certificates/authorizations obtained, mentioned in the CV

- Requested experience support documents: copy from the job description, recommendation, copy from the work contract, copy from the  cooperation/services contract, copy of the REVISAL.

- For key experts which are not employed by the tenderer the cooperation contract will be presented, mentioning  on it -  ” according to the original” thoughout the entire project period.

- In case of submitting a common offer, the minimum requirements will be demonstrated by considering the resources of all associates.

Part of the investment objective is foreseen the arrangement of the Maneuver House .It is listed on the  2010 Historical Monuments List , under the name „Casa baraj” (stavilar) Historical Monument code TM- II -m -06283.

Interventions on historical monuments, as they are defined in Law 422/2001, regarding the protection of historical monuments, republished, with additional modifications, no matter of their legal status, will be carried out only with  attested specialists, experts and technical verifiers, signed up in special registers, according to legal foresees in force.

Under these conditions, within the technical offer, the tenderer will specify the modality of providing the specialist attested by the Ministry of Culture in the domains –I, architectural restaurations, 4 -  consolidation and restauration historical structures.

Cost for backstopping and support staff, as needed are considered to be include in the financial offer of the tender.

Office accomodation and/or transportation from service provider office to Contracting Authority office, for each expert working on the contract, is to be provided by the Service Provider.

OTHER ASPECTS THAT WILL BE PRESENTED AS PART

OF THE TECHNICAL OFFER

Activities of the personnel appointed throughout the works execution

For the Project Coordinator:

- detailed description of responsibilities and obligations throughout  the works execution period

- number of working days  for each month throughout the contract execution period

- the frequency of presence at the building site

For responsible with technical execution

- detailed description of responsibilities and obligations throughout the contract execution period

- number of labour days foreseen in each month throughout the contract execution period

- frequency of presence on the building site

For the building site chief:

- number of working days  every month throughout the contract execution period

- professional  responsibilities and tasks  on professional line, on NPM and PSI line, on environment

- Endowments, tillages and equipments proposed to be used

Only the necessarry and proposed equipment for the contract progress will be presented and not the entire equipment owned by the tenderer

In case hired equipments and tillages are presented, besides their features, the hiring tenders of the owner/owners, documents attesting the property, as well as relevant documents to atest the availability of hiring throughout the works execution period.

- Approaching modality in  relation with subcontractors (if it is the case)

- Building site organization project

It is compulsory to contain:

-  detailed description of the organizing procedure

- detailed list of endowments from the building site organization with respecting legal foresees

-  drawing part with location of the building site organization

D. The necessarry time period for the tenderer to realize the afferent construction works for the investment objective above mentioned wil be 24 month, includind 2 month for the design.

E. QUALITY control plan – Description of technologies foreseen for works execution

- Quality control plan applicable exclusively for the investment objective subjected to the assignment procedure

- detailed  execution procedures  according to works categories contained in the tender dossier

- Economic operators will proof they have (property/leasing/hiring/commitments by making available) authorized laboratories of  proper degree to works (can be own laboratories or presenting a contract with other laboratories etc.)

- Information about the impact of  investment objective realizing  on people’s health and environment.

- Other information considered significant for the proper evaluation of technical proposal

- At technical offer issuing it will be considered:

  - Proposed approaching for the project implementation

The execution procedures applicable for the investment objective subjected to the assingment will be presented clearly and in detail

  - Human resources and materials and achievements corresponding to each activity

The identified resources and indicated achievements must be fully correlated/mainly with the complexity of each proposed activity.

  - Responsibilities of the team members in implementing the contract activities and each economic operator group member contribution, as well as distribution and interaction of tasks and responsibilities between them,

Are indicated responsibilities in contract execution and interaction between the team members, including those reffering to contract management, support activities and if it is the case, distribution and interaction of tasks ans responsibilities between the operators of the group.

  - Timing, succesion and length of proposed activities

The duration of activities will fully correspond to their complexity, and the succession between them, including the period in progress is established according to the relation logics between them.The duration foreseen for each  main  necessarry operation is connected with the activities foreseen to be realized in the respective months and resources identified for their progress.

  - Number of working days foreseen for each expert categories every month troughout the contract execution period.Number of working days distributed on expert categories (key experts/non- key experts and senior experts/junior experts) has to be connected to the activities foreseen to be realized in the respective months and indicated resources for their progress.

OTHER ASPECTS

-The tenderer must provide  the proper endowment of the responsible personnel with the designing and construction works transport ( for transport to the investment objective location during works execution period),  office and IT equipment for the office work,  work protection equipment, communication means ( phone, fax).

-For special situations, for which the contracting authority considers necessarry to be realized, such as execution measures, lab analyses, expertizes, additional to those carried out by entrepreneures (according to the tender do0sier and programes of quality assuring), these will be realized by the contractor (tenderer) by his own means (if he is able to), or by specialized companies, agreed by the contracting authority.

VISIT  AT THE INVESTMENT OBJECTIVE SITE FOR WHICH THE CONSTRUCTION WORKS EXECUTION IS REQUIRED

In order to issue a detailed and compliant tender, the Contracting Authority specify the site location visit is compulsatory for identifaing all the risk factors ( that are connected with the investment realization), for presenting Technical Proposals and Financial proposals according to the Technical Specifications and compulsory contract clauses.

Applicable legislation

Law no.554/2004 of the contentious administrative

Law no 215/2001 Law for local public administration published in the Official Paper no 204/2001, modified

Law no. 500/2002 refferring to public finances, published in the Official Paper no 597/2002, with subsequent modifications and completions

Law no 273/2006 regarding local public finances

Law no 10/1995 regarding the quality in constructions

HG 766/1997 regarding the obligativity of using agreeded materials at works execution

HG no 907/2016 regarding the stages of elaborating and the frame contents for technical-economic documentations afferent to investment projects financed from public funds

HG no 1072/2003 regarding  the notification by ISC of technical-economic documentations for the investment objectives financed from public funds

Law no 161/2003 regarding some measures to assure transparency in performing publicdignities, public  functions and business environment, preventing and santioning coruption with subsequent additions and completions

HG no 925/1995 for approval of the regulations for verifying and  quality technical expertize for projects, for works and constructions execution.

Law  265/2006 regarding the approval of OUG 195/2005/ for  the environment protection

Law 50/1991 regarding the autorisation of works execution and some measures for houses constructions with subsequest aditions and completions.

Law no 319/2006 regarding  protection and security at work

HG 51/1996 regarding the approval of the Regulation for reception of assembling works, tillages, equipments, technological instalations and  commissioning of production capacities

Order of the Ministry for Internal Affairs and Administrative Reform no 597/2008 regarding the establishing the frame content, issuing and approval of technical-economic documentations afferent to the new investment objectives and/or intervention works at existing constructions, included into the Ministru for Internal Affairs and Administrative Reform Programmes.

HG 273/1994 regarding the approval of the Reception Regulation for the construction works and their afferent installations

National Standards and technical regulations in the field.