ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania

## Contracting Authority

Intercultural Institute Timișoara

## Country background

The Interreg - IPA CBC Romania – Serbia Programme is a continuation of previous CBC programmes, under the framework of the new Instrument for Pre-accession Assistance (IPA II). The Programme is the result of a co-operative effort by the Romanian and Serbian national, regional and local authorities.

## Current situation in the sector

Intercultural Institute Timisoara as Lead beneficiary is implementing project InclusiveArt – Access to Culture for Disadvantaged Children and Youth together with Nevo Parudimos, City of Zrenjanin and Center for Fine and Applied Arts Terra, Kikinda.

Among other activities, InclusiveArt project implies organisation of training activities by the project partners, with the aim of raising capacities of project communities for inclusive practices through culture.

For the successful implementation of the Inclusive Art project and of this contract it is compulsory for some days of the training to be held in parallel with another training organised by Nevo Parudimos.

## Related programmes and other donor activities

Not Applicable

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To increase the potential of the local communities and disadvantaged groups for innovative inclusive social practices by using art and culture to create inclusive contexts for integration and creative growth.

## Purpose

The purposes of this contract are as follows:

- to develop a favourable frame for learning by ensuring adequate location, spaces, materials and equipment, meals, accommodation and covering transportation of all participants, trainers and international expert.

## Results to be achieved by the Contractor

- Provide adequate and needed services necessary for the organisation of a nine (9) days Training in socio-educational animation for min. 24 young people.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The Contractor will receive the relevant information – content and visibility – from the Contracting Authority and the staff involvement will be ensured.

## Risks

Risk: Due to various reasons, the contract cannot be signed / the implementation cannot start at the indicated time.

Measure: to postpone the activities with maximum one month from the required dates.

# SCOPE OF THE WORK

## General

### Description

Provide adequate and needed services necessary for the organisation of a nine (9) days Training in socio-educational animation for min. 24 young people; between 16 and 24 April 2018

### Geographical area to be covered

The trainings should take place in the area of the Interreg - IPA CBC Romania – Serbia Programme. In order to ensure good learning conditions for a consecutive 9 days period, in order to coordinate with the partners and in order to share an extreme example of bad practice in cultural heritage management, Baile Herculane is the excelent location.

### Target groups

24 young creative young people selected by the Contracting Authority and partners at the end of creative entrepreneurship course.

## Specific work

The aim of the course is to ensure theoretical and practical learning issues concerning social educational animation for disadvantaged children from marginal communities.

For a period of 9 days, 24 young creative young people will to be involved in the training activity, consisting of two modules. The training should take place between 16 and 24 April 2018

The first module of 6 days will be theory dedicated to the familiarization with the methods and techniques of social educational animation, project management, volunteering etc. After the analysis of training needs, theoretical modules may have different teaching duration or will be replaced / supplemented with others.

The second module of training will be a 3 days of artistic residency on the subjects of inclusive community development with arts and culture. In this framework participants will prepare the final projects for cultural interventions in 12 communities and define the necessary resources with the support of local stakeholders and project team. A Regalement of intervention will be prepared in advance and in the last day of residency Project Steering Committee will select each participant/artist and each communities.

The training will be delivered by trainers from IIT and Nevo Parudimos partner, together with one of the experts who delivered TOT (from Activity 1.2), in order to present international good practices example. This training will contain an accredited Course that will be delivered and that offers the chance of a specialization / qualification to young graduates.

The Contractor will:

- provide a location to ensure proper organisation of an event with the duration of 9 days for minimum 24, maximum 27 persons (24 young creators and 3 trainers-project team members per day).  For the last night will also provide 4 accommodations for Project Steering Committee members.

- provide good level of accommodation (clean single rooms with bathrooms) with breakfast, 8 nights for 27 persons, one international expert for 2 nights, and 4 member of Project Steering Committee for last night.

- provide regular and vegetarian meals during the activity. The Contracting Authority will provide in advance the number of portions related to each category. For the lunch Contractor will served three dishes. For dessert, the cakes will be alternate with fresh fruit. The Contractor will offer in advance a Menu proposal that will be agreed with Contracting Authority.

- provide two coffee breaks and tea each day (tea, coffee, milk, mineral water, still water and natural juice, sweet and salty cookies (maximum 27 persons)

- ensure local and international transportation costs to the meeting place for the participants (from Timis and Caras Severin County from Romania and from Kikinda and Zrenjanin from Serbia), trainers from Timisoara and Resita and international expert from Budapest.

- organisation of a proper meeting place for minimum 27 persons during a period of 9 days; venue and facilities, including tables, chairs, air-condition system, a projector screen, laptop, flip chart.

- organisation of a proper meeting place for minimum 50 persons during a period of 2 days; venue and facilities, including tables, chairs, air-condition system, a projector screen, laptop, flip chart. During these two training days a joint training session is to be organised with participants from other training organised by Nevo Parudimos.

- ensure good wireless internet connection at the location and facilities to print plain A4 documents (max 100 pages during the whole activity)

- provide means to cover the transport cost and fees for one international expert with experience in the fields of socio-educational animation in the limit of 600 euro. The expert is invited and arranged by IIT (fee of 500 euro, total per day x 1 work day, on a contract basis)

The activity programme will be prepared by the Contracting Authority in consultation with the Contractor and the relationship with the participants will be managed by project team of the Contracting Authority.

## Project management

### Responsible body

The team of “InclusiveArt – Access to Culture for Disadvantaged Children and Youth” project from the Intercultural Institute of Timisoara is responsible for managing the contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Calin Rus -Training Manager. Corina Raceanu, the Project Director, and Marcel Bajka, the Project Coordinator, will assist it step by step.

### Facilities to be provided by the Contracting Authority and/or other parties

The Contracting Authority will provide its staff (team) that will hold a part of the trainings, lectures and presentations. The Contracting Authority will be represented by the Training Director together with the Project Director and the Project Coordinator of the Inclusive Art project.

# LOGISTICS AND TIMING

## Location

The Contracting Authority is located in Timisoara.

The location of the training venue will be in Herculane, Caras Severin County, Romania.

## Start date & Period of implementation of tasks

The intended start date is the date of contract signature and the period of implementation of the contract will be 3 (three) months from this date. According to Articles 19.1 and 19.2 of the Special Conditions, the actual start date and period of implementation will be defined by the Contracting Authority at the signing of the contract. The course will take place between 16 and 24 April 2018.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

Qualified and experiences staff capable to deliver meeting and conference services are needed.

### Key experts

Key expert: Team leader

Qualifications and skills

- Adequate qualifications in hotel services;

General professional experience

- Professional experience in hotel services

Specific professional experience

- Experience in conferences and meeting services.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language in one original and one copy:

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 4 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on services provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality and quantity manor, as required in these Terms of Reference.

## Special requirements

Not applicable