## Liste de cantitati BOQ
|  | Construction of Touristic Center for Cultural and Sport Activities in Lupsa de Jos Village, Brosteni Commune, Mehedinti County | [6 empty] | Date / Data
|  | Construire Centru turistic pentru activitati culturale si sportive in satul Lupsa de Jos, Comuna Brosteni, Judetul Mehedinti | [6 empty] | December / Decembrie
|  | Bills of Quantities | Liste de cantitati | [5 empty] | 2017
|  | Technical Design | Proiect tehnic |  |  | exchange rate | RON | Bank | Date
|  | Cells marked with this color, to be completed by Contractor | Se vor completa celulele marcate cu aceasta culoare de catre Constructor |  |  | curs schimb |  | Banca | Data
[6 empty] | 1 EUR = | 4.644 | INFOREURO | 29.12.2017
|  | COSTS FOR THE MAIN INVESTMENT | CHELTUIELI PENTRU INVESTITIA DE BAZA |  |  | Estimated / Estimare
code cod |  | Type of works [ENG] | Tipul lucrarii [RO] | Unit Unitate | Quantity Cantitate | Unit Price [EUR] Pret unitar | Unit Price [RON] Pret unitar | Amount [EUR] Cost | Amount [RON] Cost
|  | Design Item: DO 04 | Obiect deviz: DO 04
|  | CONSTRUCTIONS AND INSTALLATIONS (Main Building, storage) | CONSTRUCTII SI INSTALATII (cladire principala, magazie) | total |  |  |  | 0 | 0
|  | ARCHITECTURE | ARHITECTURA |  |  |  | TOTAL | 0 | 0
|  | Main Building | Cladirea principala |  |  |  |  | 0 | 0
ARCmb | 1 | Efficient masonry in ceramic blocks 30cm | Zidarie eficienta din blocuri ceramice 30cm | m3 | 224.1 | 0 |  | 0 | 0
ARCmb | 2 | Efficient masonry in ceramic blocks 20cm | Zidarie eficienta din blocuri ceramice 20cm | m3 | 12.2 | 0 |  | 0 | 0
ARCmb | 3 | Efficient masonry in ceramic blocks 15cm | Zidarie eficienta din blocuri ceramice 15cm | m3 | 69.1 | 0 |  | 0 | 0
ARCmb | 4 | Interior wall plasters, all operations | Tencuieli interioare la pereti, inclusiv strat final glet | sqm/mp | 1271.5 | 0 |  | 0 | 0
ARCmb | 5 | Interior ceilings plastering, all operations | Tencuieli interioare la tavane, inclusiv strat final glet | sqm/mp | 306 | 0 |  | 0 | 0
ARCmb | 6 | Closure of gypsum board RF 30min | Inchideri gips carton RF 30min | sqm/mp | 274 | 0 |  | 0 | 0
ARCmb | 7 | Double plasterboard wall (10cm) with mineral wool interior | Perete dublu din rigips (10cm) cu interior din vata minerala | sqm/mp | 67.5 | 0 |  | 0 | 0
ARCmb | 8 | Closure of drywall at the stairwells ceiling | Inchideri gipscarton tavan la casa scarii | sqm/mp | 17.55 | 0 |  | 0 | 0
ARCmb | 10 | Washable paint on walls and ceilings | Zugraveli lavabile la pereti si tavane | sqm/mp | 1837 | 0 |  | 0 | 0
ARCmb | 11 | Embrasure od doors and windows | Realizare spaleti | m | 256.5 | 0 |  | 0 | 0
ARCmb | 12 | Expansion pads from pre-painted sheet, 18cm width | Glafuri exterioare din tabla prevopsita/aluminiu, 18cm latime | m | 33.8 | 0 |  | 0 | 0
ARCmb | 13 | PVC interior window sills, 25cm width | Glafuri interioare din PVC, 25 cm latime | m | 33.8 | 0 |  | 0 | 0
ARCmb | 14 | traffic tiles | Gresie trafic | sqm/mp | 234 | 0 |  | 0 | 0
ARCmb | 15 | Tiles - walls | Faianta | sqm/mp | 164 | 0 |  | 0 | 0
ARCmb | 16 | Tile flooring h = 10cm | Plinta gresie h=10cm | m | 239.8 | 0 |  | 0 | 0
ARCmb | 17 | High traffic laminate flooring | Parchet laminat trafic intens | sqm/mp | 314 | 0 |  | 0 | 0
ARCmb | 18 | Parquet mdf flooring | Plinta mdf pentru parchet | m | 137 | 0 |  | 0 | 0
ARCmb | 19 | Molding equalization 4cm | Turnare sape egalizare 4cm | sqm/mp | 547 | 0 |  | 0 | 0
ARCmb | 20 | Extruded polystyrene 5cm under the screed | Polistiren extrudat 5cm sub sapa | sqm/mp | 547 | 0 |  | 0 | 0
ARCmb | 21 | Casting self-leveling screeds | Turnare sape autonivelante | sqm/mp | 547 | 0 |  | 0 | 0
ARCmb | 22 | Metal exterior doors 1,89mp | Usi metalice de exterior S=1,89mp | pc/buc | 2 | 0 |  | 0 | 0
ARCmb | 23 | Aluminum exterior doors with thermal barrier and insulationg glass | Usi exterioare din aluminiu cu bariera termica si geam termopan | sqm/mp | 16.8 | 0 |  | 0 | 0
ARCmb | 24 | PVC interior doors with decorative foil wood model 30cm | Usi interioare din PVC cu folie decorativa model lemn toc de 30cm | sqm/mp | 18.9 | 0 |  | 0 | 0
ARCmb | 25 | PVC door 15cm | Usa PVC toc de 15cm | sqm/mp | 1.89 | 0 |  | 0 | 0
ARCmb | 26 | Internal fire resistant door 30 minutes S = 1,89mp | Usa interioara rezistenta la foc 30 minute S=1,89mp | pc/buc | 1 | 0 |  | 0 | 0
ARCmb | 27 | Internal fire resistant door 30 minutes S= 1.68mp | Usa interioara rezistenta la foc 30 minute S= 1,68mp | pc/buc | 1 | 0 |  | 0 | 0
ARCmb | 28 | Sanitary partition panels, phenolic resins, with accessories (upright legs, connecting pieces, hinges, locks) | Panouri compartimentare grupuri sanitare, din rasini fenolice, cu accesorii (picioare inaltatoare, piese legatura, balamale, incuietori) | sqm/mp | 27.7 | 0 |  | 0 | 0
ARCmb | 29 | PVC windows with wooden decorative sheet | Ferestre PVC cu folie decorativa model lemn | sqm/mp | 50.2 | 0 |  | 0 | 0
ARCmb | 30 | Laying 2cm travertine at the poles | Placare cu travertin 2cm la stalpi | sqm/mp | 31 | 0 |  | 0 | 0
ARCmb | 31 | Thermo isolation on the terrace 20cm mineral wool | Termoizolatie la terasa vata minerala 20cm | sqm/mp | 168 | 0 |  | 0 | 0
ARCmb | 32 | Terraced waterproofing - PVC membrane with polyester reinforcement, mechanical fastening and longitudinal welding of hot air strips | Hidroizolatie la terasa – membrana PVC cu armatura poliesterica, fixare mecanica si sudare longitudinala a fasiilor cu aer cald | sqm/mp | 240 | 0 |  | 0 | 0
| 33 | Mounting pre-painted jambs on the terrace attic, width=56cm | Montare sorturi tabla prevopsita la atic terasa, latime l=56cm | m | 58 | 0 |  | 0 | 0
| 34 | Mounting pre-painted jambs on top of walls, width=55cm | Montare sorturi tabla prevopsita pe timpane, latime l=55 | m | 49 | 0 |  | 0 | 0
ARCmb | 35 | Thermosystem façade of 10cm basalt cotton and decorative plaster granulation 2-3mm | Termosistem fatade vata bazaltica 10cm si tencuiala decorativa granulatie 2-3mm | sqm/mp | 462.5 | 0 |  | 0 | 0
ARCmb | 36 | Thermosystem of expanded polystyrene of 10cm at attic | Termosistem la atic polistiren expandat 10cm | sqm/mp | 61.5 | 0 |  | 0 | 0
ARCmb | 37 | thermosystem 5cm thick polystyrene + base plaster | termosistem 5cm grosime polistiren + tencuiala soclu | sqm/mp | 51.5 | 0 |  | 0 | 0
ARCmb | 38 | plaster on the outer stairs | tencuiala soclu la scarile exterioare | sqm/mp | 14.5 | 0 |  | 0 | 0
ARCmb | 39 | realization of resin wood treated with antifungal and fire retardant framing | realizare sarpanta din lemn rasinoase tratat antifungic si ignifug | sqm/mp | 458 | 0 |  | 0 | 0
ARCmb | 40 | Realization of framing thermoinsulation in mineral wadding mattresses, 20cm thick, vapour barrier | Realizare termoizolatie la sarpanta cu vata minerala saltele, 20cm grosime, bariera de vapori | sqm/mp | 495 | 0 |  | 0 | 0
ARCmb | 41 | Larch ladder | Astereala scandura | sqm/mp | 495 | 0 |  | 0 | 0
ARCmb | 42 | Locks from 18mm OSB to the roof | Inchideri din OSB 18mm la intrados acoperis | sqm/mp | 495 | 0 |  | 0 | 0
ARCmb | 43 | Ceramic tile covers, full system | Invelitoare tigla ceramica, incl. parazapezi, accesorii aerisire | sqm/mp | 495 | 0 |  | 0 | 0
ARCmb | 44 | Attic windows 80x120cm (0.96mp) | Ferestre de mansarda 80x120cm (0,96mp) | pc/buc | 6 | 0 |  | 0 | 0
ARCmb | 45 | 2cm granite plywood on extruded stairs and ramp | Placaj granit fiamat 2cm la scari ext si rampa | sqm/mp | 130 | 0 |  | 0 | 0
ARCmb | 46 | Pre-painted sheet gutters | Jgheaburi din tabla prevopsita | m | 21 | 0 |  | 0 | 0
ARCmb | 47 | Extruded 100mm bumper | Burlane 100mm din tabla prevopsita | m | 21.4 | 0 |  | 0 | 0
ARCmb | 48 | Metallic balustrades with alkyd dyes, h=90cm | Balustrade metalice h=90cm cu vopsitorii alchidice | m | 19.5 | 0 |  | 0 | 0
ARCmb | 49 | Polystyrene caps with resin finish, int. 40cm | Capiteluri polistiren cu finisaj rasini, diametru int. 40cm | pc/buc | 5 | 0 |  | 0 | 0
ARCmb | 50 | Transport of materials 50km | Transport materiale 50km | to | 634 | 0 |  | 0 | 0
|  | Storehouse | Magazie |  |  |  |  | 0 | 0
ARCmg | 1 | Whitewood poles 15x15cm | Stalpi lemn rasinoase 15x15cm | m3 | 1.6 | 0 |  | 0 | 0
ARCmg | 2 | Fixing poles in foundations with metal parts | Fixare stalpi in fundatii cu piese metalice | pc/buc | 22 | 0 |  | 0 | 0
ARCmg | 3 | Realization of planed wood beams with softwood beams | Realizare planseu cu grinzi lemn rasinoase ecarisat | m3 | 0.81 | 0 |  | 0 | 0
ARCmg | 4 | Whitewood framing | Sarpanta din lemn rasinoase | sqm/mp | 52 | 0 |  | 0 | 0
ARCmg | 5 | OSB II plating, 15mm thick on the walls | placare OSB II, grosime 15mm la pereti | sqm/mp | 96.8 | 0 |  | 0 | 0
ARCmg | 6 | Ceramic tile cover | Invelitoare tigla ceramica | sqm/mp | 50 | 0 |  | 0 | 0
ARCmg | 7 | Drains | Jgheaburi | m | 12 | 0 |  | 0 | 0
ARCmg | 8 | downspouts | Burlane | m | 7 | 0 |  | 0 | 0
ARCmg | 9 | Wood door | Usa lemn | sqm/mp | 5.85 | 0 |  | 0 | 0
ARCmg | 10 | Wooden windows | Ferestre lemn | sqm/mp | 1.1 | 0 |  | 0 | 0
|  | STRUCTURE | STRUCTURA |  |  |  | TOTAL | 0 | 0
|  | Main Building | Cladirea principala |  |  |  |  | 0 | 0
STRmb | 1 | earth digging in limited spaces | sapatura de pamant in spatii limitate | m3 | 185 | 0 |  | 0 | 0
STRmb | 2 | reinforced concrete in foundations c12 / 15 (b200) | beton armat in fundatii c12/15 (b200) | m3 | 170 | 0 |  | 0 | 0
STRmb | 3 | reinforced concrete in elevators and c16 / 20 (b250) | beton armat in elevatii si cuzineti c16/20 (b250) | m3 | 60 | 0 |  | 0 | 0
STRmb | 4 | concrete floors c8 / 10 (b150) | pardoseli din beton c8/10(b150) | sqm/mp | 735 | 0 |  | 0 | 0
STRmb | 5 | shuttering panels made of reusable panels at elevators | cofraje din panouri refolosibile la elevatii | sqm/mp | 367 | 0 |  | 0 | 0
STRmb | 6 | reinforcement ob37 d <= 8, in foundations | armatura ob37 d<= 8, in fundatii | kg | 2400 | 0 |  | 0 | 0
STRmb | 7 | reinforcement ob37 d> 8 in foundations | armatura ob37 d> 8, in fundatii | kg | 450 | 0 |  | 0 | 0
STRmb | 8 | reinforcement pc52, d> 8, in foundations | armatura pc52, d> 8, in fundatii | kg | 4500 | 0 |  | 0 | 0
STRmb | 9 | spreading the earth with the shovel | imprastierea pamantului cu lopata | mc | 190 | 0 |  | 0 | 0
STRmb | 10 | compaction with vibrating plate | compactarea cu placa vibranta | m3x100 | 1.9 | 0 |  | 0 | 0
STRmb | 11 | watering with tanks | udarea cu autocisterna | m3 | 10 | 0 |  | 0 | 0
STRmb | 12 | transporting land with a mast to 30m | transport pamant cu roaba la 30m | to | 330 | 0 |  | 0 | 0
STRmb | 13 | ballast stuffing | umplutura de balast | m3 | 90 | 0 |  | 0 | 0
STRmb | 14 | road transport of the ballast with dumper at 5 km | transport rutier al balastului cu autobasculanta la 5 km | to | 162 | 0 |  | 0 | 0
STRmb | 15 | road transport of concrete at 15km | transportul rutier al betonului la 15km | to | 759 | 0 |  | 0 | 0
STRmb | 16 | installation of welded netting in floors | montare plase sudate in pardoseli | kg | 4100 | 0 |  | 0 | 0
STRmb | 17 | road transport of dump materials at 15 km | transport rutier al materialelor cu autobasculanta la 15 km | to | 10 | 0 |  | 0 | 0
STRmb | 18 | concrete b250 (c16 / 20) in boards, beams and poles | beton b250(c16/20) in placi, grinzi si stalpi | m3 | 138 | 0 |  | 0 | 0
STRmb | 19 | shuttering panels made of reusable panels, exclusively supporting plates and beams | cofraje din panouri refolosibile, exclusiv sustineri la placi si grinzi | sqm/mp | 650 | 0 |  | 0 | 0
STRmb | 20 | moldings made of reusable panels at the poles | cofraje din panouri refolosibile la stalpi | sqm/mp | 365 | 0 |  | 0 | 0
STRmb | 21 | system of expandable metal beams | sistem din grinzi metalice extensibile | sqm/mp | 390 | 0 |  | 0 | 0
STRmb | 22 | extended extension props | sustineri din popi extensibili | pc/buc | 400 | 0 |  | 0 | 0
STRmb | 23 | reinforcement from ob37 d <= 8mm in poles and beams | armatura din ob37 d<=8mm in stalpi si grinzi | kg | 4000 | 0 |  | 0 | 0
STRmb | 24 | reinforcement from pc52 d> 8mm in poles, beams | armatura din pc52 d>8mm in stalpi, grinzi | kg | 8000 | 0 |  | 0 | 0
STRmb | 25 | reinforcement of ob37 d <8mm in plates | armatura din ob37 d<8mm in placi | kg | 170 | 0 |  | 0 | 0
STRmb | 26 | reinforcement from pc52 d> 8mm in plates | armatura din pc52 d>8mm in placi | kg | 6920 | 0 |  | 0 | 0
STRmb | 27 | road transport of concrete at 15km | transport rutier al betonului la 15km | to | 345 | 0 |  | 0 | 0
STRmb | 28 | road transport of materials to 15km | transport rutier al materialelor la 15km | to | 80 | 0 |  | 0 | 0
STRmb | 29 | Metal fabrications | confectii metalice | to | 5 | 0 |  | 0 | 0
STRmb | 30 | painting metallic fabrics with a minium lead coat | vopsitoria confectiilor metalice cu un strat minium de plumb | to | 5 | 0 |  | 0 | 0
STRmb | 31 | painting metallic fabrics with fireproofing paint | protectia confectiilor metalice cu vopsitorie termospumanta | to | 5 | 0 |  | 0 | 0
|  | Storehouse | Magazie |  |  |  |  | 0 | 0
STRmg | 1 | earth digging in limited spaces | sapatura de pamant in spatii limitate | m3 | 13.5 | 0 |  | 0 | 0
STRmg | 2 | reinforced concrete in foundations c12 / 15 (b200) | beton armat in fundatii c12/15 (b200) | m3 | 10 | 0 |  | 0 | 0
STRmg | 3 | reinforced concrete in elevations c16 / 20 (b250) | beton armat in elevatii c16/20 (b250) | m3 | 2.5 | 0 |  | 0 | 0
STRmg | 4 | reinforcement ob37 d <= 8, in foundations | armatura ob37 d<= 8, in fundatii | kg | 95 | 0 |  | 0 | 0
STRmg | 5 | reinforcement ob37 d> 8 in foundations | armatura ob37 d> 8, in fundatii | kg | 230 | 0 |  | 0 | 0
STRmg | 6 | underfloor ballast stuffing | umplutura de balast sub pardoseli | m3 | 2.9 | 0 |  | 0 | 0
STRmg | 7 | road transport of land to 5km | transportul rutier al pamntului la 5km | to | 30 | 0 |  | 0 | 0
STRmg | 8 | uploading land in the car | incarc. pamantului in auto | to | 30 | 0 |  | 0 | 0
STRmg | 9 | transporting land with a mast to 30m | transport pamant cu roaba la 30m | to | 30 | 0 |  | 0 | 0
STRmg | 10 | concrete floor c8 / 10 | pardoseala din beton c8/10 | sqm/mp | 29 | 0 |  | 0 | 0
STRmg | 11 | shuttering panels in elevators | cofraje din panouri refolosibile in elevatii | sqm/mp | 19 | 0 |  | 0 | 0
STRmg | 12 | transport of concrete at 15km | transportul rutier al betonului la 15km | to | 35 | 0 |  | 0 | 0
STRmg | 13 | installation of welded netting in floors | montare plase sudate in pardoseli | kg | 150 | 0 |  | 0 | 0
STRmg | 14 | transport of dump materials at 15 km | transport rutier al materialelor cu autobasculanta la 15 km | to | 8 | 0 |  | 0 | 0
|  | INSTALLATIONS | INSTALATII |  |  |  | TOTAL | 0 | 0
|  | Sanitary interior installations | Instalatii sanitare interioare |  |  |  |  | 0 | 0
SANmb | 1 | earth digging in limited spaces | sapatura de pamant in spatii limitate | m3 | 2.88 | 0 |  | 0 | 0
SANmb | 2 | draintrap flooring Dn 100 | sifon pardoseala Dn 100 | buc | 1 | 0 |  | 0 | 0
SANmb | 3 | draintrap flooring Dn 50 | sifon pardoseala Dn 50 | buc | 5 | 0 |  | 0 | 0
SANmb | 4 | PVC pipe Dn 50 | teava PVC Dn 50 | ml | 62 | 0 |  | 0 | 0
SANmb | 5 | PVC pipe Dn 75 | teava PVC Dn 75 | ml | 2.5 | 0 |  | 0 | 0
SANmb | 6 | PVC pipe Dn 110 | teava PVC Dn 110 | ml | 48 | 0 |  | 0 | 0
SANmb | 7 | PVC branch 110x110 - 45 degrees | ramificatie PVC 110x110 - 45 grd | buc | 9 | 0 |  | 0 | 0
SANmb | 8 | PVC branch 110x50 - 45 degrees | ramificatie PVC 110x50 - 45 grd | buc | 6 | 0 |  | 0 | 0
SANmb | 9 | PVC branch 110x75 - 45 degrees | ramificatie PVC 110x75 - 45 grd | buc | 1 | 0 |  | 0 | 0
SANmb | 10 | PVC branch PVC 50x50 - 45 degrees | ramificatie PVC 50x50 - 45 grd | buc | 15 | 0 |  | 0 | 0
SANmb | 11 | PVC branch PVC 75x50 - 45 degrees | ramificatie PVC 75x50 - 45 grd | buc | 1 | 0 |  | 0 | 0
SANmb | 12 | reduction PVC 110-50 | reductie PVC 110-50 | buc | 2 | 0 |  | 0 | 0
SANmb | 13 | PVC bend 50 - 45 degrees | cot PVC 50 - 45 grd | buc | 52 | 0 |  | 0 | 0
SANmb | 14 | PVC bend 50 - 90 degrees | cot PVC 50 - 90 grd | buc | 44 | 0 |  | 0 | 0
SANmb | 15 | PVC bend 110 - 45 degrees | cot PVC 110 - 45 grd | buc | 39 | 0 |  | 0 | 0
SANmb | 16 | reduction PVC 75-50 | reductie PVC 75-50 | buc | 1 | 0 |  | 0 | 0
SANmb | 17 | sink 600 mm with pedestal | lavoar 600 mm cu piedestal | buc | 12 | 0 |  | 0 | 0
SANmb | 18 | urinal | pisoar | buc | 4 | 0 |  | 0 | 0
SANmb | 19 | toilt bowl | vas closet | buc | 10 | 0 |  | 0 | 0
SANmb | 20 | shower 90x90 | cadita dus 90x90 | buc | 6 | 0 |  | 0 | 0
SANmb | 21 | washing, including supporting furniture | spalator inclusiv mobilier sustinere | buc | 3 | 0 |  | 0 | 0
SANmb | 22 | T-square PPR 20-20-20 | teu PPR 20-20-20 | buc | 34 | 0 |  | 0 | 0
SANmb | 23 | T-square PPR 25-20-25 | teu PPR 25-20-25 | buc | 13 | 0 |  | 0 | 0
SANmb | 24 | T-square PPR 32-20-32 | teu PPR 32-20-32 | buc | 9 | 0 |  | 0 | 0
SANmb | 25 | T-square PPR 40-20-40 | teu PPR 40-20-40 | buc | 2 | 0 |  | 0 | 0
SANmb | 26 | T-square PPR 40-25-40 | teu PPR 40-25-40 | buc | 1 | 0 |  | 0 | 0
SANmb | 27 | T-square PPR 40-32-40 | teu PPR 40-32-40 | buc | 1 | 0 |  | 0 | 0
SANmb | 28 | PPR bend 20 - 90 degrees | cot PPR 20 - 90 grd | buc | 12 | 0 |  | 0 | 0
SANmb | 29 | PPR bend 25 - 90 degrees | cot PPR 25 - 90 grd | buc | 2 | 0 |  | 0 | 0
SANmb | 30 | PPR bend 40 - 90 degrees | cot PPR 40 - 90 grd | buc | 5 | 0 |  | 0 | 0
SANmb | 31 | reduction PPR 25-20 | reductie PPR 25-20 | buc | 4 | 0 |  | 0 | 0
SANmb | 32 | reduction PPR 32-25 | reductie PPR 32-25 | buc | 3 | 0 |  | 0 | 0
SANmb | 33 | reduction PPR 40-32 | reductie PPR 40-32 | buc | 2 | 0 |  | 0 | 0
SANmb | 34 | PPR bend 20x1/2 inner thread | cot PPR 20x1/2 FI | buc | 56 | 0 |  | 0 | 0
SANmb | 35 | PPR pipe Dn 20 | teava PPR Dn 20 | ml | 67 | 0 |  | 0 | 0
SANmb | 36 | aluminium pipe PPR Dn 20 | teava PPR AL Dn 20 | ml | 81 | 0 |  | 0 | 0
SANmb | 37 | PPR pipe Dn 25 | teava PPR Dn 25 | ml | 14 | 0 |  | 0 | 0
SANmb | 38 | aluminium pipe PPR Dn 25 | teava PPR AL Dn 25 | ml | 17 | 0 |  | 0 | 0
SANmb | 39 | PPR pipe Dn 32 | teava PPR Dn 32 | ml | 14 | 0 |  | 0 | 0
SANmb | 40 | aluminium pipe PPR Dn 32 | teava PPR AL Dn 32 | ml | 11 | 0 |  | 0 | 0
SANmb | 41 | PPR pipe Dn 40 | teava PPR Dn 40 | ml | 10 | 0 |  | 0 | 0
SANmb | 42 | aluminium pipe PPR Dn 40 | teava PPR AL Dn 40 | ml | 10 | 0 |  | 0 | 0
SANmb | 43 | adapter PE 40x11/4" external thread | adaptor PE 40x11/4" FE | buc | 1 | 0 |  | 0 | 0
SANmb | 44 | adapter PPR 20x1/2" inner thread | adaptor PPR 20x1/2" FI | buc | 2 | 0 |  | 0 | 0
SANmb | 45 | adapter PPR 20x1/2" external thread | adaptor PPR 20x1/2" FE | buc | 5 | 0 |  | 0 | 0
SANmb | 46 | adapter PPR 40x11/4" inner thread | adaptor PPR 40x11/4" FI | buc | 4 | 0 |  | 0 | 0
SANmb | 47 | adapter PPR 40x11/4" external thread | adaptor PPR 40x11/4" FE | buc | 3 | 0 |  | 0 | 0
SANmb | 48 | adapter alama 18x1/2 external thread | adaptor alama 18x1/2 FE | buc | 1 | 0 |  | 0 | 0
SANmb | 49 | brass adapter 22x3/4" external thread | adaptor alama 22x3/4" FE | buc | 1 | 0 |  | 0 | 0
SANmb | 50 | brass adapter 28x1" external thread | adaptor alama 28x1" FE | buc | 8 | 0 |  | 0 | 0
SANmb | 51 | copper bend PPR 20 - 90 degrees | cot PPR 20 - 90 grd | buc | 6 | 0 |  | 0 | 0
SANmb | 52 | PPR bend 40 - 90 degrees | cot PPR 40 - 90 grd | buc | 9 | 0 |  | 0 | 0
SANmb | 53 | copper bend 28 - 90 inner-inner | cot cupru 28 - 90 MM | buc | 2 | 0 |  | 0 | 0
SANmb | 54 | drain tap Dn 1/2" | robinet golire Dn 1/2" | buc | 2 | 0 |  | 0 | 0
SANmb | 55 | valve with metallic connection Dn 1/2" | robinet olandez Dn 1/2" | buc | 3 | 0 |  | 0 | 0
SANmb | 56 | valve with metallic connection Dn 1" | robinet olandez Dn 1" | buc | 2 | 0 |  | 0 | 0
SANmb | 57 | valve with metallic connection Dn 11/4" | robinet olandez Dn 11/4" | buc | 5 | 0 |  | 0 | 0
SANmb | 58 | PPR plug with metallic connection Dn 20x1/2" | mufa PPR cu olandez Dn 20x1/2" | buc | 2 | 0 |  | 0 | 0
SANmb | 59 | PPR plug with metallic connection Dn 40x11/4" | mufa PPR cu olandez Dn 40x11/4" | buc | 2 | 0 |  | 0 | 0
SANmb | 60 | sens valve Dn 1/2" | supapa sens Dn 1/2" | buc | 1 | 0 |  | 0 | 0
SANmb | 61 | sens valve Dn 11/4" | supapa sens Dn 11/4" | buc | 1 | 0 |  | 0 | 0
SANmb | 62 | couple pump domestic hot water recirculation pump | cuple pompa recirculare ACM | buc | 2 | 0 |  | 0 | 0
SANmb | 63 | T-square PPR 40-20-40 | teu PPR 40-20-40 | buc | 1 | 0 |  | 0 | 0
SANmb | 64 | T-square copper 28-18-28 | teu cupru 28-18-28 | buc | 1 | 0 |  | 0 | 0
SANmb | 65 | T-square cooper 28-22-28 | teu cupru 28-22-28 | buc | 1 | 0 |  | 0 | 0
SANmb | 66 | cold water dispenser | distribuitor apa rece | buc | 1 | 0 |  | 0 | 0
SANmb | 67 | cooper pipe 28x1 mm | teava cupru 28x1 mm | ml | 50 | 0 |  | 0 | 0
SANmb | 68 | material transport at 50 km | transport materiale la 50 km | to | 1.5 | 0 |  | 0 | 0
SANmb | 69 | downloading materials | descarcare materiale | to | 1.5 | 0 |  | 0 | 0
SANmb | 70 | pressure samples | probe de presiune | ml | 224 | 0 |  | 0 | 0
SANmb | 71 | cover toilet | capac closet | buc | 10 | 0 |  | 0 | 0
SANmb | 72 | shower cabin | cabina dus | buc | 6 | 0 |  | 0 | 0
SANmb | 73 | support for toilet paper | porthartie | buc | 12 | 0 |  | 0 | 0
SANmb | 74 | bath soap | portsapun | buc | 18 | 0 |  | 0 | 0
SANmb | 75 | mirror 600 x 600 | oglinda 600 x 600 | buc | 12 | 0 |  | 0 | 0
SANmb | 76 | channels for installations | slit zidarie | ml | 72 | 0 |  | 0 | 0
SANmb | 77 | urinal battery with sensor | baterie pisoar cu senzor | buc | 4 | 0 |  | 0 | 0
SANmb | 78 | tank closet | rezervor closet | buc | 10 | 0 |  | 0 | 0
SANmb | 79 | shower battery | baterie dus | buc | 6 | 0 |  | 0 | 0
SANmb | 80 | washbasin mixer | baterie lavoar | buc | 12 | 0 |  | 0 | 0
SANmb | 81 | kitchen plator battery | baterie spalator | buc | 3 | 0 |  | 0 | 0
SANmb | 82 | concrete breakage | spargere beton | mc | 0.5 | 0 |  | 0 | 0
SANmb | 83 | transport of materials by direct wearing on a distance of 10 m | transport materiale prin purtare directa pe distanta de 10 m | to | 1.5 | 0 |  | 0 | 0
SANmb | 84 | flexible drain bowl closet | racord flexibil scurgere vas closet | buc | 10 | 0 |  | 0 | 0
SANmb | 85 | water drain trap sink | sifon scurgere lavoar | buc | 12 | 0 |  | 0 | 0
SANmb | 86 | water drain trap washing | sifon scurgere spalator | buc | 3 | 0 |  | 0 | 0
SANmb | 87 | water drain trap shower | sifon scurgere cadita dus | buc | 6 | 0 |  | 0 | 0
SANmb | 88 | valve mounted under sink | robinet sublavoar | buc | 40 | 0 |  | 0 | 0
SANmb | 89 | insulated type Armaflex Dn 20 | izolatie tip Armaflex Dn 20 | ml | 148 | 0 |  | 0 | 0
SANmb | 90 | insulated type Armaflex Dn 25 | izolatie tip Armaflex Dn 25 | ml | 31 | 0 |  | 0 | 0
SANmb | 91 | insulated type Armaflex Dn 32 | izolatie tip Armaflex Dn 32 | ml | 25 | 0 |  | 0 | 0
SANmb | 92 | insulated type Armaflex Dn 40 | izolatie tip Armaflex Dn 40 | ml | 20 | 0 |  | 0 | 0
SANmb | 93 | device for supporting disabled people | dispozitiv sustinere persoane cu handicap | buc | 1 | 0 |  | 0 | 0
SANmb | 94 | transport wasteland at 10 km | transport pamant la 10 km | mc | 0.5 | 0 |  | 0 | 0
SANmb | 95 | plastering 5 cm | tencuiala 5 cm | mp | 21.6 | 0 |  | 0 | 0
SANmb | 96 | sealing test for sewer pipes | proba etanseitate la conducte canalizare | ml | 112.5 | 0 |  | 0 | 0
|  | Electrical interior installations | Instalatii electrice interioare |  |  |  |  | 0 | 0
ELmb | 1 | TECT electric panel fully equipped | tablou electric TECT complet echipat | buc | 1 | 0 |  | 0 | 0
ELmb | 2 | TES electric panel fully equipped | tablou electric TES complet echipat | buc | 1 | 0 |  | 0 | 0
ELmb | 3 | TEG electric panel fully equipped | tablou electric TEG complet echipat | buc | 1 | 0 |  | 0 | 0
ELmb | 4 | LED backlight 600 x 600 mm | corp iluminat tip LED 600 x 600 mm | buc | 10 | 0 |  | 0 | 0
ELmb | 5 | LED backlight 300 x 300 mm | corp iluminat tip LED 300 x 300 m | buc | 1 | 0 |  | 0 | 0
ELmb | 6 | pendant luminaire equipped with 3 x 20 W LED | corp iluminat tip pendul echipat cu sursa LED 3x20 W | buc | 90 | 0 |  | 0 | 0
ELmb | 7 | EXIT luminaire with 2 hours battery life | corp de iluminat EXIT cu acumulator cu autonomie 2 ore | buc | 9 | 0 |  | 0 | 0
ELmb | 8 | 100 x 100 mm ram branch | doza ramificatie 100 x 100 mm | buc | 71 | 0 |  | 0 | 0
ELmb | 9 | appliance dose | doza aparat | buc | 83 | 0 |  | 0 | 0
ELmb | 10 | 220 V buried plug with protection contact | priza ingropata 220 V cu contact de protectie | buc | 62 | 0 |  | 0 | 0
ELmb | 11 | simple buried switch | intrerupator simplu ingropat | buc | 21 | 0 |  | 0 | 0
ELmb | 12 | switch buried head ladder | intrerupator ingropat cap scara | buc | 4 | 0 |  | 0 | 0
ELmb | 13 | fireproof cable type CYYF 3x1.5 mmp | cablu ignifug tip CYYF 3x1.5 mmp | ml | 750 | 0 |  | 0 | 0
ELmb | 14 | fireproof cable type CYYF 3x2.5 mmp | cablu ignifug tip CYYF 3x2.5 mmp | ml | 810 | 0 |  | 0 | 0
ELmb | 15 | fireproof cable type CYYF 5x6 mmp | cablu ignifug tip CYYF 5x6 mmp | ml | 76 | 0 |  | 0 | 0
ELmb | 16 | slits for installations | slit zidarie | ml | 1126 | 0 |  | 0 | 0
ELmb | 17 | electrical protection PVC tubes Dn18 | copex Dn 18 | ml | 750 | 0 |  | 0 | 0
ELmb | 18 | electrical protection PVC tubes Dn20 | copex Dn 20 | ml | 810 | 0 |  | 0 | 0
ELmb | 19 | plastering 5 cm | tencuiala 5 cm | mp | 225.2 | 0 |  | 0 | 0
ELmb | 20 | supports LED light fixtures | suporti sustinere corpuri de iluminat LED | buc | 10 | 0 |  | 0 | 0
ELmb | 21 | electrical connections | legaturi electrice | buc | 1233 | 0 |  | 0 | 0
ELmb | 22 | realization of electrical connections | realizare izolatii legaturi electrice | buc | 1233 | 0 |  | 0 | 0
ELmb | 23 | transport of material on a distance of 50 km | transport materiale pe distanta de 50 km | to | 0.89 | 0 |  | 0 | 0
ELmb | 24 | downloading materials | descarcare materiale | to | 0.89 | 0 |  | 0 | 0
ELmb | 25 | electrical power for samples | energie electrica pentru probe | kW | 10 | 0 |  | 0 | 0
ELmb | 26 | electrical protection PVC tubes Dn40 | copex Dn 40 | ml | 76 | 0 |  | 0 | 0
ELmb | 27 | electrical protection metal tubes Dn18 | copex metalic Dn 18 | ml | 40 | 0 |  | 0 | 0
ELmb | 28 | metallic grip clamps for metal protection tubes | cleme prindere copex metalic | buc | 50 | 0 |  | 0 | 0
|  | Fire detection ALARM SYSTEM | Instalatii detectie si semnalizare incendii |  |  |  |  | 0 | 0
FDmb | 1 | fire detection and fire alarm system | centrala detectie si semnalizare incendiu | buc | 1 | 0 |  | 0 | 0
FDmb | 2 | conventional outdoor siren with flash and included battery | sirena conventionala de exterior cu flash si acumulator inclus | buc | 1 | 0 |  | 0 | 0
FDmb | 3 | siren and flash addressable interior | sirena si flash adresabil de interior | buc | 5 | 0 |  | 0 | 0
FDmb | 4 | optical smoke detector | detector optic de fum | buc | 26 | 0 |  | 0 | 0
FDmb | 5 | optical-thermal indoor detector | detector optic-termic de interior | buc | 2 | 0 |  | 0 | 0
FDmb | 6 | indoor fire button of addressable type | buton de incendiu de interior de tip adresabil | buc | 8 | 0 |  | 0 | 0
FDmb | 7 | fireproof wire type JYSTY 2x2x1 mmp | conductor ignifug tip JYSTY 2x2x1 mmp | ml | 560 | 0 |  | 0 | 0
FDmb | 8 | electrical protectionPVC tubes Dn18 | copex Dn 18 | ml | 520 | 0 |  | 0 | 0
FDmb | 9 | electrical protection metal tubes Dn18 | copex metalic Dn 18 | ml | 40 | 0 |  | 0 | 0
FDmb | 10 | electrical connections | legaturi electrice | buc | 1233 | 0 |  | 0 | 0
FDmb | 11 | realization of electrical connections | realizare izolatii legaturi electrice | buc | 1233 | 0 |  | 0 | 0
FDmb | 12 | transport of material on a distance of 50 km | transport materiale pe distanta de 50 km | to | 0.89 | 0 |  | 0 | 0
FDmb | 13 | downloading materials | descarcare materiale | to | 0.89 | 0 |  | 0 | 0
|  | Heating installation | Instalatii incalzire |  |  |  |  | 0 | 0
THmb | 1 | steel radiator PKKP 600x400 | radiator otel PKKP 600x400 | buc | 3 | 0 |  | 0 | 0
THmb | 2 | steel radiator PKKP 600x600 | radiator otel PKKP 600x600 | buc | 5 | 0 |  | 0 | 0
THmb | 3 | steel radiator PKKP 600x800 | radiator otel PKKP 600x800 | buc | 3 | 0 |  | 0 | 0
THmb | 4 | steel radiator PKKP 600x900 | radiator otel PKKP 600x900 | buc | 1 | 0 |  | 0 | 0
THmb | 5 | steel radiator PKKP 600x1000 | radiator otel PKKP 600x1000 | buc | 2 | 0 |  | 0 | 0
THmb | 6 | steel radiator PKKP 600x1400 | radiator otel PKKP 600x1400 | buc | 4 | 0 |  | 0 | 0
THmb | 7 | steel radiator PKKP 600x2000 | radiator otel PKKKP 500x2000 | buc | 1 | 0 |  | 0 | 0
THmb | 8 | steel radiator PKKP 600x1800 | radiator otel PKKKP 600x1800 | buc | 2 | 0 |  | 0 | 0
THmb | 9 | steel radiator PKKP 600x2000 | radiator otel PKKKP 600x2000 | buc | 7 | 0 |  | 0 | 0
THmb | 10 | manifold-collector 5 fully equipped circuits | distribuitor-colector 5 circuite complet echipat | buc | 2 | 0 |  | 0 | 0
THmb | 11 | manifold-collector 7 fully equipped circuits | distribuitor-colector 7 circuite complet echipat | buc | 1 | 0 |  | 0 | 0
THmb | 12 | manifold-collector 11 fully equipped circuits | distribuitor-colector 11 circuite complet echipat | buc | 1 | 0 |  | 0 | 0
THmb | 13 | manifold-collector box 5 circuits | cutie distribuitor-colector 5 circuite | buc | 2 | 0 |  | 0 | 0
THmb | 14 | manifold-collector box 7 circuits | cutie distribuitor-colector 7 circuite | buc | 1 | 0 |  | 0 | 0
THmb | 15 | manifold-collector box 11 circuits | cutie distribuitor-colector 11 circuite | buc | 1 | 0 |  | 0 | 0
THmb | 16 | main radiator tap | robinet radiator tur | buc | 28 | 0 |  | 0 | 0
THmb | 17 | second radiator tap | robinet radiator retur | buc | 28 | 0 |  | 0 | 0
THmb | 18 | brass adapter 18x1 / 2 "outer thread | adaptor alama 18x1/2" FE | buc | 56 | 0 |  | 0 | 0
THmb | 19 | copper bridle 18 - 90 degrees inside inside | cot cupru 18 - 90 grd MM | buc | 112 | 0 |  | 0 | 0
THmb | 20 | insulated copper pipe 18x1 mm | teava cupru izolata 18x1 mm | ml | 980 | 0 |  | 0 | 0
THmb | 21 | insulated copper pipe 28x1 mm | teava cupru izolata 28x1 mm | ml | 30 | 0 |  | 0 | 0
THmb | 22 | insulated copper pipe 35x1 mm | teava cupru izolata 35x1 mm | ml | 140 | 0 |  | 0 | 0
THmb | 23 | copper bend 28 - 90 inner-inner | cot cupru 28 - 90 grd MM | buc | 12 | 0 |  | 0 | 0
THmb | 24 | copper bend 28 - 90 inner-inner | cot cupru 35 - 90 grd MM | buc | 40 | 0 |  | 0 | 0
THmb | 25 | copper plug 28 inner-inner | mufa cupru 28 MM | buc | 6 | 0 |  | 0 | 0
THmb | 26 | copper plug 28 inner-inner | mufa cupru 35 MM | buc | 26 | 0 |  | 0 | 0
THmb | 27 | metallic necklace with 1" | colier metalic cu cauciuc 1" | buc | 14 | 0 |  | 0 | 0
THmb | 28 | metallic necklace with 11/4 " | colier metalic cu cauciuc 11/4" | buc | 80 | 0 |  | 0 | 0
THmb | 29 | heating header - inlet | distribuitor tur incalzire | buc | 1 | 0 |  | 0 | 0
THmb | 30 | heating header - outlet | distribuitor retur incalzire | buc | 1 | 0 |  | 0 | 0
THmb | 31 | valve 1" with screwed union | robinet olandez 1" | buc | 2 | 0 |  | 0 | 0
THmb | 32 | brass adapter 28x12 " inside thread | adaptor alama 28x1" FI | buc | 2 | 0 |  | 0 | 0
THmb | 33 | screwed union for 1'' pump | olandez pompa 1" | buc | 2 | 0 |  | 0 | 0
THmb | 34 | brass adapter 28x12 " outer thread | adaptor alama 28x1" FE | buc | 2 | 0 |  | 0 | 0
THmb | 35 | brass screwed union 1'' inside/outside thread | olandez alama 1" FIFE | buc | 2 | 0 |  | 0 | 0
THmb | 36 | reversing flap 1" | clapeta sens 1" | buc | 1 | 0 |  | 0 | 0
THmb | 37 | valve 3/4" with screwed union | robinet olandez 3/4" | buc | 3 | 0 |  | 0 | 0
THmb | 38 | brass adapter 28x12 " outside thread | adaptor alama 22x3/4" FI | buc | 2 | 0 |  | 0 | 0
THmb | 39 | elbow piece 22-90mm | cot cupru 22 - 90 MM | buc | 14 | 0 |  | 0 | 0
THmb | 40 | brass adapter 22x3/4" outside thread | adaptor alama 22x3/4" FE | buc | 8 | 0 |  | 0 | 0
THmb | 41 | brass screwed union 3/4'' inside/outside thread | olandez alama 3/4 FIFE | buc | 2 | 0 |  | 0 | 0
THmb | 42 | reversing flap 3/4" | clapeta sens 3/4" | buc | 1 | 0 |  | 0 | 0
THmb | 43 | copper pipe 22x1 mm | teava cupru 22x1 mm | ml | 20 | 0 |  | 0 | 0
THmb | 44 | metallic necklace with 3/4 " | colier metalic cu cauciuc 3/4" | buc | 10 | 0 |  | 0 | 0
THmb | 45 | drain tap 1/2 " | robinet golire 1/2" | buc | 1 | 0 |  | 0 | 0
THmb | 46 | valve 1 1/4" with screwed union | robinet olandez 11/4" | buc | 6 | 0 |  | 0 | 0
THmb | 47 | brass screwed union 35x1 1/4" inside thread | adaptor alama 35x11/4" FI | buc | 6 | 0 |  | 0 | 0
THmb | 48 | screwed union for 1 1/4'' pump | olandez pompa 11/4" | buc | 6 | 0 |  | 0 | 0
THmb | 49 | brass screwed union 35x1 1/4" outside thread | adaptor alama 35x11/4" FE | buc | 6 | 0 |  | 0 | 0
THmb | 50 | reversing flap 11/4" | clapeta sens 11/4" | buc | 3 | 0 |  | 0 | 0
THmb | 51 | galvanized steel elbow 2 "inner-threaded thread | cot otel zincat 2" FIFI | buc | 10 | 0 |  | 0 | 0
THmb | 52 | galvanized T-pipe 2" x 1" x 2" | teu redus zincat 2"x1"x2" | buc | 7 | 0 |  | 0 | 0
THmb | 53 | thermometer | termometru | buc | 2 | 0 |  | 0 | 0
THmb | 54 | pressure gauge | manometru | buc | 4 | 0 |  | 0 | 0
THmb | 55 | reducer galvanized steel 1 "-3/8" | reductie otel zincat 1"-3/8" | buc | 4 | 0 |  | 0 | 0
THmb | 56 | valve 3/8" | robinet trecere 3/8" | buc | 4 | 0 |  | 0 | 0
THmb | 57 | valve 2" | robinet trecere 2" | buc | 4 | 0 |  | 0 | 0
THmb | 58 | reversing flap | clapeta sens 2" | buc | 1 | 0 |  | 0 | 0
THmb | 59 | translation | olandez pompa 2" | buc | 2 | 0 |  | 0 | 0
THmb | 60 | 3-way valve 2" | vana cu 3 cai 2" | buc | 1 | 0 |  | 0 | 0
THmb | 61 | translation | olandez otel zincat 2" | buc | 2 | 0 |  | 0 | 0
THmb | 62 | reducer galvanized steel 2 "-11/4" | reductie otel zincat 2"-11/4" | buc | 1 | 0 |  | 0 | 0
THmb | 63 | valve 11/4" | robinet trecere 11/4" | buc | 2 | 0 |  | 0 | 0
THmb | 64 | translation | olandez pompa 11/4" | buc | 2 | 0 |  | 0 | 0
THmb | 65 | translation | Teu redus zincat 2"x11/4"x2" | buc | 1 | 0 |  | 0 | 0
THmb | 66 | galvanized pipe 2" | teava zincata 2" | ml | 15 | 0 |  | 0 | 0
THmb | 67 | zinc pipe 11/4 " | teava zincata 11/4" | ml | 1 | 0 |  | 0 | 0
THmb | 68 | safety valve 1 " | supapa siguranta 1" | buc | 2 | 0 |  | 0 | 0
THmb | 69 | transport of material on a distance of 50 km | transport materiale pe distanta de 50 km | to | 2.6 | 0 |  | 0 | 0
THmb | 70 | downloading materials | descarcare materiale | to | 2.6 | 0 |  | 0 | 0
THmb | 71 | the tightness test | proba de etanseitate | ml | 1150 | 0 |  | 0 | 0
THmb | 72 | testing in operation | proba la cald | ml | 1150 | 0 |  | 0 | 0
THmb | 73 | Zinc coated steel nipple 1 " | niplu otel zincat 1" | buc | 7 | 0 |  | 0 | 0
| 4.2 | Installation for technological & functional equipments | Montaj utilaje, echipamente tehnologice si functionale |  |  |  |  | 0 | 0
AextM | 1 | Main building, storage DO 04 | Cladire principala, magazie DO 04 |  | according to List / conform listei |  |  | 0 | 0
AextM | 2
AextM | 3
| 4.3 | Technological & functional equipments- acquisition | Utilaje, echipamente tehnologice si functionale - aprovizionare |  |  |  |  | 0 | 0
AextA | 1 | Main building, storage DO 04 | Cladire principala, magazie DO 04 |  | according to List / conform listei |  |  | 0 | 0
AextA | 2
| 4.4 | Technological & transport equipments- acquisition | Utilaje, echipamente tehnologice si de transport - aprovizionare |  |  |  |  | 0 | 0
AextT | 1 | Main building DO 04 | Cladire principala DO 04 |  |  |  |  | 0 | 0
AextT | 2 | [6 empty] | 0 | 0
| 4.5 | Appliances | Dotari |  |  |  |  | 0 | 0
AextD | 1 | Furniture - Main building, storage DO 04 | Mobilier - Cladire principala, magazie DO 04 |  | according to List / conform listei |  |  | 0 | 0
AextD | 2 | Appliances - Main building, storage DO 04 | Dotari - Cladire principala magazie DO 04 |  | according to List / conform listei |  |  | 0 | 0
| 4.6 | Non-physical assets | Active necorporale |  |  |  |  | 0 | 0
AextN | 1 | [6 empty] | 0 | 0
AextN | 2 | [6 empty] | 0 | 0
|  | TOTAL 4.3+.4.4+4.5+4.6, excl. VAT | TOTAL 4.3+.4.4+4.5+4.6, fara TVA |  |  |  |  | 0 | 0
|  | Item TOTAL, excl. VAT | TOTAL OBIECT, fara TVA |  |  |  |  | 0 | 0
|  | Design Item: DO 05 | Obiect deviz: DO 05
|  | Exterior arrangement works | Amenajari exterioare |  |  | Estimated / Estimare
code cod |  | Type of works [ENG] | Tipul lucrarii [RO] | Unit Unitate | Quantity Cantitate | Unit Price [EUR] Pret unitar | Unit Price [RON] Pret unitar | Amount [EUR] Cost | Amount [RON] Cost
| 4.1 | Construction and installation Works | Lucrari de constructii si instalatii |  |  |  |  | 0 | 0
Aext | 1 | Vertical systematization (land mobilization) | Lucrari de sistematizare pe verticala (mobilizare teren) | 100m3 | 9.82 | 0 |  | 0 | 0
Aext | 2 | Walkways, pavements and pedestrian platforms made of low-strength concrete, 15cm thick, with infrastructure. from 20cm ballast | Alei, trotuare si platforme pietonale betonate din beton slab armat de 15cm grosime, cu infrastruct. din balast 20cm | sqm/mp | 201 | 0 |  | 0 | 0
Aext | 3 | Prefab curbs of vibropressed concrete mounted on mortar, dimensions 500x120x250mm between alleyways and green spaces | Borduri prefab. din beton vibropresat montate pe strat de mortar, dimensiuni 500x120x250mm intre alei si spatiile verzi | m | 220 | 0 |  | 0 | 0
Aext | 4 | Execution of parking platforms and carriageways from broken stone 0-63mm with ballast foundation 20cm | Executie platforme parcare si alei carosabile din piatra sparta impanata 0-63mm cu fundatie de balast 20cm | sqm/mp | 790 | 0 |  | 0 | 0
Aext | 5 | Realization of synthetic multisport glued, sanded with fine sand, 25-30mm long carpet | Realizare covor sintetic multisport, lipit, lestat cu nisip fin, cu lungimea firului de 25-30mm | sqm/mp | 684 | 0 |  | 0 | 0
Aext | 6 | realization of 15cm thick reinforced concrete sports platform on ballast base layer, thickness 15cm | realizare platforma sportiva din beton armat cu grosime de 15cm pe strat de baza din balast, grosime 15cm |  | 684 | 0 |  | 0 | 0
Aext | 7 | The platform adjacent to the sports field from the compacted ballast, 15-20cm thick | Platforma adiacenta terenului de sport din balast compactat, 15-20cm grosime | sqm/mp | 362 | 0 |  | 0 | 0
Aext | 8 | Sport field fencing H=4m with concrete border stone 20x20cm | Gard teren sport H=4m cu bordura de beton de 20x20cm, armat constructiv | m | 41 | 0 |  | 0 | 0
Aext | 8 | Sport field fencing H=4m with concrete seating | Gard teren sport H=4m pe soclu din b.a. | m | 43 | 0 |  | 0 | 0
Aext | 8 | Sport field fencing H=6m with concrete border stone 20x20cm | Gard teren sport H=6m cu bordura de beton de 20x20cm, armat constructiv | m | 25 | 0 |  | 0 | 0
Aext | 8 | Sport field fencing H=4m with concrete seating | Gard teren sport H=6m pe soclu din b.a. | m | 21 | 0 |  | 0 | 0
|  | Concrete seating for the sport field fencing, 20cm width, variable height | realizare soclu gard teren sport, beton armat constructiv, 20cm latime, inaltime variabila, | m3 | 9.6 | 0 |  | 0 | 0
Aext | 9 | Perimeter fence H=2m with casted concrete base, 20x20cm | Gard perimetral H=2m cu bordura turnata din beton 20x20cm | m | 170 | 0 |  | 0 | 0
Aext | 10 | Excavating excavated earth | Evacuare pamant excavat | m3 | 98.5 | 0 |  | 0 | 0
Aext | 11 | Transport of materials | Transport materiale | to | 972.2 | 0 |  | 0 | 0
Aext | 12 | Transport of concrete | Transport beton | to | 526.4 | 0 |  | 0 | 0
Aext | 13 | drain profiling, 20-40 x 30cm | profilare rigola pamant, 20-40 x 30cm | m | 63 | 0 |  | 0 | 0
Aext | 14 | making lawns | realizare suprafete gazon | sqm/mp | 1130 | 0 |  | 0 | 0
Aext | 15 | planting medium-sized fruit trees, complete work | plantare pomi fructiferi talie medie, lucrare completa | pc/buc | 30 | 0 |  | 0 | 0
Aext | 16 | planting decorative shrubs - tuia occidentalis fastigiata, h = 1-1,5m | plantare arbusti decorativi - tuia occidentalis fastigiata, h=1-1,5m | pc/buc | 10 | 0 |  | 0 | 0
| 4.2 | Installation for technological & functional equipments | Montaj utilaje, echipamente tehnologice si functionale |  |  |  |  | 0 | 0
AextM | 1 | exterior arrangement | amenajari exterioare |  | according to List / conform listei
AextM | 2
AextM | 3
| 4.3 | Technological & functional equipments- acquisition | Utilaje, echipamente tehnologice si functionale - aprovizionare |  |  |  |  | 0 | 0
AextA | 1 | exterior arrangement | amenajari exterioare |  | according to List / conform listei
AextA | 2
| 4.4 | Technological & transport equipments- acquisition | Utilaje, echipamente tehnologice si de transport - aprovizionare |  |  |  |  | 0 | 0
AextT | 1 | exterior arrangement | amenajari exterioare |  | according to List / conform listei |  |  | 0 | 0
AextT | 2 | [6 empty] | 0 | 0
| 4.5 | Appliances | Dotari |  |  |  |  | 0 | 0
AextD | 1 | Exterior arrangement DO 05 | Amenajari exterioare DO 05 |  | according to List / conform listei |  |  | 0 | 0
AextD | 2 | [6 empty] | 0 | 0
| 4.6 | Non-physical assets | Active necorporale |  |  |  |  | 0 | 0
AextN | 1 |  |  |  | according to List / conform listei |  |  | 0 | 0
AextN | 2 |  |  |  | according to List / conform listei |  |  | 0 | 0
|  | TOTAL 4.3+.4.4+4.5+4.6, excl. VAT | TOTAL 4.3+.4.4+4.5+4.6, fara TVA |  |  |  |  | 0 | 0
|  | Item TOTAL, excl. VAT | TOTAL OBIECT, fara TVA |  |  |  |  | 0 | 0
|  | Design Item: DO 06 | Obiect deviz: DO 06
|  | Exterior Electrical Installations | Instalatiii electrice exterioare |  |  | Estimated / Estimare
code cod |  | Type of works [ENG] | Tipul lucrarii [RO] | Unit Unitate | Quantity Cantitate | Unit Price [EUR] Pret unitar | Unit Price [RON] Pret unitar | Amount [EUR] Cost | Amount [RON] Cost
| 4.1 | Construction and installation Works | Lucrari de constructii si instalatii |  |  |  |  | 0 | 0
Iext | 1 | foundation poles for the light poles | fundatii stalpi iluminat exterior | m3 | 3.46 | 0 |  | 0 | 0
Iext | 2 | cable type CYAbY 5x10 mmp | cablu tip CYAbY 5x10 mmp | m | 20 | 0 |  | 0 | 0
Iext | 3 | cable type CYAbY 3x2,5 mmp | cablu tip CYAbY 3x2.5 mmp | m | 135 | 0 |  | 0 | 0
Iext | 4 | galvanized steel strip 25x4 mm | platbanda OL Zn 25x4 mm | m | 176 | 0 |  | 0 | 0
Iext | 5 | galvanized steel strip 40x4 mm | platbanda OL Zn 40x4 mm | m | 58 | 0 |  | 0 | 0
Iext | 6 | galvanized galvanized steel electrode 2 ", L = 3 m | electrod vertical OL Zn 2", L= 3 m | pc/buc | 10 | 0 |  | 0 | 0
Iext | 7 | the separation piece | piesa de separatie | pc/buc | 5 | 0 |  | 0 | 0
Iext | 8 | grounding check | verificare priza de pamant | pc/buc | 5 | 0 |  | 0 | 0
Iext | 9 | manual digging | sapatura manuala | m3 | 16 | 0 |  | 0 | 0
Iext | 10 | transport land at 10 km | transport pamant la 10 km | m3 | 16 | 0 |  | 0 | 0
Iext | 11 | transportation of materials to 50 km | transport materiale la 50 km | to | 2.5 | 0 |  | 0 | 0
Iext | 12 | unloading materials on site | descarcare materiale in santier | to | 2.5 | 0 |  | 0 | 0
Iext | 13 | electrical power for samples | energie electrica pentru probe | kW | 2 | 0 |  | 0 | 0
| 4.2 | Installation for technological & functional equipments | Montaj utilaje, echipamente tehnologice si functionale |  |  |  |  | 0 | 0
IextM | 1 | electrical installations - lighting | instalatii electrice - iluminat |  | according to List / conform listei |  |  | 0 | 0
IextM | 2 | surge protection, lightning proofing | instalatii protectie - priza de pamant, protectie trasnet |  | according to List / conform listei |  |  | 0 | 0
IextM | 3
| 4.3 | Technological & functional equipments- acquisition | Utilaje, echipamente tehnologice si functionale - aprovizionare |  |  |  |  | 0 | 0
IextA | 1 | electrical installations | instalatii electrice - iluminat |  | according to List / conform listei |  |  | 0 | 0
IextA | 2 | surge protection, lightning proofing | instalatii protectie - priza de pamant, protectie trasnet |  | according to List / conform listei |  |  | 0 | 0
| 4.4 | Technological & transport equipments- acquisition | Utilaje, echipamente tehnologice si de transport - aprovizionare |  |  |  |  | 0 | 0
IextT | 1 | electrical installations | instalatii electrice - iluminat |  |  |  |  | 0 | 0
IextT | 2 | surge protection, lightning proofing | instalatiiprotectie - priza de pamant, protectie trasnet |  |  |  |  | 0 | 0
| 4.5 | Appliances | Dotari |  |  |  |  | 0 | 0
IextD | 1 | electrical installations | instalatii electrice - iluminat |  |  |  |  | 0 | 0
IextD | 2 | surge protection, lightning proofing | instalatiiprotectie - priza de pamant, protectie trasnet |  |  |  |  | 0 | 0
| 4.6 | Non-physical assets | Active necorporale |  |  |  |  | 0 | 0
IextN | 1 | electrical installations | instalatii electrice - iluminat |  |  |  |  | 0 | 0
IextN | 2 | surge protection, lightning proofing | instalatiiprotectie - priza de pamant, protectie trasnet |  |  |  |  | 0 | 0
|  | TOTAL 4.3+.4.4+4.5+4.6, excl. VAT | TOTAL 4.3+.4.4+4.5+4.6, fara TVA |  |  |  |  | 0 | 0
|  | Item TOTAL, excl. VAT | TOTAL OBIECT, fara TVA |  |  |  |  | 0 | 0
|  | Providing UTILITIES | Asigurarea UTILITATILOR obiectivului |  |  | Estimated / Estimare
|  | Design Item: DO 01 | Obiect deviz: DO 01
|  | Electric power supply | Alimentare cu energie electrica | total |  |  |  | 0 | 0
code cod |  | Type of works [ENG] | Tipul lucrarii [RO] | Unit Unitate | Quantity Cantitate | Unit Price [EUR] Pret unitar | Unit Price [RON] Pret unitar | Amount [EUR] Cost | Amount [RON] Cost
| 4.1 | Construction and installation Works | Lucrari de constructii si instalatii |  |  |  |  | 0 | 0
EP | 1 | cable type CYAbY 5x10 mmp | cablu tip CyAby 5 x 10 mmp | ml | 20 | 0 |  | 0 | 0
EP | 2 | the pillar stradal | stalp stradal | buc | 1 | 0 |  | 0 | 0
EP | 3 | stretching strings | tiranti intindere | buc | 4 | 0 |  | 0 | 0
| 4.2 | Installation for technological & functional equipments | Montaj utilaje, echipamente tehnologice si functionale |  |  |  |  | 0 | 0
EPM | 1 | [6 empty] | 0 | 0
EPM | 2 | [6 empty] | 0 | 0
| 4.3 | Technological & functional equipments- acquisition | Utilaje, echipamente tehnologice si functionale - aprovizionare |  |  |  |  | 0 | 0
EPA | 1 | [6 empty] | 0 | 0
EPA | 2 | [6 empty] | 0 | 0
| 4.4 | Technological & transport equipments- acquisition | Utilaje, echipamente tehnologice si de transport - aprovizionare |  |  |  |  | 0 | 0
EPT | 1 | [6 empty] | 0 | 0
EPT | 2 | [6 empty] | 0 | 0
| 4.5 | Appliances | Dotari |  |  |  |  | 0 | 0
EPD | 1 | [6 empty] | 0 | 0
EPD | 2 | [6 empty] | 0 | 0
| 4.6 | Non-physical assets | Active necorporale |  |  |  |  | 0 | 0
EPN | 1 | [6 empty] | 0 | 0
EPN | 2 | [6 empty] | 0 | 0
|  | TOTAL 4.3+.4.4+4.5+4.6, excl. VAT | TOTAL 4.3+.4.4+4.5+4.6, fara TVA |  |  |  |  | 0 | 0
|  | Design Item: DO 02 | Obiect deviz: DO 02
|  | Drinking water supply | Alimentare cu apa potabila | total |  |  |  | 0 | 0
code cod |  | Type of works [ENG] | Tipul lucrarii [RO] | Unit Unitate | Quantity Cantitate | Unit Price [EUR] Pret unitar | Unit Price [RON] Pret unitar | Amount [EUR] Cost | Amount [RON] Cost
| 4.1 | Construction and installation Works | Lucrari de constructii si instalatii |  |  |  |  | 0 | 0
|  | Interior network | Retea interioara |  |  |  |  | 0 | 0
DWS | 1 | manual digging | sapatura manuala | mc | 24 | 0 |  | 0 | 0
DWS | 2 | sand filling | umplutura nisip | mc | 3 | 0 |  | 0 | 0
DWS | 3 | ballast filling | umplutura balast | mc | 4 | 0 |  | 0 | 0
DWS | 4 | clay filling | umplutura pamant | mc | 17 | 0 |  | 0 | 0
DWS | 5 | transport land at 10 km | transport pamant la 10 km | mc | 17 | 0 |  | 0 | 0
DWS | 6 | transport land at 10 km | transport pamant la 10 km | mc | 17 | 0 |  | 0 | 0
DWS | 7 | transportation of materials to 50 km | transport materiale la 50 km | to | 0.8 | 0 |  | 0 | 0
DWS | 8 | unloading materials on site | descarcare materiale in santier | to | 0.8 | 0 |  | 0 | 0
DWS | 9 | HDPE pipe Dn 40 | teava PEHD Dn 40 | ml | 50 | 0 |  | 0 | 0
|  | Service line | Bransament |  |  |  |  | 0 | 0
DWS | 10 | HDPE pipe Dn 40 | teava PEHD Dn 40 | ml | 6 | 0 |  | 0 | 0
DWS | 11 | manual digging | sapatura manuala | mc | 6 | 0 |  | 0 | 0
DWS | 12 | sand filling | umplutura nisip | mc | 2 | 0 |  | 0 | 0
DWS | 13 | ballast filling | umplutura balast | mc | 4 | 0 |  | 0 | 0
DWS | 14 | transport land at 10 km | transport pamant la 10 km | mc | 6 | 0 |  | 0 | 0
DWS | 15 | transportation of materials to 50 km | transport materiale la 50 km | to | 0.2 | 0 |  | 0 | 0
DWS | 16 | unloading materials on site | descarcare materiale in santier | to | 0.2 | 0 |  | 0 | 0
DWS | 17 | PVC pipe Dn 125 | teava PVC Dn 125 | ml | 40 | 0 |  | 0 | 0
| 4.2 | Installation for technological & functional equipments | Montaj utilaje, echipamente tehnologice si functionale |  |  |  |  | 0 | 0
DWSM | 1 | Drinking water counter | Contor apa potabila |  | according to List / conform listei |  |  | 0 | 0
DWSM | 2 | [6 empty] | 0 | 0
| 4.3 | Technological & functional equipments- acquisition | Utilaje, echipamente tehnologice si functionale - aprovizionare |  |  |  |  | 0 | 0
DWSA | 1 | Drinking water counter | Contor apa potabila |  | according to List / conform listei |  |  | 0 | 0
DWSA | 2 | [6 empty] | 0 | 0
| 4.4 | Technological & transport equipments- acquisition | Utilaje, echipamente tehnologice si de transport - aprovizionare |  |  |  |  | 0 | 0
DWST | 1 |  |  |  | according to List / conform listei |  |  | 0 | 0
DWST | 2 |  |  |  | according to List / conform listei |  |  | 0 | 0
| 4.5 | Appliances | Dotari |  |  |  |  | 0 | 0
DWSD | 1 |  | Retea interioara |  |  |  |  | 0 | 0
DWSD | 2 |  | Bransament |  |  |  |  | 0 | 0
| 4.6 | Non-physical assets | Active necorporale |  |  |  |  | 0 | 0
DWSN | 1 | [6 empty] | 0 | 0
DWSN | 2 | [6 empty] | 0 | 0
|  | TOTAL 4.3+.4.4+4.5+4.6, excl. VAT | TOTAL 4.3+.4.4+4.5+4.6, fara TVA |  |  |  |  | 0 | 0
|  | Design Item: DO 03 | Obiect deviz: DO 03
|  | Sewage system | Canalizare | total |  |  |  | 0 | 0
code cod |  | Type of works [ENG] | Tipul lucrarii [RO] | Unit Unitate | Quantity Cantitate | Unit Price [EUR] Pret unitar | Unit Price [RON] Pret unitar | Amount [EUR] Cost | Amount [RON] Cost
| 4.1 | Construction and installation Works | Lucrari de constructii si instalatii |  |  |  |  | 0 | 0
|  | Installations Works | Lucrari de instalatii |  |  |  |  | 0 | 0
SWSI | 1 | manual digging | sapatura manuala | mc | 30.6 | 0 |  | 0 | 0
SWSI | 2 | sand filling | umplutura nisip | mc | 7.92 | 0 |  | 0 | 0
SWSI | 3 | ballast filling | umplutura balast | mc | 8.92 | 0 |  | 0 | 0
SWSI | 4 | clay filling | umplutura pamant | mc | 13.76 | 0 |  | 0 | 0
SWSI | 5 | transport land at 10 km | transport pamant la 10 km | mc | 13.76 | 0 |  | 0 | 0
SWSI | 6 | transport land at 10 km | transport pamant la 10 km | mc | 13.76 | 0 |  | 0 | 0
SWSI | 7 | transportation of materials to 50 km | transport materiale la 50 km | to | 2.2 | 0 |  | 0 | 0
SWSI | 8 | unloading materials on site | descarcare materiale in santier | to | 2.2 | 0 |  | 0 | 0
SWSI | 9 | manhole for waste water inclusive cover | camin canalizare 80 x 80 inclusiv capac | buc | 5 | 0 |  | 0 | 0
|  | Structure Works (sewage tank) | Lucrari structura de rezistenta (bazin vidanjabil) |  |  |  |  | 0 | 0
SWSS | 1 | mechanical excavator digging | sapatura mecanica cu excavatorul | m3x100 | 0.11 | 0 |  | 0 | 0
SWSS | 2 | shoveling the earth | imprastierea cu lopata a pamantului | m3 | 63 | 0 |  | 0 | 0
SWSS | 3 | transporting land with a mast to 30m | transport pamant cu roaba la 30m | m3 | 63 | 0 |  | 0 | 0
SWSS | 4 | uploading land in the car | incarc. pamantului in auto | to | 85 | 0 |  | 0 | 0
SWSS | 5 | road transport of land to 5km | transportul rutier al pamntului la 5km | to | 85 | 0 |  | 0 | 0
SWSS | 6 | equalising casting concrete c8 / 10 (b150) | turnare betonului c8/10(b150) de egalizare | m3 | 2.1 | 0 |  | 0 | 0
SWSS | 7 | concrete casting in sockets and walls c20 / 25 (b330) | turnare betonului in socluri si pereti c20/25(b330) | m3 | 21 | 0 |  | 0 | 0
SWSS | 8 | shuttering panels made of reusable panels at elevators | cofraje din panouri refolosibile la elevatii | sqm/mp | 86 | 0 |  | 0 | 0
SWSS | 9 | shuttering panels made of board reusable panels | cofraje din panouri refolosibile la placi | sqm/mp | 12.5 | 0 |  | 0 | 0
SWSS | 10 | system of expandable metal beams | sistem din grinzi metalice extensibile | sqm/mp | 12.5 | 0 |  | 0 | 0
SWSS | 11 | extended extension props | sustineri din popi extensibili | pc/buc | 12 | 0 |  | 0 | 0
SWSS | 12 | reinforcement of ob37; d <= 8, in foundations and radiier | armatura din ob37; d<=8, in fundatii si radier | kg | 350 | 0 |  | 0 | 0
SWSS | 13 | reinforcement of pc52; d> 8, in foundations and elevations | armatura din pc52; d>8, in fundatii si elevatii | kg | 500 | 0 |  | 0 | 0
SWSS | 14 | mounting welded nets | montare plase sudate | kg | 595 | 0 |  | 0 | 0
SWSS | 15 | road transport of concrete at 15km | transport rutier al betonului la 15km | to | 59 | 0 |  | 0 | 0
SWSS | 16 | road transport of materials to 15km | transport rutier al materialelor la 15km | to | 12 | 0 |  | 0 | 0
SWSS | 17 | surface priming for differential vapor application with bitumen cut in 2 layers horizontal and vertical surface | amorsarea supr. pt. aplic. strat dif. vapori cu bitum taiat in 2 straturi supraf. orizont. si vert. | sqm/mp | 66 | 0 |  | 0 | 0
SWSS | 18 | hot waterproof bit board with bit mastic bit or bit with added rubber type supr incl> 40% ve | strat hidroiz cald cu carton bit lip cu mastic bit sau bit cu adaos cauciuc tip supr incl >40% ve | sqm/mp | 66 | 0 |  | 0 | 0
SWSS | 19 | vertical waterproofing protection against hdpe membrane walls | protectie hidroizolatie verticala la pereti cu membrana hdpe | sqm/mp | 66 | 0 |  | 0 | 0
| 4.2 | Installation for technological & functional equipments | Montaj utilaje, echipamente tehnologice si functionale |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.3 | Technological & functional equipments- acquisition | Utilaje, echipamente tehnologice si functionale - aprovizionare |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.4 | Technological & transport equipments- acquisition | Utilaje, echipamente tehnologice si de transport - aprovizionare |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.5 | Appliances | Dotari |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.6 | Non-physical assets | Active necorporale |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
|  | TOTAL 4.3+.4.4+4.5+4.6, excl. VAT | TOTAL 4.3+.4.4+4.5+4.6, fara TVA |  |  |  |  | 0 | 0
|  | Utilities TOTAL, excl. VAT | TOTAL Utilitati, fara TVA |  |  |  |  | 0 | 0
|  | Design Item: DO OS | Obiect deviz: DO OS
|  | Electric power supply | Organizare de santier | total |  |  |  | 0 | 0
code cod |  | Type of works [ENG] | Tipul lucrarii [RO] | Unit Unitate | Quantity Cantitate | Unit Price [EUR] Pret unitar | Unit Price [RON] Pret unitar | Amount [EUR] Cost | Amount [RON] Cost
| 4.1 | Construction and installation Works | Lucrari de constructii si instalatii |  |  |  |  | 0 | 0
os | 1 | Location barracks for construction site (Site Manager office, tool storage, locker) | amplasare baraci (birou sef santier, magazie scule si unelte, vestiar) | buc | 2 | 0 |  | 0 | 0
os | 2 | Site presentation sign | panoul de santier | buc | 1 | 0 |  | 0 | 0
os | 3 | Temporary fencing | imprejmuire provizorie | ml | 200 | 0 |  | 0 | 0
os | 4 | Location for toilettes | amplasare grupuri sanitare ecologice | buc | 2 | 0 |  | 0 | 0
os | 5 | Warning signs | marcaje avertizare | buc | 2 | 0 |  | 0 | 0
os | 8 | Arrangement of materials platform | amenajare platforma materiale | mp | 60 | 0 |  | 0 | 0
os | 9
os | 10
os | 11
os | 12
os | 13
os | 14
os | 15
| 4.2 | Installation for technological & functional equipments | Montaj utilaje, echipamente tehnologice si functionale |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.3 | Technological & functional equipments- acquisition | Utilaje, echipamente tehnologice si functionale - aprovizionare |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.4 | Technological & transport equipments- acquisition | Utilaje, echipamente tehnologice si de transport - aprovizionare |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.5 | Appliances | Dotari |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
| 4.6 | Non-physical assets | Active necorporale |  |  |  |  | 0 | 0
| 1 | [6 empty] | 0 | 0
| 2 | [6 empty] | 0 | 0
|  | TOTAL 4.3+.4.4+4.5+4.6, excl. VAT | TOTAL 4.3+.4.4+4.5+4.6, fara TVA |  |  |  |  | 0 | 0

## fise tehnice
Construire Centru Turistic pentru activitati culturale si sportive - Lupsa de Jos, comuna Brosteni, jud. Mehedinti
Building a Tourism Center for cultural and sports activities- Lupsa de Jos, comuna Brosteni, jud. Mehedinti
LIST OF EQUIPMENTS & APPLIANCES LISTA echipamente si dotari
| Curs |  |  | Exchange rate / Curs schimb InforEUR | 29.12.2017 | 1 EUR = | 4.644 | RON | installation / montaj (%) |  | 5
|  |  | Cells marked with this color, to be completed by Contractor | Se vor completa celulele marcate cu aceasta culoare de catre Constructor
Nr. Crt. | Denomination | Denumire | Specifications | Principalele caracteristici tehnice | Quantity / Cantitate | Price [EUR] excl. VAT | Price [RON] excl. VAT | Amount Cost total [EUR] | Amount Cost total [RON] | INSTALLATION cost /Montaj [EUR] | INSTALLATION cost / Montaj [RON]
| Technological equipments | Echipamente tehnologice | [5 empty] | 0 | 0 | 0 | 0
DO 04 | Main Building, Storage | Cladire principala, magazie | [5 empty] | 0 | 0 | 0 | 0
1 | Heating station (wood) | Centrala termica pe lemne | Gasification plant; thermal power 100kw; single-phase food; modular power in the power range | Centrala cu gazeificare; putere termica 100kw; alimentare monofazica; putere modulanta in plaja de puteri | 1 | 0 |  | 0 | 0 | 0 | 0
2 | Bivalent boiler for domestic hot water preparation | Boiler bivalent preparare apa calda menajera | Capacity 300 liters; number of resistances: 1;vertical mounting | Capacitate 300 litri; numar rezistente:1; montaj vertical | 1 | 0 |  | 0 | 0 | 0 | 0
3 | Heat circulation pump | Pompa circulatie incalzire | Single-phase pump; maximum flow rate 3,87mc / h; pumping height 6mCA; | Pompa monofazica; debit maxim 3,87mc/h; inaltime de pompare 6mCA; | 1 | 0 |  | 0 | 0 | 0 | 0
4 | Domestic hot water circulation pump | Pompa circulatie apa calda menajera | Single-phase pump; maximum flow 0,43 mc / h; pumping height 2 mCA; | Pompa monofazica; debit maxim 0,43 mc/h; inaltime de pompare 2 mCA; | 1 | 0 |  | 0 | 0 | 0 | 0
5 | Solar panels kit | Kit panouri solare | Kit fully equipped for solar panels; Expansion vessel included | Kit complet echipat pentru panouri solare; Vas de expansiune inclus | 1 | 0 |  | 0 | 0 | 0 | 0
6 | Closed expansion vessel | Vas de expansiune inchis | Vertical expansion vessel: Capacity 50 liters | Vas de expansiune vertical; Capacitate 50 litri | 3 | 0 |  | 0 | 0 | 0 | 0
7 | Recirculating central heating pump | Pompa recirculare centrala termica | Single-phase pump; Max flow rate 2,5mc / h; Pumping height 3 mCA | Pompa monofazica; Debit maxim 2,5mc/ h; Inaltime de pompare 3 mCA | 1 | 0 |  | 0 | 0 | 0 | 0
8 | Uninterruptible source UPS 2 kW | Sursa uninteruptibila UPS 2 kW | Single-phase power supply; Power 2 kW; Operating time 6 hours | Sursa monofazica; Putere 2 kW; Timp de functionare 6 ore | 1 | 0 |  | 0 | 0 | 0 | 0
10 | Solar panels for DHW preparation | Panouri solare pentru preparare ACM | Number of vacuum tubes 12 / panel | Numar tuburi vidate 12/ panou | 2 | 0 |  | 0 | 0 | 0 | 0
11 | Air conditioner | Aparat aer conditionat | Wall mounting, Cooling capacity - 12,000 Btu, Single-phase power supply | Montaj pe perete, Capacitate de racire – 12000 Btu, Alimentare monofazica | 13 | 0 |  | 0 | 0 | 0 | 0
15 | Recirculating central heating pump | Pompa recirculare centrala termica | Single-phase pump; Max flow rate 0,44mc / h; Pumping height 2,5 mCA | Pompa monofazica; Debit maxim 0,44mc/ h; Inaltime de pompare 2,5 mCA | 1 | 0 |  | 0 | 0 | 0 | 0
16 | Recirculating central heating pump | Pompa recirculare centrala termica | Single-phase pump; Max flow rate 1,21mc / h; Pumping height 2,5 mCA | Pompa monofazica; Debit maxim 1,21mc/ h; Inaltime de pompare 2,5 mCA | 1 | 0 |  | 0 | 0 | 0 | 0
17 | Recirculating central heating pump | Pompa recirculare centrala termica | Single-phase pump; Max flow rate 1,29mc / h; Pumping height 2,5 mCA | Pompa monofazica; Debit maxim 1,29mc/ h; Inaltime de pompare 2,5 mCA | 1 | 0 |  | 0 | 0 | 0 | 0
18 | Recirculating central heating pump | Pompa recirculare centrala termica | Single-phase pump; Max flow rate 0,92mc / h; Pumping height 2,5 mCA | Pompa monofazica; Debit maxim 0,92mc/ h; Inaltime de pompare 2,5 mCA | 1 | 0 |  | 0 | 0 | 0 | 0
19 | Recirculating hot water pump | Pompa recirculare apa calda | Single-phase pump; Max flow rate 1mc / h; Pumping height 1 mCA | Pompa monofazica; Debit maxim 1mc/ h; Inaltime de pompare 1 mCA | 1 | 0 |  | 0 | 0 | 0 | 0
DO 06 | Exterior electrical installations | Instalatii electrice exterioare | [5 empty] | 0 | 0 | 0 | 0
| Electrical installations - lighting | Instalatii electrice - iluminat | [5 empty] | 0 | 0 | 0 | 0
20 | sports field poles with halogen projectors | Stalp iluminat teren sport cu proiectoare halogen | Halogen projectors, 400w; poles H=6m | Proiectoare halogen, 400w; stalpi H=6m | 4 | 0 |  | 0 | 0 | 0 | 0
21 | Illuminated incandescent poles | Stalp iluminat incinta | Independent luminaires with solar panel, led lamp, 30w, battery, automation, autonomy t = 6h | Corpuri de iluminat independente cu panou solar, proiector led, 30w, acumulator, automatizare, autonomie t=6h | 8 | 0 |  | 0 | 0 | 0 | 0
| Surge protection, lightning proofing | Instalatii protectie - priza de pamant, protectie trasnet | [5 empty] | 0 | 0 | 0 | 0
22 | Lightning rod system | Paratrasnet de tip Ioniflash | Action range 23 m • Counter included • Lowering to ground sockets included | Raza de actiune 23 m; Contor inclus; Coborari la prize de pamant incluse | 1 | 0 |  | 0 | 0 | 0 | 0
DO 02 | Drinking water system | Alimentare cu apa | [5 empty] | 0 | 0 | 0 | 0
23 | Drinking water counter | Contor apa potabila | Drinking water meter Dn 32 - Outdoor mounting | Contor apa potabila Dn 32 - Montaj la exterior | 1 | 0 |  | 0 | 0 | 0 | 0
| Furniture | Mobilier | [5 empty] | 0 | 0 | 0 | 0
DO 04 | Main Building | Cladire principala | [5 empty] | 0 | 0
1 | Visitor seat with backrest | Scaun tip vizitator cu spatar | Size (L x W x h): 0.54x0.45x0.79m (+/- 10%); steel frame, seat and back made of lacquered wood | Gabarit ( L x l x h ) : 0.54x0.45x0.79m (+/- 10%); cadru metalic din otel, sezut si spatar realizat din lemn lacuit | 60 | 0 |  | 0 | 0 | 0 | 0
2 | Ergonomic office chair | Scaun ergonomic pentru birou | Size (L x W x Hmax): 0.45x0.41x1.175m (+/- 10%), structure: nylon and metal, upholstery: black cloth, seat and seat mechanism seat: fixed, with backrest and armrests | Gabarit ( L x l x hmax ) : 0.45x0.41x1.175m (+/- 10%); structura: nylon si metal; tapiterie: stofa neagra; Mecanism scaun si sezut scaun: fix; dotat cu spatar si cotiere | 2 | 0 |  | 0 | 0 | 0 | 0
3 | Wall hung | Cuier de perete | Size (L x W): 0.60x0.04m (+/- 10%), wood / stainless steel | Gabarit ( L x l ) : 0.60x0.04m (+/- 10%), lemn/inox | 1 | 0 |  | 0 | 0 | 0 | 0
4 | Office desk | Birou | Chipboard with ABS edges, 70x150x80, drawer, one door, 2 intermediate shelves | PAL cu canturi din ABS, 70x150x80, sertar, o usa, 2 polite intermediare | 2 | 0 |  | 0 | 0 | 0 | 0
5 | Toilet table with mirror | Masa de toaleta cu oglinda | Chipboard with ABS edges; 1.85 x 0.6m; the mirror with the frame | PAL cu canturi din ABS; 1.85 x 0.6m; oglinda cu rama | 2 | 0 |  | 0 | 0 | 0 | 0
6 | locker room bench | Banca vestiar | 1.80 x 0.45, metal frame and wooden saddle | 1.80 x 0.45, cadru metalica si sezut din lemn | 4 | 0 |  | 0 | 0 | 0 | 0
7 | 3-door locker | Dulap vestiar cu 3 usi | 0.9m x 0.6m x 0.90m; Fiscal metallic paint in electrostatic field; Equipped with locks | 0.9m x 0.6m x 0.90m; Fiset metalic vopsit in camp electrostatic; Dotate cu incuietori | 6 | 0 |  | 0 | 0 | 0 | 0
8 | Document box with 5 shelves | Dulap pentru documente cu 5 polite | 0.80m x 0.45m x 2.00m; made of chipboard with shelves open; light color, wood essence | 0.80m x 0.45m x 2,00m; realizat din PAL; cu rafturi deschise; culoare deschisa, esenta lemn | 4 | 0 |  | 0 | 0 | 0 | 0
9 | Buffet shelves | Rafturi bufet | 0.85 x 0.45 m x 2.00 m; made of melaminated chipboard | 0.85 x 0.45 m x 2,00 m; realizat din PAL melaminat | 3 | 0 |  | 0 | 0 | 0 | 0
10 | Counter | Tejghea | 2.70x0.60m; laminated chipboard | 2.70x0.60m; PAL melaminat | 1 | 0 |  | 0 | 0 | 0 | 0
11 | Countertop bodies | Corpuri cu blat | 1.20x 0.6 x 0.9m; body furniture made of melaminated chipboard with drawers, shelves and doors | 1.20x 0.6 x 0.9m; corp mobilier din PAL melaminat dotata cu sertare, rafturi si usi | 2 | 0 |  | 0 | 0 | 0 | 0
12 | Suspended bodies | Corpuri suspendate | 0.6x 0.6 x0.6 m; made of melaminated chipboard, equipped with doors | 0.6x 0.6 x0.6 m; realizate din PAL melaminat, dotat cu usi | 2 | 0 |  | 0 | 0 | 0 | 0
| Appliances | Dotari | [5 empty] | 0 | 0 | 0 | 0
DO 04 | Main Building | Cladire principala | [5 empty] | 0 | 0
1 | Info kiosk | Info kiosk | Single-phase power supply, specific foot mounting - 17 "diagonal screen, Full HD 1920x1080 display resolution - 1TB HDD, USB 2.0, media player directly included - Built-in and active acoustic enclosures - Operating system Windows 10, processor, fanless, minimum 2 Gb RAM - Integrated UPS - Metal keypad | Alimentare monofazica, montaj pe picior specific - Touch screen cu diagonala de 17 inch, rezolutie display Full HD 1920x1080 - HDD 1 TB, USB 2.0, player media direct inclus - Incinte acustice incorporate si active - Sistem de operare Windows 10, processor, fanless, minim 2 Gb RAM - UPS integrat - Tastatura metalica | 1 | 0 |  | 0 | 0 | 0 | 0
2 | Microwave oven | Cuptor cu microunde | Capacity: 20l (+/- 10%); 800W | Capacitate: 20l (+/- 10%); 800W | 1 | 0 |  | 0 | 0 | 0 | 0
3 | Two-sided splitting panels for display | Panourile despartitoare cu 2 fete pt. afisaj | 1.20x2.00m; of metal structure coated with OSB panels finished with washable dyes | 1.20x2.00m; din structura metalica placata cu panouri din OSB finisate cu vopsitorii lavabile | 22 | 0 |  | 0 | 0 | 0 | 0
4 | Refrigerator | Frigider | Efficiency class A +; V 220 - 350l | Clasa de eficienta A+; V 220 - 350l | 2 | 0 |  | 0 | 0 | 0 | 0
5 | Scene Modules | Module scena | 1.05x4.00 m; of the metallic structure; load capacity 150kg / sqm; with mechanical fixation between them to form a stage showcase | 1.05x4.00 m; din structura metalica; capacitate portanta 150kg/mp; cu fixare mecanica intre ele pentru alcatuirea unei podine de spectacol | 11 | 0 |  | 0 | 0 | 0 | 0
6 | projector | Videoproiector | Full HD, 2000lumeni, 1920 x 1080 resolution, with connectors: 1 x USB (Type A) 1 x Composite In 1 x Audio in 2 x HDMI in 1 x stereo mini-jack out | Full HD, 2000lumeni; rezolutie 1920 x 1080; cu conectori: 1 x USB (Type A) 1 x Composite In 1 x Audio in 2 x HDMI in 1 x Stereo mini-jack out | 1 | 0 |  | 0 | 0 | 0 | 0
7 | Projection screen | Ecran proiectie | 180x240cm +/- 10%; Screen type: electric; Surface of vinyl type | 180x240cm +/- 10% ; Tip ecran: electric; Suprafata din material tip vinil | 1 | 0 |  | 0 | 0 | 0 | 0
8 | Portable Calculator for projector | Calculator portabil pt. videoproiector | Dual Core Processor; Video card: 1GB; Operating system included; Hard 1TB | Procesor Dual Core; Placa video: 1GB; Sistem de operare inclus; Hard 1TB | 1 | 0 |  | 0 | 0 | 0 | 0
9 | Exhibition frames | Rame expo | 50x70cm; glass composite frame and hanging system on the wall; back made of MDF | 50x70cm; rama din material compozit cu sticla si sistem de agatat pe perete; spate realizat din MDF | 50 | 0 |  | 0 | 0 | 0 | 0
10 | TV | TV | LCD, diagonal 125-128cm | LCD, diagonala 125-128cm | 1 | 0 |  | 0 | 0 | 0 | 0
DO 05 | Exterior arrangement works | Amenajari exterioare | [5 empty] | 0 | 0
11 | Fully equipped fire extinction set | Pichet PSI complet echipat | 2 portable fire extinguishers, 1 pickaxes ax and 4 buckets of sheet metal | 2 stingatoare portabile, 1 topor tarnacop şi 4 galeti din tabla | 1 | 0 |  | 0 | 0 | 0 | 0
12 | football gates | porti fotbal | galvanized profile, 2x3m including net | porti profile zincate, 2x3m, inclusiv plasa | 2 | 0 |  | 0 | 0 | 0 | 0