ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	3

2.2.	Purpose	4

2.3.	Results to be achieved by the Contractor	4

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	5

4.1.	General	5

4.2.	Specific work	6

4.3.	Project management	10

5.	LOGISTICS AND TIMING	10

5.1.	Location	10

5.2.	Start date & Period of implementation of tasks	10

6.	REQUIREMENTS	10

6.1.	Staff	10

6.2.	Office accommodation	10

6.3.	Facilities to be provided by the Contractor	11

6.4.	Equipment	11

7.	REPORTS	11

7.1.	Reporting requirements	11

7.2.	Submission and approval of reports	11

8.	MONITORING AND EVALUATION	11

8.1.	Definition of indicators	11

8.2.	Special requirements	11

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

General Hospital “Sveti Luka”, Knez Mihajlova 51, Smederevo, Republic of Serbia

## Country background

Republic of Serbia and Romania are faced with challenges in using of new information and communication technologies in medicine what provides new methods for utilizing and improving health services. E-Health is one of the fastest growing sectors in the overall health care market and can be used at the local, national, regional and global levels as a resourceful means to promote and strengthen health systems and health information. It encompasses the ability to document, manage, find, use and share information to support health and social care.

The project is implemented within the Cross-Border Program between Romania and Republic of  Serbia for the period 2014 - 2020. It lays the foundations for using EU funds under the cross-border component of the IPA Regulation, to support cross-border cooperation on the Romanian-Serbian border. Promotion of greater cooperation and contact between the regions and communities on the both sides of the border are one of the main objectives of the Programme, while the improvement of the quality of life for the communities of the border area is perceived as a main specific objective.

Development of cooperation e-Health platform will enable all project partners to cooperate even closer, by using e-health system of telemedicine. The collaboration of hospitals will highlight common issues of interests in public health, health care and health policies and it will, consequently, contribute to the strengthening of the cross-border cooperation between the two countries.

## Current situation in the sector

In today’s healthcare we cannot underestimate the importance of using modern ICT solutions. As these state-of-the-art technologies make healthcare faster, more secure, more efficient, higher in quality, more responsive to patients’ needs – these (sometimes life-saving) solutions inevitably serve the base for the future of healthcare.

In Serbia, up until the year 2000 there was no appropriately structured, operatively efficient information system (the information system was outdated, limited to paper work). Dynamic development that begun in 2005 with the European Union and World Bank has resulted in the launch of several projects. Main health institutions in Serbia following the development and provide telemedicine services (Military Medical Academy, the Institute for Pathology and Forensic Medicine, etc.). This concept should be expanded to all hospitals in Serbia to the entire population had adequate health care.

Romania is an eastern European country that is undergoing rapid reform of its medical system. Assessment of the potential for telemedicine in the country, through a literature review, suggest that telemedicine has the potential to accelerate health-care reform. The main hospitals and universities could promote the wider distribution and development of telemedicine within Romania, which in turn would bring benefits to the Romanian people, 46% of whom live in rural areas.

Also, in both countries existing a lack of of qualified health personnel, as a result of international migration which is mainly driven by economic and job-related reasons, from sending citizen of south east countries preferentially to west Europe. This is especially pronounced in Serbia, from which more and more people are leaving, as well as an increasing number of highly educated population.

Therefore, use of electronic information and communication technologies for providing health care when the participants are physically remote, regardless of their geographic location, have great potential to improve public health in both countries.

## Related programmes and other donor activities

The project is financed by Cross-border Cooperation Programme INTERREG IPA CBC Romania – Serbia Programme, the Priority Axis 1: Employment promotion and basic services strengthening for an inclusive growth. The aim of the project complies with the Programme Priority specific objective 1.2: To enhance the potential of the programme area for an inclusive growth, based on the improvement of quality of life to all residents on the two sides of the border through joint cross border actions for the access to modern and efficient health care services, social services, services supporting access to primary education.

- This Project is in agreement with European and national trends. It will create a collaborative environment where participants included in the project will show the ability to achieve national and international competitiveness of the cross-border region.

Today, in Europe, more and more initiatives are launched at national, regional or local level to enable health professionals to access the medical and medication history of their patients at any time and any place. This access is however often limited by various barriers. European citizens have become more mobile; they travel and work abroad and when they need healthcare away from home it should be delivered based on knowledge of the past medical history.

Member States have taken important steps towards a collaborative approach for resolving this cross-borders issue; the European Commission is supporting such collaboration initiatives through both its policy initiatives and funding instruments. Currently, through the Competitiveness and Innovation Framework Programme (CIP), the European Commission is co-funding two collaboration actions aiming at moving forward the agenda for interoperable cross border eHealth: epSOS, a Large Scale Pilot, and CALLIOPE, a European Thematic Network. Both initiatives are joining their forces in a strategic complementary approach:

- epSOS (Smart Open Services for European Patients) is developing interoperable Patient Summaries and ePrescription services to be piloted within the three years life time of the project; a long term perspective is guaranteed by the commitment of the participating Member States, and

- CALLIOPE (Call for Interoperability) is supporting this process by providing a European platform for open dialogue and strategic collaborations with relevant stakeholders to further advance the development of interoperable eHealth services and facilitate their adoption.

These projects are working in close collaboration with the eHEALTH INTEROP project launched by three European Standardisation organisations (CEN, CENELEC and ETSI) with the support of the European Commission with the view to enable the market to deliver interoperable solutions.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

“Improvement of quality of life in border region through medical prevention in neurology and psychiatry.”

Through this project, cooperation of medical experts in the fields of neurology and psychiatry at the level of theory and research, using a e-Health platform will lead to a significant reduction in neurological diseases and thus greatly contribute to a better and productive life in the border region.

## Purpose

The purpose of this contract is as follows:

To arrange for services of external experts who will develop multilingual specialized software for image/data transfer related to telemedicine.

The system should be based on central server located in General Hospital "Sveti Luka”, Psychiatry Department, Smederevo. The basic postulate of the system should be interoperability and the possibility of exchanging data between different sources and types of information. This should be achieved by using the web service, with clearly defined data structures and types.The entire system should be patient-oriented, which entails that all the data exchanged is related to a specific patient

## Results to be achieved by the Contractor

## Result 1: Developed e-Health platform

## Result 2: Installation of application in partners institution

## Result 3: Establishing a communication with 10 health institution

## Result 4: Organization of staff training sessions in partners institutions,

## Result 5: Organization of  three workshops

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

## Availability of financial resources the project needs;

## Staff responsible, competent and motivated;

## The persons involved in project management maintain regular and  continuous communication within the partnership and with the Programme authorities.

## Risks

Risks to the project in question can be structured in following categories of risks: technical risks and financial risks.

# Technical risks:

# The risk of an unexpected event during project implementation, an event leading to the impossibility of meeting its estimated costs and time;

# The risk that resources needed for the investment cost more than expected;

During the procurement of professional services the desired quality and contents of implementation can be guaranteed by the accurate definition of the expected fulfilment and by ensuring that the service provider has the required professional experience.

# Financial risks:

# The amount of service and operating costs are understated;

# The real value of payments over time is diminished by inflation.

# Pre-financing the project also emerges as risk, but members of the partnership have the sufficient funds to eliminate such a risk

# SCOPE OF THE WORK

## General

### Description of the assignment

The purpose of this contract is to arrange services of external experts who will develop e-Health platform - an application software for image/data transfer related to telemedicine. In developing e-health, healthcare institutions are given an opportunity to improve the quality of their services through the use of advanced electronic systems.

Availability of high performance telemedicine systems has been for a long time a goal for most health institutions. This technological advancement is considered a fundamental asset for those institutions with interest in dissemination of their expertise but also as a way to continuously keep their professionals updated on the most novel techniques. Also, second opinion type of services as well as distantly located collaborative activities in between different medical disciplines may also benefit of this technological solutions.

By the end of the project, General Hospital “Sveti Luka", Smederevo, Hospital for Psychiatric diseases “dr Siavoljub Bakalovic”, Vrsac and in University Victor Babes in Timisoara will be able to communicate between each other and with health care institutions across Europe. Preventive measures, better diagnostic, faster reaction and consultations with experts all over the world will be enabled through this platform.

### Geographical area to be covered

The project cross-border area is composed from Timisoara - Timis County (Romania), South Banat District and Podunavski District – Serbian partner locations.

### Target groups

- Medical organizations, experts, workers in border region

New protocols, technics and approaches developed during implementation of the project “Improved health care in neurology and psychiatry – longer life” will be used after the life-time of the project in all three partners institutions. However, one of the project activities will be promotion of the project results to the other similar institutions, not just in the border area, but wide across Romania and Serbia. e-Health platform will cover an area of permanent interaction between medical professionals, institutions and organizations among which there are actions of medical preventing, diagnosis, monitoring, education. The technological and informatics support includes physical networks, medical apparatus portable devices, personal monitors, databases in which information about acute and chronic patients are stocked and accessed, electronic files and records, centralized electronic medical information. By using of cooperation e-Health platform, even more health experts could be involved in the project. The patient is the final winner when medical professionals can access information in the most practical way.

## Specific work

During the implementation of project “Improved health care in neurology and psychiatry – longer life”, the Contractor is expected to provide expert services for the development of the Cooperation e-Health platform..

## The Contractor’s responsibility include the following tasks:

- Activity 1:	Development of specialized software for image/data transfer in medicine:

I.1 Description of system operation:

- Primary health care providers send medical images in digital format, together with textual data and a request for a consultation, to the central servers using the Internet.

- The web services on the central servers receive data, archive it, and send appropriate notification  about the arrival of a new request for a consultation to the chosen consultant or the referent institution.

- The referent institution or consultant chosen receives the new requests for consultations.

- The requested consultant connects to the appropriate server and the patient data together with the diagnostic question and the medical images will be available for him/her. That is, all the relevant data will be downloaded to the consultant's computer independently from his or her location.

- It should be possible to send the relevant data to the requested consultant’s computer independently of his/her actual presence.

- On the basis of the received information, the consultant forms his/her opinion and a report. The report is then transferred through the web service to the initiating central server, which automatically notifies the sender of the request for a consultation, and forwards the report to the sender.

I.2 Secure remote connection with other institutions (VPN architecture)

System must to fulfill the following requirements:

- Secure remote study access: beneficiaries (health units and consultants) access the system via a VPN (Virtual Private Network) by using a username and a password

- Study storage allowed on archiving systems of other institutions

- Web server configuration to achive bidirectional communication in the exchange of DICOM data

- Information encryption configuration to protect patient data

- Exchange of radiological reports with other institutions allowed

- Settings up software to automatically copy all the exams to the archieves of other institutions

- Appropriate Data Encryption Standard

- Appropriate network security system

I.3 Services of configuration and connection

Configuration and connection of the system to three locations, to enable the following:

- The system should enable the HL7 connection to the existing or to be developed HIS/RIS systems

- The administrative user interface used by system administrators and  the language of the crossbred consultation should be English

- The central healthcare institution server shell allow satellite facilities to send medical studies and text data in digital format, as well as consultation request through Internet

- Configuration of a VPN tunnel between hardware and devices i.e. healthcare institutions

- Configuration of the server software to allow data exchange between healthcare institutions

- After receiving the consultation request, the central server healthcare institution server should be able to send a notification on the receipt of the application to the consultants both by email and&or SMS

- The consultatnt shell be able to connect to the server and download medical studies and other relevant medical data to their computer

- During the diagnosis, the consultant creates a radiological report. The consultant shell be able to send such report to the central server that automaticaly notifies and forwards the report to the consultant request sender

- The system shell allows user to ask questions related to medical studies

- The system shell enable the medical consultant to provide written or audio response to the request sender/user

I.4 Accessories – software

Software for radiological workstations (unlimited number of licences):

- Software for diagnostic – min. 3D, vessel tracking analysis, PET/CT fusion analysis form different modalities (min. CT, MR, CR, DR, PET CT, US, XA,EKG)

- The viewing application should be designed according to the needs of the telemedicine applications, which means that downloading images should be driven by the user's activity. The basic features should be:

- Window/leveling

- Measurement tools (calculation of diameter change allowed through studies of different dates of the same patient)

- Use of bookmarks allowed  - recorded  i.e. marked anatomical 2D or 3D locations with comments

- Opening multiple studies

- Viewing the images in actual size

- Stitching Images

- Statistical tool for measuring volumes of interest

- The viewing utility should be available in three languages (English, Romanian, Serbian)

- Ability to remember marked change diameters and ability to display them at each subsequent study load

- Automatic generation a special series/group of pictures made up of key messages

- Support for displaying and importing data that does not confirm to the DICOM standard (min. jpeg, avi, pdf, doc files)

- Automatic alligment allowed as well as synchronus view of study slices in comparasion by all three levels (transversal, frontal, sagittal) as well as between different modalities (CT, MRI)

- Activity 2:	Installation of the application software:

Relating to this activity, the Contractor will be required to:

Install and activate the above described application software in the following health institutions:

1. General Hospital “Sveti Luka", Psychiatry Department, Smederevo

2. Special Hospital for Psychiatric diseases “Dr Slavoljub Bakalovic", Vrsac

3. University Victor Babes,Timisoara

The Contractor should provide a description of the technical and financial conditions under which they will be able to increase the size of the storage capacity and the number of participating institutions in the future in order to provide the Contracting Authority with an outline for future planning of network expansion.

In order to guarantee the reliable and long-term operation of the e-Health platform, Contractor need to deliver and install following hardware to three partners institution:

- high-performance server (hardware) on which the application will be installed with min:

- 20 GBRAM

- Intel CPU or appropriate, 3.0 GHz, 8 cores

- RAID 1, RAID 5 and/or RAID 6 configuration

- 8x 6TB HDD

- SAS or FC connection with the storage system

- redundant power supply

- redundant fans

- with licenced operating system

- redundant connection between server and storage system

- appropriate antivirus software for server operating system

- UPS – Uninterrupptible power supply for min 15 minutes of autonomous server operation

- appropriate server rack

(3 pieces, one per institution)

- Storage systems for backing up medical images with min:

- 8 HDD trays

- redundant power supply

- SAS or FC connection with server

- Following RAID options: RAID 0,1,5,6, HOT spare

- 8x 6TB HDD for back up of medical images

- UPS – Uninterrupptible power supply for min 15 minutes of autonomous operation

(3 pieces, one per institution)

- Appropriate graphics card with color monitor to use for diagnostic purposes (brightness: min 350 cd/m2)

(6 pieces, two per institution)

- Activity 3:	Organization  staff training sessions on all three locations upon system installation

In order to familiarize the local staff with system operation, 2 days staff training sessions will have to be provided on each location: Smederevo, Timisoara and Vrsac by the Contractor at the time of the installation. The training sessions should be introductory, since more detailed training will be provided in workshops organized for this purpose. Additionally to providing on-site training, it will be expected that the Contractor will provide over-the-distance support if needed for additional questions and inquiries from local staff.

Since the installation on different locations will be completed at different timeframes, it is essential that the Contractor works closely with IT experts from all health institutions in order to determine the dynamics of system installation appropriately.

- Activity 4:	Organization of workshops

In order to provide the staff and medical experts of health units included in the telediagnostic network with sufficient knowledge on system operation, the Contractor is required to provide a complete training program and material for three 3-day workshops for min. 50 participants.

The first 3-day workshop will be organized in Smederevo upon the installation of application software in General Hospital "Sveti Luka", while the second 3-day workshop will be organized in Vrsac upon installation of application software in Special Hospital for Psychiatric diseases “Dr Slavoljub Bakalovic'. Third 3-day workshop will be organized in Timisoara upon the installation of application software in Victor Babes University.

For each workshop technical conditions:venue, translation, technical equipmentas well as accommodation, catering, travel, and workshop organizationtasks will be provided by the Contractor. Each workshop will be attended by participants from both sides of the border. The Contractor will be required to arrange experts who will implement the presentations during the workshops and prepare professional level training for the participants.

The training material will have to be provided to all participants in an electronic form either via email or a website where participants can access it quickly and easily. The User manuals will have to be provided in all three languages by the Contractor: English, Romanian and Serbian and they should also be accessible in an electronic format via the internet.

The English and Serbian version of the User manuals will have to be provided by the first workshop organized in Serbia, while the Romanian version of the manual will have to be provided the latest by the second workshop that will be organized in Romania. Since the training material will be printed separately, it is also expected from the Contractor to submit the training material one week before the workshop is organized in order to allow enough time for printing of materials.

## Project management

### Responsible body

The Contracting Authority is General Hospital “Sveti Luka”, Smederevo which is Partner 3 of the project. The Contractor is responsible for all the activities regarding this contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Activity coordinator - Sasa Botic.

### Facilities to be provided by the Contracting Authority and/or other parties

Contracting Authority will provide adequate space for installation of hardware required for application functioning.

# LOGISTICS AND TIMING

## Location

The Republic of Serbia, Smederevo.

## Start date & Period of implementation of tasks

The intended start date is the date of signature of the contract by both parties and the period of implementation of the contract will be 7 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

Any equipment, operating system licenses, certificates related to this contract, which is to be acquired, must be purchased by Contractor.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and one copy:

- Final report at the end of the service shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference”.

## Special requirements

All justificatory documents can be in copy, strongly recommended. The originals must be dispatched to the Contracting Authority upon request.