ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

Municipality of Golubac, Cara Lazara 15, 12223 Golubac, Republic of Serbia

## Country background

Republic of Serbia is Country which is currently preparing for membership of European Union. Number reforms and actions in various spheres of society and state administration are being pursued in order to achieve this goal. Some of this action like Project of which this contract is one part are financed by European Union using specialized funds from various Programmes. Project under which this contract will be funded is Interreg IPA cross border Romania Serbia Programme.

## Current situation in the sector

In the area of civil protection the European Commission and Participating States are taking an integrated approach to disaster management including prevention, preparedness and response. In the area of prevention, the agreed priorities include: the development of knowledge based disaster prevention policies (spreading best practices, developing common guidelines on risk assessment and mapping); and linking the actors and policies throughout the disaster management cycle (developing lessons learnt, reinforcing early warning tools).

## Related programmes and other donor activities

This Project is in agreement with European and national trends. It will create a collaborative environment where participants included in the project will show the ability to achieve national and international competitiveness of the cross-border region

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The overall objective of the project is: Improving the quality of life in the cross border and Danube area by raising the level of safety and awareness among citizens from both sides of the border through an effective emergency situations management and preparedness.

## Purpose

The purpose of this contract as follows:

- Training a group of 12 volunteers for intervention in emergency situations.

## Results to be achieved by the Contractor

- 12 volunteer firefighters are trained examined and certified as well prepared for professional exam for fire protection.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- n/a

## Risks

- n/a

# SCOPE OF THE WORK

## General

### Description of the assignment

Contractor is expected to prepare for 12 volunteers Professional Exam for Fire protection, as well perform all necessary trainings (theoretical, specialist and practical) in order to certify candidates that they passed professional examination of the Law on Fire Protection and that they passed the examination for the profession of volunteer firefighter.

### Geographical area to be covered

Municipality of Golubac/Serbia

### Target groups

Project team, Local Authorities, future volunteer fire fighting unit.

## Specific work

1. Preparation for professional Exam for Fire Protection

Special training and professional examinations in the field of fire protection should be conducted on the basis of Article 55 of the Law on Fire Protection ("Official Gazette of RS",No. 111 / 09, 20 / 15), and persons trained for working on fire prevention tasks are prepared and to take and pass the State Exam.

Special training in the field of fire protection should consists of: general, specialist and practical work.

The training should be conducted by experts with adequate licenses and authorizations in accordance with the subject of training and with use of appropriate teaching aids.

Contractor will prepare Reference Manual necessary for adequate preparation of candidates and it remains as the property of candidates after completion of training, as well as professional literature that will be used in carrying out their daily tasks.

After completion of the classes for the candidates should be organized exam, which is taken under control of the commission of the Ministry of Internal Affairs of Serbia, Sector for Emergency Situations.

After passing the exam, candidates should receive a certificate issued by Ministry of Internal Affairs of Serbia, Sector for Emergency Situations

Curricula should contain material defined by Regulation on preparing candidates for taking a special exam in the field of fire protection that includes at least following:

1 Normative regulation of fire protection

2. Hazardous substances, fire and explosion

3. Preventive fire protection

4. Fire extinguishers

5. Fire fighting devices and equipment

6. Fire fighting tactics

7. The practical part of the special training

2. Practical training and examination for the position of a volunteer firefighter

The offer should include the following:

- Theoretical training and preparing for the exam for the title of a volunteer fireman.

- Practical exercises with firemen (fire-fighting in the woods, technical interventions, cutting cars, access to the fire in the open air and indoors.)

At the end of the training, each candidate should receive two certificates:

1. The certificate on professional examination of the Law on Fire Protection

2. Diploma from Fire fighting association of Serbia that he passed the examination for the profession of volunteer fire-fighter.

Important Notice:

All 12 candidates will have a minimum IV degree of vocational education / secondary school qualifications. They are located in Municipality of Golubac. Contractor is expected to cover all costs required for this service including organization transportation, provision of training venue and training grounds, provision of all required materials, costs of examination, meals and lodgings for candidates if necessary and other (depending on offer). All training sessions and other events related to this service must have participant lists, be photographed and in all aspects in line with the Visibility Manual for Interreg Cross-border IPA program Romania Serbia

http://www.romania-serbia.net/?page_id=212&lang=en_GB

## Project management

### Responsible body

The Contractor is responsible for all the activities regarding this contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Biljana Stevanović Dautbašić, Project Coordinator

### Facilities to be provided by the Contracting Authority and/or other parties

The Contractor shall ensure any other facilities, including the transportation means, necessary for quality and timely implementation of the tasks described in these Terms of Reference.

# LOGISTICS AND TIMING

## Location

Municipality of Golubac, Serbia

## Start date & Period of implementation of tasks

The intended start date is date of signature of contract by both parties and the period of implementation of the contract will be 3 months and 15 days from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Team Leader

Qualifications and skills

- BSc Degree

- Valid licence recognised by legislative system of Serbia for licenses and authorization for the preparation of the Main Fire Protection Project and special systems and fire protection measures.

General professional experience

- 3 years of professional experience fire fighting services

Specific professional experience

- Professional experience related to training of fire-fighters

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original:

- Final report at the end of the service shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Coordinator identified in the contract. The Project Coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference”.

## Special requirements

n/a