ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Serbia

## Contracting Authority

Coka Municipality

## Country background

N/A

## Current situation in the sector

- N/A

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

Project Regional Employment Center has, as a main goal, establishing pre-conditions for employment opportunities in the rural area of cross-border region. Municipality of Coka and Municipality of Deta are similar in number of inhabitant, also they are both rural agricultural area with most population acting in this field. Taking into account that those two municipalities are similar in many ways, it was natural that they have similar problems. All these lead to the joint project proposal and establishment of partnership between these two municipalities. By establishing Regional Employment Center, with offices in both municipalities, we will implement several different sets of trainings in order to provide conditions for new jobs in our municipalities.

## Purpose

The purpose of this contract is as follows:

Organizing of trainings for: Motivational trainings, New IT jobs, Finding jobs in IT industry, SME establishing and management, Traditional wine producing, Traditional bee keeping, Train the Trainers PCM organization

## Results to be achieved by the Contractor

- Motivational trainings delivered

- New IT jobs training delivered

- Finding jobs in IT industry training delivered

- SME establishing and management training delivered

- Traditional wine producing training delivered

- Traditional bee keeping training delivered

- Train the Trainers PCM organization training delivered

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

N/A

## Risks

N/A

# SCOPE OF THE WORK

## General

### Description of the assignment

Project Regional Employment Center has, as a main goal, establishing pre-conditions for employment opportunities in the rural area of cross-border region. Municipality of Coka and Municipality of Deta are similar in number of inhabitant, also they are both rural agricultural area with most population acting in this field. Taking into account that those two municipalities are similar in many ways, it was natural that they have similar problems. All these lead to the joint project proposal and establishment of partnership between these two municipalities. By establishing Regional Employment Center, with offices in both municipalities, we will implement several different sets of trainings in order to provide conditions for new jobs in our municipalities. One of the set of the trainings will be composed with different kind of business trainings: new IT jobs, SME establishing and management, wine producing, bee keeping, PCMU, so as motivational trainings.

### Geographical area to be covered

North Banat, Serbia

### Target groups

- Unemployed youth

- Women in rural areas

- People with special needs

- Elderly people in villages

## Specific work

- The Contract will be last for 6 months. The Contractor is obliged to organize the following trainings under this Contract:

- Motivational trainings

- New IT jobs training

- Finding jobs in IT industry training

- SME establishing and management training

- Traditional wine producing training

- Traditional bee keeping training

- Train the Trainers PCM organization training

- Detailed description of activities:

- 1. Motivational training

Motivational training contains:

2 motivational seminars will help participants to develop self-confidence, feel that they are strong enough for new challenges, that they can truly contribute to the quality of life of their own and their families.

| Duration | Number of training days | Training days per month |
| --- | --- | --- |
| 1 month | 2 training days | 2 training days per month |

- It should start at most one week after the contract signing. One expert is necessary. For each training session, the Contractor should provide: list of participants, photos and evaluation.

- The Contracting Authority is obliged to provide: premises for trainings, necessary equipment, so as participants.

- 2. New IT jobs training

New IT jobs training contain:

- 12 training days in Business development by using blog

- 12 training days in Business development by using vlog

- 12 training days in Business development by using YouTube

- 3 extra months of online mentoring for each topic

| Duration | Number of training days | Training days per week |
| --- | --- | --- |
| 3 months | 36 training days | 3 trainings per week |

- Trainings should be delivered in Čoka. One expert is necessary. For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

- The Contracting Authority is obliged to provide: premises for trainings, necessary equipment, so as participants.

- 3. Finding jobs in IT industry

Finding jobs in IT industry training contains:

- 4 training days in How to find job in IT industry (designing of portfolio, presentation to potential employers, branding one’s self, promoting on professional’s online platforms, social networks presentations, etc)

| Duration | Number of training days | Training days per week |
| --- | --- | --- |
| 1 month | 4 training days | 1 training per week |

- Trainings should be delivered in Čoka. One expert is necessary. For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

- The Contracting Authority is obliged to provide: premises for trainings, necessary equipment, so as participants.

- 4. SME establishing and management training

SME establishing training contains:

- 1 training day in: Legal basis for SME establishing

- 1 training day in: Procedures for SME establishing

- 1 training day in: Marketing in SME

- 1 training day in: Management of SME

| Duration | Number of training days | Training days per week |
| --- | --- | --- |
| 1 month | 4 training days | 1 training per week |

- Trainings should be delivered in Čoka. One expert is necessary. For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

- The Contracting Authority is obliged to provide: premises for trainings, necessary equipment, so as participants.

- 5. Traditional wine producing training

Trainings for traditional wine producing contain:

- 24 training days in traditional wine producing based on tradition of grape and wine producing in Čoka municipality

| Duration | Number of training days | Training days per week |
| --- | --- | --- |
| 2 months | 24 training days | 3 training days per week |

- Trainings should be delivered in Čoka. One expert is necessary. For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

The Contracting Authority is obliged to provide: premises for trainings, necessary equipment, so as participants.

- 6. Traditional bee keeping training

Trainings for traditional bee keeping contain:

- 24 training days in traditional bee keeping based on tradition of bee keeping and honey production in Čoka municipality

| Duration | Number of training days | Training days per week |
| --- | --- | --- |
| 2 months | 24 training days | 3 training days per week |

- Trainings should be delivered in Čoka. One expert is necessary. For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

The Contracting Authority is obliged to provide: premises for trainings, necessary equipment, so as participants.

7. Train the Trainers PCM organization training delivered

Train the Trainers PCM organization contain:

- 10 training days in providing participants with not only the practical instructional design skills, platform techniques and confidence they need, but also with critical skills to facilitate learning and ensure retention.

| Duration | Number of training days | Training days per month |
| --- | --- | --- |
| 1 month | 10 training days | 10 training days per month |

- Trainings should be delivered in Čoka. One expert is necessary. For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

The Contracting Authority is obliged to provide: premises for trainings, necessary equipment, so as participants.

## Project management

### Responsible body

The Project team members, led by Project Manager is responsible for managing this Contract on behalf of the Contracting Authority

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Mr Zoran Jovanov.

### Facilities to be provided by the Contracting Authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

Coka Municipality, North Banat, Serbia

## Start date & Period of implementation of tasks

The intended start date is the date of signing Contract by both parties and the period of implementation of the contract will be 6 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key expert 1: Expert in SME establishing and management, Team leader

Qualifications and skills

Minimum High school degree; University degree in Economy, Business, Law, Entrepreneurship or equivalent will be an asset

General professional experience

Minimum 3 years of practical experience in SME management

Specific professional experience

Minimum 1 year experience in SME management teaching or training delivery or mentoring; or involvement in at least 1 project in a position of business/SME trainer.

Key expert 2: Motivational speaker

Qualifications and skills

University degree in Psychology, or Sociology, or Philosophy, or Certificate in Life skills education, or equivalent

General professional experience

Minimum 3 years of practical experience in motivational speaking, or life couching, or life quality advising, or equivalent

Specific professional experience

Minimum 1 contract in motivational speaking

Key expert 3: Expert in social media marketing

Qualifications and skills

Minimum High school degree; University degree in IT, or Technical science, or Political science, or Organisational science, or equivalent will be an asset

General professional experience

Minimum 3 years of practical experience in social media marketing/management, or blogging, or Youtube channel management

Specific professional experience

Minimum 1 contract in social media marketing training

Key expert 4: Expert in wine producing

Qualifications and skills

Minimum High school degree; University degree in Agriculture, or Technology science, or equivalent will be an asset

General professional experience

Minimum 3 years of practical experience in wine producing

Specific professional experience

Minimum 1 contract in wine producing training

Key expert 5: Expert in bee keeping

Qualifications and skills

Minimum High school degree; University degree in Agriculture, or Technology science, or equivalent will be an asset

General professional experience

Minimum 3 years of practical experience in bee keeping and honey producing

Specific professional experience

Minimum 1 contract in bee keeping and honey producing training

Key expert 6: Trainer in PCM

Qualifications and skills

Minimum High school degree; University degree in Management, or Organisational science, or Political science, or Economy, or Law, or equivalent will be an asset

General professional experience

Minimum 3 years of practical experience in PCM

Specific professional experience

Minimum 1 contract in PCM training

### Other experts, support staff & backstopping

Contractor should provide supporting staff for administrating of this Contract.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language in one original:

- 1 Interim report should be prepared at the end of the 3rd month of the implementation of the Contract. The report should be done in English, in one original. It should contain detailed information about services implemented in that period.

- Final report should be prepared at the end of the Contract. The report should be done in English, in one original. It should contain detailed information about services implemented in that period, so as the whole Contract.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality and quantity manor, as required in these Terms of Reference.

## Special requirements

N/A