ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

Public Water Management Company “Vode Vojvodine”, Bulevar Mihajla Pupina 25, 21000 Novi Sad, Republic of Serbia

## Country background

Serbia is faced with similar challenges that are also present in the Programme area of the -border Cooperation Programme INTERREG IPA CBC Romania – Serbia Programme:

- The Bega Canal is from more points of view one of the key linkers of Romanian and Serbian Communities. It links two major cities Timisoara and Zrenjanin.

Timisoara is the capital city of Timis County, in Western Romania. One of the largest Romanian cities (the third most populous city in the country starting from 2011), with a population of 319,279 inhabitants. It is the main social, economic and cultural center in the western part of Romania.

Zrenjanin is the administrative center of the Central Banat District. In 2002 the city’s population reached 79,773 inhabitants, while Zrenjanin area was populated by 132,051 inhabitants. Zrenjanin is the biggest Serbian Banat town, the third biggest town in Vojvodina and the sixth town in Serbia.

They are located in the Banat region which is geographically referred to as a part of the Pannonian Basin bordered by the River Danube to the south, the River Tisa to the west, the River Mureș to the north, and the Southern Carpathian Mountains to the east.

Bega River has a total length of 240 km, of which 178 km on Romanian territory and 76 km on Serbian territory. It springs in the Poiana Rusca mountains to the northeast of Timisoara, part of the Carpathian Mountains, and it flows into the Tisa in Serbia and thereafter into the Danube.

The Bega Canal is located in the West part of Timis County and it is one of the few artificial waterways in Romania. The Bega Canal has a total length of 120km, of which 45km on Romanian territory and was the first navigable Canal built in the country. The navigable part of the Bega Channel starts in Timisoara, then flows to Southwest, crosses the Romanian Serbian border and continues 75km in Southwest direction to the river Tisa. In the Serbian territory, the Bega Canal crosses the middle Banat region and Zrenjanin and Žitište cities.  The Bega Canal could be considered a living boulevard between the two countries.

Within the Cross-border Cooperation Programme INTERREG IPA CBC Romania – Serbia Programme’s First Call for Strategic Projects, under Priority Axis 3: Sustainable mobility and accessibility, Public Water Management Company “Vode Vojvodine” (SRB) - Partner 4, in partnership with Lead Partner: Banat River Basin Administration (RO) – Partner 1, Timis County Council Timisoara, Romania (RO) - Partner 2 and Provincial Secretariat for Regional Development, Interregional Cooperation and Local Self-Government (SRB) – Partner 3, submitted the project ”The Repairing of the navigation infrastructure on Bega Canal”.

The project is consistent with the Programme strategy by implementing an overarching objective that includes joint cross-border actions by Romanian and Serbian stakeholders to achieve a more balanced and sustainable socio-economic development and inclusive growth of the Romanian-Serbian border area.

The project initiatives are aimed to revitalize the Bega Canal, both in terms of infrastructure and construction of a specific framework meant to lead to a sustainable development of the tourism attractions, create new jobs and attract foreign tourists.

The aim of the project complies with the Programme Priority specific objective 3.1 – Mobility and transport infrastructures and services:

“Promote the achievement of improved quality standard in public transport and mobility services in the eligible area across the border and the integration in the main EU transport corridors, complying to EU Environmental legislation and sustainability principles, especially in remote and disadvantaged areas”.

This project requires a strong cooperation between Romanian and Serbian partners. We want that Bega canal become a navigable one like in old times, and for this, the cooperation with Serbia is very important. The challenges set cannot be efficiently resolved acting only at national/regional/local level because the Bega canal links the two big cities of this two countries, Timisoara and Zrenjanin. Consequently, better transport links will strengthen intra region cooperation and activities (increase of passenger travel and contact among communities, tourism promotion) thus promoting socio economic development and increase of the region’s competitiveness, contributing to the improvement of the population’s life quality.

## Current situation in the sector

The IPA funds facilitate the economic growth and social cohesion in the cross border area.

The Romania-Serbia border is 546 km long, with the River Danube forming a natural frontier for approximately 230 km of this length. According to the 2011 census, a population of roughly 2.4 million lives in the eligible area, that represents roughly 9% of the total combined national populations of Romania and Republic of Serbia. Of the 2.335 million people who live in the border area, 1.36 million live in Romania, and 1.035 million live in Serbia.  Thus, within the border area, 56% of the population is living in Romania, and 44% is living in Serbia.

Lack of development of transport, of investment in infrastructure, (which is at the moment, poorly maintained and not in line with EU standards) and purchase of equipment for ports and water related mobility, tourism facilities, present a constrained upon development of the region.

Lack of transport connections has proven to be a huge obstacle in developing tourism, mobility from one location to the other, new businesses, ecotourism, potentials of bordering municipalities of Timisoara and Zrenjanin.

Currently, within Timisoara city limits, with the exception of several small and leisure boats, only the dredges of Banat River Administration are moving on the Canal, with the purpose of cleaning it. Depending on the short and mid term development of the volume of cargo transport along the canal, it can be enlarged to accomodate ships with a transport capacity of 1,000 tons or more. The navigation facilities (docks, loading sites etc …)  along the canal are small, derelict and need to be modernized. There are no markings in the canal and the km – signaling along the canal is mostly missing or hidden behind the vegetation. The turning basins for the boats are too small and need to be deepened.

When transport systems are efficient, they provide economic and social opportunities and benefits that result in positive multipliers effects such as better accessibility to one place to another and additional investments. When transport systems are deficient in terms of capacity or reliability, they can have an economic cost such as reduced or missed opportunities. Transport also carries an important social and environmental load, which cannot be neglected.

Also, consideration was given to the idea of connecting, in the future, Timisoara to the navigation system Rhine-Main-Danube, which connects the North Sea with the Black Sea. In order to reopen the navigation on the Bega Canal and to boost the tourism in the area, there are some measures to be taken and it can be an important common challenge and an opportunity to develop the region.

Another common challenge and opportunity to develop the mobility of people and the tourism potential in the programme area is to continue the working inspection/bicycle path which is already built on the Romanian side up to the Serbian border. The project official name is: “Improving the Cross Border Tourism demand including cycling path among the Bega River downstream Timisoara” with Banat River Basin Administration as lead beneficiary. The cycling tracks along the Bega river, downstream of Timisoara  is 40 km in length, is arranged on the pier/floating dock and mooring point and has a width of two meters throughout the river  on both sides, it started near the Bridge Modoș route: Splaiul Sophocles – Freidorf Industrial Park – Utvin – Uivar – Otelec. Within this project on the Serbian side was made only the feasibility study for the cycle tracks so, it will be a big opportunity that through this project it will be build the cycling tracks up to Zrenjanin. The bicycle track will be a strong asset in tourism development as long as the communities will (further) diversify their hospitality offer.

Making alternative transport infrastructure for recreation and leisure in the cross border area is essential for balanced economic and social development and for promotion of tourism and cultural exchanges. Leisure and recreation tourism on short distances is an alternative for classic tourism, with great contributions in reducing pollution and raising the level of satisfaction of population.

The main common challenge of the project is to improve the general accessibility and mobility of people and goods through Repairing of Bega Canal. Mobility is one of the most fundamental and important characteristics of economic activity, as it satisfies the basic need of going from one location to the other, a need shared by passengers, freight and information. This project aims to continue the steps that have been taken so far by implementing the above mentioned project through the Repairing of the hydrotechnical complex Sanmihaiul Roman, Klek and Srpski Srpski Itebej, the construction of working inspection/bicycle path, technical documentation for dredging Begej Canal, providing equipment for dredging and maintaining Begej Canal, wider opportunities for trade and economic cooperation will emerge. It will also result in motivation, creation and development of corresponding transport links on both sides of the border as well as promote good neighborliness and cooperation between Romania and Serbia.

But, we don’t have to forget that also, these two countries, face with the problem of a significant number of flooding. Flood issue is best addressed by common effort. Thus, the works that will be done on both the Romanian and Serbian side will have a positive impact on the environment and Bega river ecosystem and human communities in the area by reducing/eliminating the risk of flooding in the first place but also by creating conditions for transport and maintenance of the Canal.

The environmental aspects regarding the Bega Canal have been analyzed in a series of studies, which all underline the advanced state of pollution. Surface water are becoming increasingly polluted due to anthropogenic factors such as industry, wastewater discharge and waste water, wastes and chemicals, but it’s also due to natural factors such  as floods, like we have mentioned above.

Taking into account its historic heritage and tourism potential, the local responsible actors and authorities have started to jointly analyze and agree upon some steps necessary for the revitalization of the Channel area. One of these steps was made by ADETIM with RDA Banat partners, by developing a feasibility study for the revitalization of Bega Canal through the project named:  “Joint development of Romanian - Serbian Bega Channel tourism potential capitalization Study and promotion of cross - border foreground investments”.

Cross-border cooperation is needed also because this two countries have already signed a partnership agreement and they have consented the works to be performed through the documents that were made in the previous project mentioned above (Bega Channel Development Strategic Programme in the cross-border cooperation area Romania-Serbia and the feasibility study for “Joint development of Romanian-Serbian channel tourism potential capitalization study and promotion of cross-border foreground investments” Developing the technical and economic study on the Repairing and development of the shipping and port infrastructure of the Bega channel on the route Timisoara - border with the Republic of Serbia for the use and development of joint tourism potential.)

Taking into account the above mentioned and the proposed investments to achieve through this project is necessary a common collaboration formula in order to develop a sustainable accessibility and mobility transport, economic and touristic development of the region.

”The Repairing of the navigation infrastructure on Bega Canal” project is consistent with the Programme strategy by implementing an overarching objective that includes joint cross-border actions by Romanian and Serbian stakeholders to achieve a more balanced and sustainable socio-economic development and inclusive growth of the Romanian-Serbian border area.

## Related programmes and other donor activities

The project is financed by Cross-border Cooperation Programme INTERREG IPA CBC Romania – Serbia Programme, the Priority Axis 3: Sustainable mobility and accessibility. The aim of the project complies with the Programme Priority specific objective 3.1 – Mobility and transport infrastructures and services:

“Promote the achievement of improved quality standard in public transport and mobility services in the eligible area across the border and the integration in the main EU transport corridors, complying to EU Environmental legislation and sustainability principles, especially in remote and disadvantaged areas”.

Related project and programmes have been implemented in the region in previous years, since the quality standard in public transport and mobility services, including the repair and maintenance of waterways remains a high priority for both countries. Some relevant projects implemented in the region of Vojvodina and Timis County:

The proposed project is a continuation of projects that have already been implemented under the Romania-Serbia IPA CBC Programme 2007-2013 by local authorities. Furthermore there is previous experience of cooperation between the partners involved in this project.

The first one and the most important project is: “Joint development of Romanian - Serbian Bega Channel tourism potential capitalization Study and promotion of cross - border foreground investments” was implemented  through Romania – Republic of Serbia IPA CBC Programme, MIS ETC 1358, by ADETIM with RDA  Banat partners and started performing current project by making a “Tehnico-economical study regarding Repairing and development of the navigation and infrastructure for Bega canal on the river reach Timisoara – border point with Republic of Serbia in order to capitalize and develop a common touristic potential”.

To this end, project partnership alongside all relevant institutions have defined strategic directions and priorities in order to revitalize the Bega Canal and improve touristic potentials and offer in cross-border area. The common tourism development strategy of Romanian – Serbian Bega Canal area formulation provides coordinating support mechanisms for tourism, local and regional organizations and agencies by creating the proper framework for debating and reaching agreement on joint projects, joint business opportunities and even joint leisure activities, under its specific strategic vision: ”By 2030, Bega Canal is an internationally recognized tourism destination known for outstanding experience in boating, sports and leisure, different cultures, integrated communities and protected nature” Slogan: „Just feeling good”.

The second project that can be considered in synergies with the current one is “Improving the Cross Border Tourism demand including cycling path among the Bega River downstream Timisoara” was implemented through Romania – Republic of Serbia IPA CBC Programme. Within this project was built, on the Romanian side, the cycling path whose lengths is 40 km and on the Serbian side, our partners have done the feasibility study for their part of working inspection/ bicycle path.

It can be a big opportunity that through this (new) project it can built their part of cycling trail that can be beneficial for the connection of the main important cities of this two countries. The construction of this cycling trail will contribute to the specific objective of the programme by developing the transport infrastructures, by promoting the mobility with bicycle which represents an alternative mode of travel, healthier for the population of the region.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

“Promoting cross – border sustainable transport and mobility infrastructure improvement for the shaping of Bega Canal area as an internationally recognized destination for outstanding tourism experience, diverse cultures, integrated communities and protected nature.”

## Purpose

The purposes of  the contract are as follows:

- To provide supervision of the works on hydro-complexes Klek and Srpski Itebej; construction works of service/cycling path; development of the left bank of the Navigable Begej Canal and installation of floating facility-dock in Zrenjanin for the project BEGA;

- To provide adequate technical assistance and advice to the Contracting Authority, in terms of quality assurance regarding implementation of the works contract;

- Issuing provisional and final acceptance certificates for construction works;

- Monitoring of the executed works during their Defects Liability Period;

## Results to be achieved by the Contractor

The results to be achieved under this contract are as follows:

- Supervision for Works Contract

- Provide sufficient, qualified and experienced staff to ensure proper supervision of the works during the Construction and Defects Liability period.

- Control of all contractual documentation available (insurances, guarantees, permits, etc);

- Design Review and approval - review the Works Contractor’s design for execution according to RS law (“PZI” as per Construction and Planning Law), working drawings.

- Smooth project implementation system in place including quality assurance system;

- All risks in terms of potential quality problems, delays or budget overruns shall be timely identified and professionally managed;

- Supervision of works carried out, all relevant documentation completed in accordance with the Works contract and relevant RS laws;

- Advise on any claims or contractual problems arising during the works, indicate potential delays and prevent the claims whenever possible;

- Verify "as build-drawings" and deliver to the Contracting Authority all reports, records, certificates and addenda prepared by the Contractor upon works completion.

- Carry out final inspection and prepare Provisional acceptance certificate and other documents corresponding to the Conditions of Works Contract demands;

- All documentation prepared for further and legal administrative actions of the Beneficiary, (Technical Acceptance, Utility Permit, etc), regarding the Serbian laws and the role of Checking and Supervising Engineers fulfilled;

- Ensure that the Works Contractor fulfils his contractual obligations during the DLP, including rectifying all defects in the works in a timely manner

- Inspect the site during the DLP Notify and instruct the Works Contractor accordingly of all defects found;

- Final Inspection on expiry of the DLP in the presence of a representative from the Works Contractor and the Contracting Authority and prior to issuing Final Acceptance Certificate;

- All required technical and administrative reports to the Contracting Authority prepared in time.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- For all promotional activities and event organization, the Contractor must be informed about promotional requirements of EU funded projects in order to comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en.

## Risks

- Continuous and close cooperation with the Contracting Authority should be respected during contract implementation in order to avoid possible issues resulting from miscommunication regarding the promotional goals or event objectives of project BEGA.

# SCOPE OF THE WORK

## General

### Description of the assignment

- The Contractor shall assist to the Contracting Authority in efficient and effective supervision of works on hydro-complexes Klek and Srpski Itebej; construction works of service/cycling path; works on floating dock in Zrenjanin for the project BEGA in accordance with the PRAG conditions of works contract, Contract documents and in line with the valid Serbian legal basis, resulting in the issuing of the Provisional Acceptance Certificate when the works are substantially completed, and the Final Acceptance Certificate at the end of the Defects Liability Period.

All of this is required to be achieved within the quality, budget and timing stipulated in the Works contract and in line with the relevant Serbian legislation.

Obligations of the Supervision body in the procedure of control over the execution of works on:

-  reparation of facilities in Klek and S. Itebej,

-  construction shared-use path along the Bega canal from the border ,

between Romania and Serbia to the village of Klek and

-  regulation of the Navigable Bega canal bank and installation of a floating dock.

Expert/professional supervision is carried out over the all works that are performed.

Expert/professional supervision must be conducted in accordance with:

- Article 153 of the LAW ON PLANNING AND CONSTRUCTION ("Official Gazette of the  Republic of Serbia", no. 72/2009, 81/2009 - corr., 64/2010 - decision of the Constitutional Court, 24/2011, 121/2012, 42/2013 - decision of the Constitutional Court, 50/2013 – decision of the Constitutional Court, 98/2013 - decision of the Constitutional Court, 132/2014 and 145/2014)  and

- RULES ON THE CONTENTS AND MANNER OF EXPERT/PROFESSIONAL SUPERVISION CONDUCTING ("Official Gazette of the Republic of Serbia", no. 22/2015 and 24/2017).

Expert/professional supervision activities refer to:

1) Preparatory works;

2) Construction and building-craft works;

3) Mounting of installations/wiring, plants and equipment (mechanical and electrical engineering works);

4) Other works carried out during building of structures.

The works that are subject to expert/professional supervision are comprehensive and multidisciplinary. Below are the most important activities that are subject to expert/professional supervision and are performed within the works on:

-  repair of facilities in Klek and S.Itebej,

-  construction  shared-use path along the Bega canal from the border between Romania

and Serbia to the village of Klek, and

-  regulation of the Navigable Bega canal bank and installation of a floating dock.

1. THE HYDROTECHNICAL COMPLEX KLEK

1.1. FACILITIES (Technical building and Workshop)

Supervision and quality control of executing of:

• CONSTRUCTION WORKS:

- Roof repairing,

- Complete construction of the floor,

- Vertical and horizontal water insulation,

- The treatment of interior walls,

- The complete replacement of the existing plumbing and drainage installation,

- Completely redesigned sanitary blocks.

• ELECTRICAL WORKS:

- Newly designed electrical installations:

o Building power supply,

o Distribution cabinets,

o Electrical installations,

o Protection against electric shock and lightning protection of facilities,

o Distribution of electrical installations,

o Anti-burglary system.

1.2. SHIP LOCK AND FLOODGATE

Checking and testing the quality of execution of all types of works on repair of the ship lock and floodgate includes the following groups of works:

•	CONSTRUCTION WORKS

- Preparatory works,

- Disassembly and demolition works,

- Earthworks including construction of access roads and handling platforms,

- Concrete works,

- Masonry works,

- Reinforcing steel works,

- Insulation works,

- Carpentry,

- Metalwork.

•	ELECTRICAL WORKS

- Lighting of ship lock and floodgate:

o Lights,

o Light poles,

o Power supply cables.

- Marking of waterways:

o Traffic lights,

o Traffic lights pole,

o Power supply cables.

- Revision of the pole-mounted substation STS 10 / 0.4 kV / kV, 50 kVA.

•	MECHANICAL WORKS:

The works include the manufacturing of parts, replacement/repairing of the following equipment parts:

- Mitre gates with a driving mechanism,

- Overhaul stop logs,

- Frames,

- Flashboards,

- Ancillary equipment, and

- Warehouse bridge crane.

2. THE HYDROTECHNICAL COMPLEX SRPSKI ITEBEJ

2.1. FACILITIES (Technical building, Workshop and Residential building)

Supervision and quality control of executing of:

•    CONSTRUCTION WORKS:

- Roof repairing,

- Complete construction of the floor,

- Vertical and horizontal water insulation,

- The treatment of interior walls,

- The complete replacement of the existing plumbing and drainage installation,

- Completely redesigned sanitary blocks.

•    ELECTRICAL WORKS:

- Newly designed electrical installations:

o Building power supply,

o Distribution cabinets,

o Electrical installations,

o Protection against electric shock and lightning protection of facilities,

2.2. SHIP LOCK AND FLOODGATE

Checking and testing the quality of execution of all types of works on repair of the ship lock and floodgate includes the following groups of works:

•    CONSTRUCTION WORKS

- Preparatory works,

- Disassembly and demolition works,

- Earthworks including construction of access roads and handling platforms,

- Concrete works,

- Masonry works,

- Reinforcing steel works,

- Insulation works,

- Carpentry,

- Metalwork.

•    ELECTRICAL WORKS

- Lighting of ship lock and floodgate:

o Lights,

o Light poles,

o Power supply cables.

- Marking of waterways:

o Traffic lights,

o Traffic lights pole,

o Power supply cables.

- Revision of the pole-mounted substation STS 20/10 / 0.4 kV / kV / kV, 50 kVA.

•    MECHANICAL WORKS:

The works include the manufacturing of parts, replacement/repairing of the following equipment parts:

- Mitre gates with a driving mechanism,

- Overhaul stop logs,

- Frames,

- Flashboards,

- Warehouse bridge crane and

- Ancillary equipment.

3. SHARED-USE PATH

(along the Bega canal from the border between Romania and Serbia to the village of Klek)

The subject matter of the service is supervision of construction of a shared-use path (service and bicycle) from the border between Romania and Serbia, along the embankment by the Bega canal to the village of Klek and its fitting into the existing bicycle path in the village. The length of the road section is cca. 33 km.

The path is intended to be used for smaller vehicles during checking and/or inspection of this section and also for the machinery with maximum 5 t axle load.

The path will also be used for cycling purposes.

A 2.0 m wide path with asphalt paving should be constructed. The beginning of the section is at the border between the Republic of Romania and the Republic of Serbia, at the top of the embankment along the Bega river, on the right, observed in the direction of the forward chainage. The path is an extension to the bicycle path intended to be constructed on the Romanian side, from Timișoara to the border with the Republic of Serbia. The path continues further along the embankment on the right side to the second bridge in the village of Srpski Itebej, situated on the local road, where it crosses to the other side of the embankment and continues further along the left side up to the existing floodgate on the Bega river in the village of Klek, where it leaves the embankment to continue along the road from the floodgate to the village of Klek, i.e. the point of fitting into the existing bicycle path passing through the village of Klek. Within this section, there are three more bridges crossing the embankment, which is where the path descends the embankment to pass along the bank under the bridges,

The works should also include construction of five resting points on the embankment, along the path, with dimensions 25x2.5 m, with the appropriate mobile street furniture (benches, tables, dustbins), located at the sections passing through the communities (Srpski Itebej, Torak, Žitište, Klek).

4. FLOATING DOCK

The works including regulation the left bank of the Bega, at km 26+612, and construction floating facility - a dock and a mooring for recreational vessels in Zrenjanin. The site is located on the Bega sector beyond the waterway under the controlled water regime.	The floating dock will be located in the urban part of Zrenjanin outfitted with utility infrastructure.

At the above site, there is an old turning basin which is currently neglected, overgrown with vegetation, primarily reed. Before the floating dock is installed, it is necessary to perform preliminary construction works both in the canal bed and on the bank.

The works shall include cleaning of overgrown vegetation and deposits at the bottom of the canal bed. The vegetation should be removed from the canal banks and from the canal bed (reed) before the commencement of any other works. After the vegetation removal, it is necessary to remove sludge down to the required level, to ensure unhindered navigation even under the conditions of minimum water regime.

The newly constructed bank obtained after the arrangement of the plateau should be secured with a bank revetment, from km 26+500 up to 26+575.. The bank revetment should be constructed in two levels. At its bottom, the bank revetment should lean against the toe made of riprap, and it should also contain reinforced concrete beams as support on the borders of its slopes.

The floating dock should be consist of three pieces HD floating concrete pontoon, interconnected by means of special cables.

The works on  floating dock including path construction with the dock and  procurement and assembly fenders, mooring bollards, fence and other equipment in accordance with the applicable regulations.

### Geographical area to be covered

The contract will cover area of Central Banat District and Novi Sad Municipality – South Backa District (Serbia).

### Target groups

The target group is made up of the final beneficiaries of this project implementation: the population of the Timis county and Central Banat District:

Primary target group:

Cross-border area population

Secondary target groups:

- Tourists

- Cross border area economic units (enterprises located in the area)

- People who work in the field of navigation.

## Specific work

During the implementation of project “The repairing of the navigation infrastructure on Bega Canal”, the Consultant is expected to provide supervision services related to works (repair) of hydro-complexes (shiplock and floodgate) Klek and Srpski Itebej; construction works of service/cycling path; hydro-technical works for regulation canal bank and installation of the floating dock on Canal Begej in Zrenjanin.

The Contractor shall ensure all supervision services and exercise all reasonable care to protect the interests of the Contracting Authority and advise the Contracting Authority on all necessary measures to overcome dispute situation and meet the works contract objectives.

To fulfil such requirements, the Contractor shall establish organizational structure during the construction supervision services in accordance with all requirements for quality control, control of quantities, supervision on the work progress, analysis of expenses and full implementation of environmental criteria as well as working on technical and administrative questions during the construction and Defects Liability Period (DLP).

In the course of the performance of its services, the Contractor will ensure that required safety measures are applied at all stages, in line with local legislation and international standards. Similarly, the Contractor will ascertain that all environmental protection aspects are considered, and in particular that the mitigation measures recommended in the EIA are effectively implemented.

The Contractor shall act as a Supervisor, in compliance with the PRAG contract, as well as with all requirements laid down by the Serbian laws.

The Contractor shall liaise with the Contracting Authority institution for the purpose of maintaining regular contacts, consultations and flow/exchange of information and keep them fully informed on all matters relating to the status of the works contract and in particular any issues with possible cost or progress implications.

The Contractor is invited to make a clear proposal in the offer on identification of key activities, organisation of the work and distribution of resources to allow timely and efficient achievement of projects' results.

The service will be contracted for a 24 months period of project implementation, as a part time job  and the offer is to be made for lump sum for the complete service of technical support.

Contractor’s services related to Works contract must cover the following main project periods:

- Pre-construction period

- Construction period

- Post-construction period (defects liability period).

### Activities during Pre-Construction period

- Recruitment of staff and logistics organization (other than proposed Key expert);

- Establishment of due procedures for proper works supervision including preparation of a Manual of Supervision Procedures. The Manual shall include the provisions of the actual Serbian legislation in connection with design and quality in construction. The Manual shall include as a minimum:

- Review the works Contractor’s safety procedures

- Review the works Contractor’s QA systems

- Review the works Contractor’s documents

- Review the works Contractor’s claims

- Review the works Contractor’s method statements, inspection plans and procedures

- Checking the equipment/ materials brought to site

- Review the construction contractors proposed changes and non-conformities to the contract

- Reporting on construction contractors progress

- Records of site meetings

- Records of site photographs of construction

- Review of construction contractors testing schedules for tests on completion and procedures to ensure validity of construction contractors process designs

- Provisional Acceptance certificate

- Regular inspections/ tests to be done throughout the Defects Liability Period

- Final Acceptance Certificate;

- Ensure that the communication and reporting mechanism with the Contracting Authority (CA) is set up, fully functioning and efficient for the duration of the project;

- Checking the validity period and approvals of relevant Works Contractor’s insurance policies, guarantees, certificates and other relevant documents under liability of the Works Contractor;

- Checking and confirming that all required approvals and permits are obtained in time, before commencement of respective works.

### Activities during Construction period

#### Contract administration and management

The Contractor shall carry out contract administration and management duties throughout the duration of the assignment to secure smooth and timely implementation, proper supervision in accordance with Technical Documentation and control of the Project. For this propose the Contractor shall establish clear lines of responsibility and procedures for each activity in the construction period.

For the implementation of the works, the Contractor shall supervise the procedures and the results of measurement of the site of the works to be carried out by the works contractor.

The Contractor shall analyse and monitor contractual programmes submitted by the works contractor and give instructions to the Works Contractor to take appropriate measures to fulfil works contractor’s tasks. The Contractor shall review Works Contractor’s programmes on a regular basis throughout the project.

The Contractor shall ensure that works will not commence before all required approvals, construction and excavation permits and permits for closing of public areas and road are obtained.

The Contractor shall ensure that all conditions of contract are strictly adhered to and that Works Contractor fulfils his contractual obligations. All instructions to the Works Contractor shall be clearly documented by the Contractor.

The Contractor shall ensure that all safety risks during construction and commissioning of the works are assessed in advance and risk mitigation measures introduced prior to commencement of the relevant activities.

Monitoring of the financial resources and immediately advise the Contracting Authority of any potential cost savings, and also if he considers that the construction costs are likely to exceed the available budget;

Interim payment certificates - check the Works Contractor’s measurement and calculations of quantities of works completed and statement. Based on this the Contractor will certify, after correction if necessary, the Works Contractor’s Interim Payment Certificate so that it can be delivered to the Contracting Authority in a format agreed with him, within the period stipulated in the works contract;

Unscheduled works items - For any unscheduled items of works that may arise, the Contractor shall negotiate the costs with the Works Contractor and make recommendations to the Contracting Authority;

The Contractor shall be in continuous contact with the Works Contractor to identify and resolve any potential problems in a proactive manner. The Contractor shall hold weekly site meetings and monthly progress meetings with the Works Contractor and other stakeholders.

The Contractor shall seek the Contracting Authority agreement prior to any instruction to the Works Contractor, which could increase the cost and the time extension of the project.

All potential delays and other problems shall be identified with corresponding actions agreed in order to assist the Contractor to avoid overall delay. The Contracting Authority shall be kept informed of the progress of works by providing detailed minutes of meetings. The Contractor shall prepare all reports.

The Contractor shall assist the Contracting Authority in administrative duties, including financial planning and preparation of cash flow forecasts for the works contract on monthly basis.

The Contractor shall carry out any other task related to the works as may be requested by the Contracting Authority.

#### Ensuring adherence to international standards

The Contractor shall ensure that works are implemented to a high standard in accordance with the PRAG conditions as well as in line with the Serbian legislation.

#### Design review

The Contractor shall review the existing design, Bills of Quantities and technical specifications, review and approve Design for execution prepared by the Works Contractor.

#### Site Supervision

The Contractor shall carry out day-to-day supervision of construction works in accordance with the Works Contracts and according to the Construction and Planning Law, Site Procedures Manual and Supervisor’s Quality Assurance Manual. The main objective of the supervision is to facilitate achievement of the highest possible standard of construction works within the contract time.

The Contractor shall advise the Contracting Authority of any appropriate measures that may be taken to avoid and rectify any deficiencies and improve the cost effectiveness of the project.

- The Contractor shall maintain and update regularly with the Works Contractor the site diary and other relevant documents in English and in Serbian, as required by the Law on Planning and Construction of the Republic of Serbia.

- Approval of Works Contractor’s performance programme (time table) - The Contractor shall approve the Works Contractor’s programme, particularly the mobilization of plant and equipment on site, and the deployment of specialized trades and of sub-contractors;

- Control of all contractual documentation available (insurances, guarantees, permits, etc);

- Surveys, site investigations and setting out of the works - check and approve all of the contractor’s surveys, investigations and setting out of the works;

- Smooth project implementation system in place including quality assurance system;

- All risks in terms of potential quality problems, delays or budget overruns shall be timely identified and professionally managed;

- All the works to be constructed by the Contractor shall be in strict compliance with respective Works Contract financed by the European Union, within contract time and budget.

- Supervision of works carried out, all relevant documentation completed in accordance with the Works contract and in line with relevant Serbian legislation;

- Monitor progress of the works

- Advise on any claims or contractual problems arising during the works, indicate potential delays and prevent the claims whenever possible;

- Provisional acceptance certificate - The Contractor shall prior to the provisional acceptance, carry out joint final site inspections and surveys and agree a snagging list with the Contracting Authority. When it is agreed that the snags are such that the works are substantially complete, and after receiving the work contractor’s request for such certificate, the Contractor shall prepare and submit to the Works Contractor in coordination with the Contracting Authority, the provisional acceptance certificate;

- All required technical and administrative reports to the Contracting Authority prepared in time.

#### Quality controls

The Contractor shall supervise quality controls:

- The Contractor shall ensure that the quality of materials and the end product is to the high standard of quality. All testing shall be carried out in accordance with the valid RS standards, works technical specifications, specified procedures and at the specified intervals;

- The Contractor may propose amendments to the design and specifications for the Contracting Authority’s approval, if such alterations are considered to be benefit to the quality and economy of the Project;

- Issue any variation order regarding the quantities of the works, if fully justified by the site situation, in consultation with the Contracting Authority;

- The Contractor shall instruct the works contractor to substitute and make good any part of the works, if levels, dimensions, materials or workmanship do not conform to the requirements and specifications;

- The Contractor shall measure and keep accurate records of permanent works executed by the works Contractor. The works shall be measured on site in accordance with the Contract and as presented on the contract drawings.

- The Contractor shall ensure that the Works Contractor’s payment requests for work executed are accurate, fair and reasonable representations of the value of the work.

- The Contractor shall prepare interim certificates for interim payments, and certify completion of parts or the totality of the works. The Contractor shall ensure that the Contracting Authority is at all times informed of all matters relating to payments, cash flow or any other impacts on budgetary provisions;

- To avoid any delays in payments the Contractor shall ensure high quality of all payment documents;

- The Contractor shall carefully monitor all levels, lines and other parameters affecting the work, so as to ensure that the works are constructed to fulfil requirements of the Contracting Authority;

- Accurate records shall be taken throughout the duration of the contract in order to reach agreement on the Contractor’s final account;

- The Contractor shall conduct regular site inspections to check the quality of the workmanship and materials in accordance with the Contract and good engineering practice.

- Organize an archiving system (digital and on paper) in order to survey the progress of works. All the documents and communications related to the programme shall be archived and the archiving system shall be maintained in full compliance both with the requirements of the financing institutions and with the requirements of the Serbian law.

- The Contractor shall obtain the specific approval of the Contracting Authority before taking action for which under Works Contract approval is required to be obtained.

#### Other activities

The Contractor shall carry out all other activities needed for the smooth implementation of the Project.

### Activities during the post-construction period (Defect Liability Period)

The Contractor shall ensure that the Works Contractor fulfils his contractual obligations during the defects liability period, including rectifying all defects in the works in a timely manner. The activities to be performed by the Contractor during this period include, but are not limited to:

- Inspections during the defects liability period:

In addition to inspection of the works at expiry of the defects liability Period (12 months), the Contractor shall undertake three intermediate inspections at approximately three month intervals during the defects liability Period. In the event that the Contracting Authority calls the Contractor to the works to deal with a particular defect at another time this shall be deemed to be one of the intermediate inspections.

In addition to dealing with any particular defect all intermediate inspections shall cover the entire works. The Contractor shall:

- Notify and instruct the Works Contractor accordingly of all defects found;

- Report on the status of the Works and on the operation and maintenance of the Works to date;

### Final Inspection on expiry of the Defects Liability Period

The final inspection of the whole works period shall be carried out just before, or on expiry of the Defect Liability Period in the presence of a representative from the respective Work Contractor, Beneficiary and the Contracting Authority. Any outstanding defects shall be issued to the works Contractor as a sang list within time stipulated in the contract. When problems or defects have been remedied, another joint site inspection shall take place and if the works are satisfactory the Contractor/Supervisor will issue the defects liability certificate. The results of the inspections and the issuing of the Final Acceptance Certificate will be covered in the final technical report of the Work Contract.

### Visibility activities

In addition to above activities, the Contractor must also perform activities defined in the latest Communication and Visibility Manual for EU External Action available at:

https://ec.europa.eu/europeaid/funding/communication-and-visibility-manual-eu-external-actions_en.

The compliance with this shall be made an output of the contract and the Contractor shall include in its reporting what have been accomplished.

### Final outputs

The required final outputs of this contract on works supervision should be as follows:

- Provisional and Final Acceptance Certificate of the Works Contract including the approval obtained from the PWMC Vode Vojvodine Novi Sad and the final site report signed by all concerned parties (Works Contractor, PWMC Vode Vojvodine Novi Sad and Supervisor);

- Provisional Acceptance Certificate of the Supply contract including the approval obtained from the PWMC Vode Vojvodine Novi Sad

- All contractual paperwork in place in time (insurances, guarantees, permits etc.);

- Smooth projects implementation system in place and implemented, including quality assurance system. Supervisor shall draft the Supervision Procedures Manual, where supervision team members have assigned responsibilities, which will be adopted by the Contracting Authority.

- All risks in terms of potential quality problems, delays or budget overruns timely identified and professionally managed;

- All the works implemented by the works Contractor in strict compliance with respective works contract, within contract time and budget lines. Supervision of works carried out, all relevant documentation completed in accordance with the works contracts and relevant law;

- Works handed-over and permissions for utilization obtained under the statutory procedures and within the specified periods;

- All required technical and administrative reports prepared in time

## Project management

### Responsible body

The Contracting Authority is Public Water Management Company “Vode Vojvodine” which is Partner 4 of the project. The Consultant is responsible for all the activities regarding this contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Assistant Project Manager Stevan Ilinčić.

### Facilities to be provided by the Contracting Authority and/or other parties

The Consultant shall ensure that experts are adequately supported and equipped. In particular it shall ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support its activities under the contract and to ensure that its employees are paid regularly and in a timely fashion.

If the Consultant is a consortium, the arrangements should allow for the maximum flexibility in project implementation. Arrangements offering each consortium member a fixed percentage of the work to be undertaken under the contract should be avoided.

The Consultant will provide at its project office the required equipment (copying equipment, fax machine, telephones, computers, computer software and other software required to perform the services, printing and/or plotting facilities) to execute the project activities, as well as the communication facilities and connections of telephone, fax and internet for the use of the staff.

The cost of all the above facilities plus translation and interpretation cost shall be borne by the Consultant and are to be included in the financial offer of the tenderer.

# LOGISTICS AND TIMING

## Location

The Republic of Serbia, AP Vojvodina, Central Banat District and City of Novi Sad.

## Start date & Period of implementation of tasks

The intended start date is the date of signature of the contract by both parties and the period of implementation of the contracts will be 24 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Supervision Team leader

Qualifications and skills:

•   University degree in Engineering

•   License of Serbian Chamber of Engineers no. 310 or 311 or 410 or 411

•   Knowledge of preparation of technical documentation;

•    IT-skills: MS Office, MS Excel, CAD software

•    Advanced level of English language.

General professional experience:

•    At least 5 years of general professional experience.

Specific professional experience:

• Minimum 1 reference (project) related to supervision services.

Key expert 2: Supervisor expert 2

Qualifications and skills:

•   University degree in Engineering

•   License of Serbian Chamber of Engineers no. 312 or 315 or 412 or 415

•   Knowledge of preparation of technical documentation;

•    IT-skills: MS Office, MS Excel, CAD software

•    Advanced level of English language.

General professional experience:

•    At least 5 years of general professional experience.

Specific professional experience:

• Minimum 1 reference (project) related to supervision services

Key expert 3: Supervisor expert 3

Qualifications and skills:

•   University degree in Engineering

•   License of Serbian Chamber of Engineers no. 313 or 314 or 413 or 414

•   Knowledge of preparation of technical documentation;

•    IT-skills: MS Office, MS Excel, CAD software

•    Advanced level of English language.

General professional experience:

•    At least 5 years of general professional experience.

Specific professional experience:

• Minimum 1 reference (project) related to supervision services

Key expert 4: Supervisor expert 4

Qualifications and skills:

•   University degree in Engineering

•   License of Serbian Chamber of Engineers no. 300 or 400

•   Knowledge of preparation of technical documentation;

•    IT-skills: MS Office, MS Excel, CAD software

•    Advanced level of English language.

General professional experience:

•    At least 5 years of general professional experience.

Specific professional experience:

• Minimum 1 reference (project) related to supervision services

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The selection of experts shall be subject to approval by the Contracting Authority.

Other experts to be employed shall include as minimum the following:

- one (1) engineer with license of Serbian Chamber of Engineers no. 332 or 432

- one (1) engineer with license of Serbian Chamber of Engineers no. 350 or 450

- one (1) engineer with license of Serbian Chamber of Engineers no. 370 or 470

- one (1) engineer with license of Serbian Chamber of Engineers no. 391 or 491

The Consultant shall provide adequate backstopping services during the project implementation. In addition, the Consultant shall provide necessary support staff to cover the needs for office management and administration, secretarial services, draughtsmen, interpretation and translation, drivers, and any other administrative needs during the performance period. Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Consultant.

## Facilities to be provided by the Contractor

The Consultant shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority/partner country as part of this service contract or transferred to the Contracting Authority/partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and one copy:

- The contractor will prepare final report on the implementation of the tasks, at the end of contract. It should be submitted at the end of 24 months. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions. The final report must be provided along with the corresponding invoice.

- The contractor will prepare brief interim reports by the end of 3rd, 6th, 12th, and 15th months. The approval of interim report will be the basis for issuing respective interim payment as indicated in the Special Conditions. The interim report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Assistant Project Manager identified in the contract. The Assistant Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

“Services provided in timely, quality and quantity manor, as required in these Terms of Reference”.

## Special requirements

Not applicable.