ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania

## Contracting Authority

Miltonia Association

## Country background

The Interreg-IPA Cross-Border Cooperation Romania-Serbia Programme is funded by the European Union under the framework of the new Instrument for Pre-accession Assistance (IPA II), the Cross-border Cooperation (CBC) Component and co-financed by the Partner States in the Programme. The Programme focuses on increasing the overall competitiveness of the economy in the Romania-Serbia border area and on the improvement of the quality of life for the border communities in both countries. The 2014-2020 Programme is the continuation of the Romania-Republic of Serbia IPA CBC Programme financed for the 2007-2013 period.

## Current situation in the sector

- All participating partners from Romania and Serbia use the same rules, implement projects jointly, and manage budgets together. This enables the establishment of long-lasting contacts between people, and joint cross-border activities to help economic development, support small-scale infrastructure, protect the environment, and foster research, culture, and education. It also increases the overall social cohesion along EU external borders. Furthermore, through the process of project identification, applying for funds and project implementation, partners from candidate countries gain valuable experience in management of EU funds. More information can be accessed via www.romania-serbia.net.

## Related programmes and other donor activities

N/a

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

”Establishing conditions for environment protection in the Banat region through creating of cross-border network for joint trainings”

## Purpose

The purposes of this contract are to organize 4 trainings for 4 categories of pupils, as follows:

- Training in applied ecology for pre-school children

- Training in applied ecology for elementary school children (I–IV grade)

- Training in applied ecology for elementary school children (V–VIII grade)

- Training in applied ecology for high school youth

## Results to be achieved by the Contractor

Children and youth educated in applied ecology and the basis of emergency situations reaction, as follows:

- Pre-school children educated about applied ecology trough training “I’m protecting environment too!”. 24 training sessions during 3 months in which were involved 50 pre-school children from Timisoara.

- Elementary school children (I-IV grade) educated about applied ecology trough training “Don’t be mean – be green!”. 24 training sessions during 3 months in which were involved 50 elementary school children (I-IV grade) from Timisoara.

- Elementary school children (V–VIII grade) educated about applied ecology trough training “Let’s do it green!”. 24 training sessions during 3 months in which were involved 50 Elementary school children (V–VIII grade) from Timisoara.

- High school youth educated about first aid, reacting in the fire emergency and responding in emergency situations trough training “ECO – EDU training”. 24 training sessions during 3 months in which were involved 50 high school youth from Timisoara.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

N/A

## Risks

N/A

# SCOPE OF THE WORK

## General

### Description of the assignment

Contractor will prepare, organize and realize 4 types of training for the targeted area (Timisoara, Timis County, Romania) in which children of four categories will be educated in ecology. The fourth category of children will be educated in how to give first aid.

The preparation and development of training plan (methodology) will be done in close cooperation with the training expert from the Contracting Authority. After obtaining approval on prepared plan and material from Contracting Authority, the Contractor will organize the trainings. The Contracting Authority will provide the Contractor with trainings schedule. The Contractor is obliged to respect the schedule.

### Geographical area to be covered

Timisoara, Timis county, Romania

### Target groups

Preschools, elementary schools, high schools for Timisoara with their pupils and teachers.

## Specific work

- Training in applied ecology for pre-school children

Training in applied ecology for pre-school children will be organized in the pre-schools in Timisoara and it will last for 3 months. During this 3 months, 50 pre-school children will be involved in 24 training sessions.

The Contractor will organize one training in 24 sessions. Each session will last 45 minutes with number of participants of 50.

Training will have two parts:

- Theoretical education – in which through educative stories, adapted to the kids age, trainers will teach the pre-school children how to embrace, respect and save the environment;

- Practical work – in this part, by using educational picture book, colouring book, making of scrapbooks, children will be directly involved in the creating of atmosphere of carrying for nature.

  - Playing with eco toys – eco toys will be provided by Contracting Authority

  - Drawing scathes, drawings and pictures with the topic of environment protection, (which will be presented on the joint exhibition in Pancevo at the end of the project)

Trainings preparation:

- Contractor will prepare methodology and content for trainings in line with the identified training needs.

- Developed training will be approved by Contracting Authority’s Training Expert.

At the end of the Training the Contractor will provide to the Contracting Authority the List of participants together with other outputs of the training.

- Training in applied ecology for elementary school children (I–IV grade)

Training in applied ecology for elementary school children (I–IV grade) will be implemented in Timisoara, and it will last for 3 months. During this 3 months, 50 elementary school children (I–IV grade) from Timisoara will be involved in 24 training sessions.

By developing of set of trainings composed with theoretical and practical part, adjusted to their age, the children will learn how to protect the environment.

The Contractor will organize one training in 24 sessions. Each session will last 45 minutes with number of participants of 50.

Training will have two parts:

- Theoretical part – in this part of the training we will deal with the following topics:

- Who are the main polluters

- What can I do to decrease pollution

- What is recycling and why it is important

- Practical part – this second part of the training will contain two activities:

  - One activity will be to organize ”Day of Forgotten Games”. Today’s children, at this age, already have their own mobile phones, computers, iPhones, iPads, iPods. In order to separate them, for at least one day, from computers and mobile phones, the central activity of this activity, in which pupils will gather in the school yard and spent the day playing hugs, mares of mares, marbles, and similar games.

  - Another activity will be drawing scathes, drawings and pictures with the topic of environment protection, which will be presented on the joint exhibition in Pancevo at the end of the project. In this part of the action, children with special needs from Pancevo will be involved.

Trainings preparation:

- Contractor will prepare methodology and content for trainings in line with the identified training needs.

- Developed training will be approved by Contracting Authority’s Training Expert.

At the end of the Training the Contractor will provide to the Contracting Authority the List of participants together with other outputs of the training.

- Training in applied ecology for elementary school children (V–VIII grade)

Training in applied ecology for elementary school children (V–VIII grade) will be implemented in Timisoara and will last for 3 months. During this 3 months, 50 elementary school children (V–VIII grade) from Timisoara will be involved in 24 training sessions.

The Contractor will organize one training in 24 sessions. Each session will last 45 minutes with number of participants of 50.

Training will have two parts:

- Theoretical part – in this part of the training, participants will be informed about:

- Energy from the sun

- Energy from the water

- Energy from the wind

- Practical work – this second part of the training will contain two activities:

  - In the first activity we could involve survey about level of awareness of importance of protecting of environment, which will be developed by children, in cooperation with trainers. One of the questions will be where the survey participants thinks it should be the place where the threes should be planted during actions of afforestation. After that, children will interview their parents, teachers, friends, etc. and analysing results of the survey.

  - In the second activity we will include drawing scathes, drawings and pictures with the topic of environment protection, which will be presented on the joint exhibition in Pancevo at the end of the project.

Trainings preparation:

- Contractor will prepare methodology and content for trainings in line with the identified training needs.

- Developed training will be approved by Contracting Authority’s Training Expert.

At the end of the Training the Contractor will provide to the Contracting Authority the List of participants together with other outputs of the training.

- Training in applied ecology for high school youth

Training in applied ecology for high school youth will be implemented in Timisoara and it will last for 3 months. During this period, 50 high school youth from Timisoara will be involved in 24 training sessions.

The Contractor will organize one training in 24 sessions. Each session will last 45 minutes with number of participants of 50.

Training will have two parts:

- Theoretical part – In this part, the high school youth, from Timisoara, will be trained in the following topics:

- First aid

- Reacting in the fire emergency

- Responding in emergency situations

- Practical part – In this part, the trained high school youth will compose 3 teams who will compete in the practical usage of first aid, responding in the case of fire and emergency situations.

  - This part will be developed through a Competition, that will be held in Pancevo and organized by the Serbian partner, in the following way:

    - Competitions will be organized in Pancevo and it will last for 3 days.

    - We will form 3 teams of high school youth from Timisoara, that participated in the theoretical part of this training.

    - Competition will be on the principle of elimination: 6 teams, 3 from Timisoara and 3 from Pancevo, will start the competition on first day; two teams that scores the least points are falling out.

    - Competition will continue next day, on the same principle, so at third day 2 finalist will compete for the first place.

    - For the competition, the partner from Serbia will provide transportation, accommodation and appropriate prizes for all participants.

The Contractor will organize one training in 24 sessions. Each session will last 45 minutes with number of participants of 50.

Trainings preparation:

- Contractor will prepare methodology and content for trainings in line with the identified training needs.

- Developed training will be approved by Contracting Authority’s Training Expert.

At the end of the Training the Contractor will provide to the Contracting Authority the List of participants together with other outputs of the training.

## Project management

### Responsible body

The Training Expert of this project is responsible for all activities regarding this contract.

### Management structure

The Training Expert of this project is responsible alone for all contract procedure.

### Facilities to be provided by the Contracting Authority and/or other parties

Based on the developed training by the Contractor and approved by the Training Expert of the Contracting Authority, the Contracting Authority will provide to the Contractor training material necessary for conducting the training sessions.

# LOGISTICS AND TIMING

## Location

Romania, Timisoara, Timis county

## Start date & Period of implementation of tasks

The intended start date is date of signature of the contract by both parties and the period of implementation of the contract will be 6 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Training coordinator

Qualifications and skills

University studies

Training experience

General professional experience

Minimum 3 years general professional experience, preferred 5 years

Specific professional experience

Minimum 2 years training experience, preferred 3 years

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and one copies:

- Inception Report of maximum 12 pages to be produced after one week from the start of implementation. In the report the Contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The Contractor should proceed with his/her work unless the Contracting Authority sends comments on the inception report.

- Interim reports (if it is the case). The contractor can prepare interim reports after providing the services according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments as indicated in the Special Conditions.

- Draft final report of maximum 12 pages (main text, excluding annexes). This report shall be submitted after the finalization of the activities.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 2 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on services provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manner, as required in these Terms of Reference”.

## Special requirements

Not the case.