ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Serbia

## Contracting Authority

Coka Municipality

## Country background

N/A

## Current situation in the sector

- N/A

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

Project Regional Employment Center has, as a main goal, establishing pre-conditions for employment opportunities in the rural area of cross-border region. Municipality of Coka and Municipality of Deta are similar in number of inhabitant, also they are both rural agricultural area with most population acting in this field. Taking into account that those two municipalities are similar in many ways, it was natural that they have similar problems. All these lead to the joint project proposal and establishment of partnership between these two municipalities. By establishing Regional Employment Center, with offices in both municipalities, we will implement several different sets of trainings in order to provide conditions for new jobs in our municipalities.

## Purpose

The purpose of this contract is as follows:

Organizing of trainings for: basic IT, web development, web design, so as IT competition

## Results to be achieved by the Contractor

- Basic IT training delivered

- Web development training delivered

- Web design training delivered

- IT competition organized

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

N/A

## Risks

N/A

# SCOPE OF THE WORK

## General

### Description of the assignment

Project Regional Employment Center has, as a main goal, establishing pre-conditions for employment opportunities in the rural area of cross-border region. Municipality of Coka and Municipality of Deta are similar in number of inhabitant, also they are both rural agricultural area with most population acting in this field. Taking into account that those two municipalities are similar in many ways, it was natural that they have similar problems. All these lead to the joint project proposal and establishment of partnership between these two municipalities. By establishing Regional Employment Center, with offices in both municipalities, we will implement several different sets of trainings in order to provide conditions for new jobs in our municipalities. One of the set of the trainings will be IT trainings, for basic IT knowledge, WEB development and WEB design. After the trainings, we will organize IT competition.

### Geographical area to be covered

North Banat, Serbia

### Target groups

- Unemployed youth

- Women in rural areas

- People with special needs

- Elderly people in villages

## Specific work

- The Contract will be last for 8 months. The Contractor is obliged to organize the following under this Contract:

- Basic IT training

- Web development training

- Web design training

- IT competition

- Detailed description of activities:

- 1. Basic IT training

Basic IT trainings contain:

- 12 training days in Microsoft Office Word

- 12 training days in Microsoft Office Excel

- 12 training days in Microsoft Office Power Point

| Duration | Number of training days | Training days per week |
| --- | --- | --- |
| 3 months | 36 training days | Min 3 trainings per week |

- Trainings should be delivered in Čoka. It should start at most one week after the contract signing. One expert is necessary with one assistant. Each group of participants will be consists with minimum 5 and maximum 10 persons.

- For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

- The Contracting Authority is obliged to provide: premises for trainings, adequate IT equipment, so as participants.

- 2. Web development training

Web development training contains:

- 96 training days

- 1 month of online mentoring

| Duration | Task | Working days / hours per week |
| --- | --- | --- |
| 8 months / 96 training days | Trainings | Min 3 trainings per week |
| 1 month | Mentoring | Depends on trainees needs, but no more than 2 hours per working day |

- Trainings should be delivered in Čoka. It should start at most one week after the contract signing. One expert is necessary, with one assistant. Each group of participants will be consists with maximum 10 persons.

- For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

- The Contracting Authority is obliged to provide: premises for trainings, adequate IT equipment, so as participants.

- 3. Web design training

Web design training contains:

- 96 training days

- 1 month of online mentoring

| Duration | Task | Working days per week |
| --- | --- | --- |
| 8 months / 96 training days | Trainings | Min 3 trainings per week |
| 1 month | Mentoring | Depends on trainees needs, but no more than 2 hours per working day |

- Trainings should be delivered in Čoka. It should start at most one week after the contract signing. One expert is necessary, with one assistant. Each group of participants will be consists with maximum 10 persons.

- For each training session, the Contractor should provide: list of participants and photos. For final training session, beside list of participants and photos, the Contractor should also provide evaluation.

- The Contracting Authority is obliged to provide: premises for trainings, adequate IT equipment, so as participants.

- 4. IT competition

- In order to provide the opportunity to our trainees to test their newly gained skills, we will organize competition for new web developers and web designers. Teams will be formed by persons trained during the project implementation and they will compete in order to develop the best web site/page. Their former trainers will be in charge for developing of tasks and they will be also their mentors. Teams will be mixed, consist of Serbian and Romanian team members, in order to jointly reach their goals.

- 4 teams will participate, each composed with 4 participants. Competition will be divided in 2 parts. First part will be implemented home-based, where each team will start with the website/page preparation, and that will last for 2 weeks. 2 teams which would be more successful in the first phase, will oppose to each other in the second phase, which will be organized on Coka local REC office and it will last for 2 days. After that, jury composed with IT experts and SME owners will choose the winners.

- The Contractor will be in charge for accommodation of participants and jury members from Romania. Food should be provided for all participants and jury members, both from Romania and Serbia.

- Transportation for Romanian participants and jury members should be provided by Romanian partner.

- Accommodation for 2 nights (bed and breakfast) for 4 competitors and 2 jury members from Romania should be provided in single or double rooms in Coka or in the vicinity of max 5km.

- Food for 2 days (lunch and dinner) for 12 persons (4 competitors and 2 jury members from Romania and 4 competitors and 2 jury members from Serbia) should be organized in Coka.

- Both meals should contain:

- Soup

- Main course with meat, side dish, bread and salad

- Dessert (cake or ice cream or fresh fruit)

- 2 non alcoholic drinks per person

- This activity is planned to be done on 8th month of the contract. The exact date will be established later, with mutual agreement of both contracting parties.

## Project management

### Responsible body

The Project team members, led by Project Manager is responsible for managing this Contract on behalf of the Contracting Authority

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Mr Zoran Jovanov.

### Facilities to be provided by the Contracting Authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

Coka Municipality, North Banat, Serbia

## Start date & Period of implementation of tasks

The intended start date is the date of signing Contract by both parties and the period of implementation of the contract will be 8 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key expert 1: Basic IT trainer, Team leader

Qualifications and skills

University degree in IT technologies or Technical sciences or Mathematic or equivalent

General professional experience

Minimum 5 years experience in education or in training deliveries

Specific professional experience

Minimum 3 years experience in IT sector education; English language fluently, reporting skills

Key expert 2: Trainer web development

Qualifications and skills

University degree in IT technologies or Technical sciences or Mathematic or equivalent

General professional experience

Minimum 3 years experience web development

Specific professional experience

Minimum 2 years experience in web development teaching or training delivery; English language fluently

Key expert 2: Trainer web design

Qualifications and skills

University degree in IT technologies or Technical sciences or Mathematic or equivalent

General professional experience

Minimum 3 years experience in web design

Specific professional experience

Minimum 2 years experience web design teaching or training delivery; English language fluently

### Other experts, support staff & backstopping

For each of above described experts, it is necessary to be provided one assistant. Assistants should have at least higher education in IT technologies or Technical sciences or Mathematic or equivalent. Previous experience in training deliveries is not obliged.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language in one original:

- 2 Interim reports should be prepared at the end of the 3rd and 5th month of the implementation of the Contract. The report should be done in English, in one original. It should contain detailed information about services implemented in that period.

- Final report should be prepared at the end of the Contract. The report should be done in English, in one original. It should contain detailed information about services implemented in that period, so as the whole Contract.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality and quantity manor, as required in these Terms of Reference.

## Special requirements

N/A