ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Serbia

## Contracting Authority

Regional Agency for Socio Economic Development – Banat Ltd., Čarnojevićeva 1, 23000 Zrenjanin, Republic of Serbia

## Country background

Republic of Serbia is Country which is currently preparing for membership of European Union. Number reforms and actions in various spheres of society and state administration are being pursued in order to achieve this goal. Some of this action like Project of which this contract is one part are financed by European Union using specialized funds from various Programmes. Project under which this contract will be funded is Interreg IPA cross border Hungary Serbia Programme.

## Current situation in the sector

The obligation for Republic of Serbia (RS) to improve EE stems from the signed Contract of establishing the Energy Community of South East Europe (SEE), and also on the basis of the adopted directives: • Directive 2006/32 / EC on EE in final consumption and energy services (at the end of 2012 it was replaced by a new Directive 2012/27 / EU) • Directive 2010/30 / EU on the labelling of products affecting energy consumption and • Directive 2010/31 / EU on the energy performance of buildings. The situation in Serbia economy, the technological state of energy and production technologies and the structure of available energy resources inherited from the previous period, leads to a deterioration of the economic effectiveness and EE in the use of energy in RS, in relation to the ASS-6 group (Czech Republic, Slovakia and Hungary, as the countries with very successful, and Bulgaria, Croatia and Romania as countries with slow economic reforms during the same decade of transition). Energy consumption in Serbia is twice higher compared to average consumption in 35 OECD countries, and it is located at the bottom list in Europe in the area of EE of buildings. Around 60% of the final energy is spent by the building sector, and it is estimated that there are between 500,000 and 700,000 energy-inefficiently facilities. Economic development and the growth of life standards are responsible for increasing the growing demand for energy, which requires the development of new, more efficient products and systems, and, on the other hand, greater information and education on EE and renewable energy sources in all sectors of consumption.

## Related programmes and other donor activities

This Project is in agreement with European and national trends. It will create a collaborative environment where participants included in the project will show the ability to achieve national and international competitiveness of the cross-border region

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

Creation of Sustainable Energy Master Plan of Central Banat

## Purpose

The purpose of this contract is as follows:

- Creation of strategic document with all required annexes and activities performed

## Results to be achieved by the Contractor

- Analysis of current situation

- Master plan creation

- Action plan creation

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

No significant social, political or natural disasters to happen during this service implementation

## Risks

No particularly significant risks are predicted which may affect this service contract.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Sustainable Energy Master Plan (Master Plan) will cover territory of Central Banat District, in order to join the planning of energy efficiency targets and measures that will contribute to their achievement at the regional level. On the Romania side, Energy Master Plan of Timis County is developed in 2015, for the period to 2020 and with same documents on SER it is intended to contribute to sustainable energy management across the entire trans boundary region.

### Geographical area to be covered

Central Banat District, Serbia

### Target groups

Local governments, Municipal Officials, Project team members, citizens living in cross border region.

## Specific work

Master Plan should provide the analysis of the current state in energy field, explain the potentials and possibilities, and provide the guidelines for increasing energy efficiency and use of renewable energy sources in the region. Master Plan for Central Banat will map all the territorial challenges and together with Action Plan offer concrete solutions for the reduction of energy consumption and increasing the use of renewable energy sources. It will contribute to the inclusion of other local self-governments in the process of development and improvement of energy efficiency and environmental protection, so that it will be the basis for the formulation of local strategic documents and local action plans in the region.

Master Plan will be strategic instrument, correlating public policies and local/regional strategies with the pragmatic approach of the market, giving the latter a sense of direction and general advisory limits and ranges for maximum sustainability of the future development.

This strategic instrument must be complemented with tactical one in the form of Sustainable Energy and Climate Action Plan (SECAP) for implementation of the Master plan, aimed on decreasing of energy consumption and increasing in using of renewable energy sources based on previously conducted analysis and cost-benefit analysis.

Master plan content:

- General information about Central Banat District (geographical, demographical, energetical and economical)

- Analysis of current state in area of energy efficiency in buildings, public lightning, public transportation and using of renewable energy sources (wind, solar, geothermal, biomass and natural and artificial watercourses)

- Analysis of potentials for energy consumption optimization and using of renewable energy sources

- Vision that will shape the climate and sustainable energy future of the covered region

- Planned energy efficiency / CO2 emission reduction targets

Sustainable Energy and Climate Action Plan for decreasing of energy consumption reduction and increasing in using of renewable energy sources based on previously conducted analysis and cost-benefit analysis - measures, concrete mitigation actions, deadlines, actors/responsibilities, budgets - possible ways to achieve them.

For the implementation of this service Contractor is obligated to perform all activities necessary by Serbian legislative for development of strategic documentation of this type. No additional costs may be charged by contractor in case that there is problem in additional travel needed, public insight of documents, public discussions or there is additional work required for the purpose of modifying, adopting or defending documents. Contractor must calculate all costs required in their financial offer.

The Contractor must also comply with the latest Visual Identity Manual (VIM) of the Interreg-IPA Cross-border Cooperation Romania-Serbia Programme. http://www.romania-serbia.net/?page_id=212&lang=en_GB

## Project management

### Responsible body

The Contractor is responsible for all the activities regarding this contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Irena Zivkovic, Legal Representative.

### Facilities to be provided by the Contracting Authority and/or other parties

The Contractor shall ensure any other facilities, including the transportation means, necessary for quality and timely implementation of the tasks described in these Terms of Reference.

# LOGISTICS AND TIMING

## Location

Central Banat District/ Serbia

## Start date & Period of implementation of tasks

The intended start date is date of signature of contract by both parties and the period of implementation of the contract will be 13 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English Language in one original:

- Interim reports  should be submitted 5th months of service when analysis is finished and 9th months of service when master plan is finished and shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The interim report must be provided along with the corresponding invoice.

- Final report at the end of the service shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Legal Representative identified in the contract. The Legal Representative is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference”

## Special requirements

n/a