ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	3

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	4

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	5

4.1.	General	5

4.2.	Specific work	5

4.3.	Project management	7

5.	LOGISTICS AND TIMING	7

5.1.	Location	7

5.2.	Start date & Period of implementation of tasks	7

6.	REQUIREMENTS	8

6.1.	Staff	8

6.2.	Office accommodation	8

6.3.	Facilities to be provided by the Contractor	8

6.4.	Equipment	8

7.	REPORTS	8

7.1.	Reporting requirements	8

7.2.	Submission and approval of reports	9

8.	MONITORING AND EVALUATION	9

8.1.	Definition of indicators	9

8.2.	Special requirements	9

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

City of Zrenjanin

## Country background

Cross border area of Republic of Serbia and Romania offer mainly identical environment conditions regarding its dynamics and preservation. The borders contact increases the risk for different evironmental aspects, on both sides, especially for climate, insect migration, water (floating and groungwater) and soil quality.

Climate and resources are global challenges needing drastic actions intensify. The expansion of the population will intensify global competition for natural resources, and put pressure on the environment. The both counties must continue to pursuit of solution to the problems of climate change at the same time as implementing climate and energy strategy across their territories.

In preserving biodiversity, landscapes and the quality of air and soils it is important to educate people from rural area to avoid the use in excess of chemicals for combating diseases and pests. Such problems are not enough and systematic approaced, on both sides of the border, regarding: interoperability, informational specialized networks, education of specialists, public administrations, stakeholders, and generally people of all ages.

The project “Integrated management of relationship climate - insect migration in Srednjebanatski district and Timis county” proposes improvements of capacities of competent bodies from local administration and universities, and promotion of cross border networks for education and studies on environmental resources for ensuring the protection and sustainable use of natural resources and preservation of biodiversity in cross border area. The entire Srednjebanatski district benefits from this project as this project proposes education of the population on rational usage of pesticides and artificial fertilizers and through constant real time monitoring alerts competent services on possible environment endangerment and soil degradation, indicating on harmful effect of insects and recommends measures of prevention.

## Current situation in the sector

The water absorption capacity of soil temporarily decreases increasing the risk of floods and soil degradation, and could create conditions for increasing number and varieties of insect and accelerate the migration process without any influence of state border. The migration of insects in the border region leads to more frequent occurrence of diseases in cultivated plants, animals and people, which contributes directly to the air quality and affects human health by consuming crops grown on the infested territory. By consequence, the migration generates human actions against pests and diseases. In addition, controlling the multiplication and migration of insects determines reduction of the quantities of chemical used for treatments and the pollution of soil, water and food products in both cross border area.

Srednjebanatski district uses a system for monitoring weather conditions and has a possibility to alert the population if there is a risk of disease appearance, but has no information from the border area and from the Timis County. Common problem in this area can be solved by implementing joint integrated methods and technologies of monitoring and alerting in case of higher risk of disease appearance or flooding due to reduced water absorbing capacity of the soil. Monitoring the insect migration and weather conditions that may affect environmental conditions presents the basis of the solution. Analyzing soil quality, focusing on parameters that affect the water absorption capacity of the soil in a large areas (especially in areas with high risk of flooding) combined with weather data transmitted in real time, creates necessary conditions for alerting the competent institutions to take measures for preventing natural disasters, reducing the environment damage and disease occurrence which have harmful effects on human health.

## Related programmes and other donor activities

The project “Integrated management of relationship climate - insect migration in Srednjebanatski district and Timiş county” is one of the projects implementing under Interreg-IPA Cross-border Cooperation Romania-Serbia Programme’s priority related to Environmental protection and risk management.

This project contributes directly to achieving the Europe 2020 objectives in chapter about climate change, because a part of its outputs monitor and provides information on the risk of developing greenhouse effect, by tracking meteorological parameters and life forms present in the area and can serve as an indicator of the occurrence of unfavorable climatic phenomena.

The proposed actions contribute to two of the four main objectives of the Danube Region Strategy: protecting the environment in the Danube region (managing environmental risks and preserving biodiversity, landscapes and the quality of air and soil) and interconnecting the Danube region, promoting durable direct contact between people through integrated solutions covering an area on the territory of two countries. An additional factor that will contribute to the interconnection of the region is the conference with scientific experts from the countries of the Danube region.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

Environment protection and biodiversity preservation by implementation of on-line information integrated system, about correlation between weather and soil conditions and insect migration for monitoring the environment, informing and educating about potential polluters (farmers and administration) by the means of new created network of cross-border partners.

Environment protection and biodiversity preservation by implementation of on-line information integrated system, about correlation between weather and soil conditions and insect migration for monitoring the environment, informing and educating target groups as well as interested population about potential polluters by the means of new created network of cross-border partners.

## Purpose

The purposes of this contract are organization of project events as follows:

- Provision of organization of the Project Launching Seminar

- Provision of organization of the conference "Integrated Solutions regarding Environment Protection by Preventing and Reducing Agroindustrial Pollution"

- Provision of organization of the training „Analysis and use of meteorological factors in purpose of environment protection“

- Provision of organization of the Project Closing Seminar

## Results to be achieved by the Contractor

- Organized Project Launching Seminar

- Organized 3-day cconference "Integrated Solutions regarding Environment Protection by Preventing and Reducing Agroindustrial Pollution"

- Organized 3-day training „Analysis and use of meteorological factors in purpose of environment protection“

- Organized Project Closing Seminar

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- The Contractor and staff of City of Zrenjanin appointed for the implementation of project “Integrated management of relationship climate - insect migration in Srednjebanatski district and Timis county” will actively cooperate in order to implement project activities which are subject of this procurement procedure.

## Risks

N/A

# SCOPE OF THE WORK

## General

### Description of the assignment

The Contractor will provide administrative, technical, logistical and catering support for organization of the of the 4 events for the needs of project CLINSIM - Integrated management of relationship climate - insect migration in Srednjebanatski district and Timiş County, RORS-380, according to following schedule:

- Project Launching Seminar on March 2020 in Zrenjanin, Republic of Serbia;

- 3-days International Scientific Conference "Integrated Solutions regarding Environment Protection by Preventing and Reducing Agroindustrial Pollution" September 2020 in Zrenjanin, Republic of Serbia;

- 3-days Training „Analysis and use of meteorological factors in purpose of environment protection“ June 2020 in Zrenjanin, Republic of Serbia;

- Project Closing Seminar on November 2020 in Zrenjanin, Republic of Serbia.

### Geographical area to be covered

Events will be organized in Republic of Serbia (city of Zrenjanin,). Participants of the events are from programme participating countries (Republic of Serbia, Romania) as well as countries of Danube region.

### Target groups

Representatives of local public authorities from cross border area, national authorities of Republic of Serbia and Romania, representatives of NGOs active in field of environmental protection, researchers and other representatives of higher education institutions, representatives of SMEs specialised in agricultural services as well as people interested in environmental protection and biodiversity preservation.

## Specific work

1. Organization of the Project Launching Seminar on March 2020 in Zrenjanin, Republic of Serbia

Project launching seminar aims to clearly present project objectives and expected results, primarily focusing on emphasizing the importance of cross border projects in the area of environmental protection and biodiversity preservation as an important element of sustainable development to the target groups and interested public. This event will promote the transfer of scientific know-how from institutions with expertise to the main actors of rural areas (local authorities, SME’s, NGO’s, rural community representatives).	
	
For the purpose of organisation of Project Launching Seminar the Contractor will provide the following services:

- Administrative support (Attendance list, distribution of promo material, Invitation and agenda)

- coffee break (coffee and tea, juice, mineral water, light canapé & sweets) for 50 participants

2. Organization of the International scientific conference "Integrated Solutions regarding Environment Protection by Preventing and Reducing Agroindustrial Pollution", September 2020 in Zrenjanin, Republic of Serbia

International Scientific conference „Integrated Solutions regarding Environment Protection by Preventing and Reducing agroindustrial pollution" will gather 40 scientists from Danube countries acting in environmental protection and other areas tangent to ecology. They will present 30 scientific papers in Zrenjanin with the topic of the conference generic. After the conference and review a volume will be published containing the papers presented in plenary. The objectives of this activity are the exchange of experience, knowledge and expertise to ensure project continuity and multiplication and development of similar environment monitoring systems.

The conference will take place in Zrenjanin during 3 days and will include plenary session, section sessions, workshop Researchers will present their achievements in previous activities and will answer to the public in open sessions (30 research papers). Volume of research papers: International scientific committee and organizing committee after scientific reviewing will publish the results from presented papers in a volume designated for researchers, public authorities SMEs, NGOs and other public entities interested in environment protection.

For the purpose of organisation of International scientific conference "Integrated Solutions regarding Environment Protection by Preventing and Reducing Agroindustrial Pollution” the Contractor will provide the following services:

- Provide adequate space for

- Plenary session for 50-60 participants, first day

- Section sessions (3) second day

- Workshop (tutorial(s)) third day

- Provide adequate equipment for presentation and normal work

- Lap top, projector, flip chart and sound system for plenary session

- 3 lap tops, 3 projectors and 3 flip charts for section sessions

- Lap top, projector and flip chart for tutorial(s)

- Logistics for conference itself including receiving desk, equipment operators, conference material distribution, refreshment distribution on the pauses.

- Moderators (facilitators for professional leading the sessions)

- Moderators will be non-key expert but with proven knowledge about conference thematic and knowledge of English language, Romanian language will be assets.

- Provide 2 refreshments on the pauses for the first and second day and 1 for the third day.

In the preparatory period from signing the contract to the end of conference Contractor will provide administrative support to International scientific and organizing committees for:

- Conference paper providing,

- Communication with paper writers (Announcement, invitation, technical information)

- Collecting of the papers

- Recension of the papers by the consultant with adequate CV in plant protection

Adequate CV means PhD in the area of Agriculture Biology or Plant protection, min 5 years’ experience after PhD providing in academic or research organization(s), knowledge of English).

- Design of papers for printing

- Printing joint volume in 200 pieces

- Papers from plenum session in full form and

- Papers from section sessions in the form of summary

Conference proceedings will be printed on A4 format on 80 g paper with covers in full colour on 300 g cartoon. Proceedings will be designed in accordance with the visibility rules for INTERREG IPA CBC Romania-Serbia programme. Expected size of Proceedings is 60-70 pages.

For 40 participants Contractor will organize accommodation in one-bed rooms in the hotels with 4*** as follows

- first day lunch, dinner, overnight

- second day, breakfast, lunch, dinner, overnight

- third day – breakfast and lunch

Contractor will organize transport of paper presenters

- from Belgrade to Zrenjanin and vice versa

- from Timişoara to Belgrade and vice Versa

For transport Contractor will provide vehicles, no older of 6 years, with 30 seats, experienced driver and for Timişoara destination all necessary permits for border cross.

3. Organisation of the training „Analysis and use of meteorological factors in purpose of environment protection“ on June 2020 in Zrenjanin, Republic of Serbia

This training is addressed to research, water management and environmental protection institutions. 20 representatives of those institutions, from both sides of the border will participate in this activity, which takes place in Zrenjanin for 3 days. The objective of this training is education and training stakeholders to use and improve the weather monitoring system and interpretation of meteorological factors in order to take prevention measures in case of increased risk of ponding, floods or other natural disasters caused by weather conditions and climate change. Also, informing the local population about ecological issues and the inclusion of partners in a network for environment protection by reducing agro industrial pollution.	
For the purpose of organisation of training „Analysis and use of meteorological factors in purpose of environment protection“ the Contractor will provide the following services:

- Space for 25 persons with possibilities to temperature regulation in the range of 20-220C. Space will be equipped with video projector and screen, flipchart, lap top, Wi-Fi internet access.

- Refreshment on pauses  6 (2 per day) (coffee and tea, juice, mineral water,) for participants and trainers;

- Buffet lunch for 3 days for participants and trainers. Buffet lunch will should include (at least) appetizer, main course, salad, dessert and 1 soft drink. Offer for buffet lunch must include vegetarian/vegan/special diet option;

- Transport for Romanian participants (Timişoara-Zrenjanin-Timişoara). For transport Contractor will provide vehicles, no older of 6 years, with 12 seats, experienced driver and all necessary permits for border cross.

e) Accommodation for Romanian participants. For 10 participants Contractor will organize accommodation in one-bed rooms in the hotels with 4*** as follows

- arrival day dinner and overnight

- first day breakfast, dinner, overnight

- second day, breakfast, dinner, overnight

- third day – breakfast

- course delivery for 2 trainers

B. Training Curricula and Guide

- Contractor will produce content summary of the training in the form of curricula

- Contractor will propose 2 trainers for the proposed curricula

- Min. bachelor degree in agriculture, biology or similar science; 5 years experiences in the area and 2 trainings with same or similar thematic.

- Contractor will write and distribute Guide for the participants of the training and after-training use in the size of 30-40 pages designed to be print or use in electronic way

4. Organisation of Project Closing Seminar on November 2020 in Zrenjanin, Republic of Serbia.

Closing Seminar will take place in Zrenjanin City Hall and will be focused on project results presentation in the context of new approaches and for proposals of new cooperation projects in the cross-border area.

For the purpose of organisation of Project Closing Seminar the Contractor will provide the following services:

a)	Administrative support (Attendance list, distribution of promo material, Invitation and agenda)

b)	coffee break (coffee and tea, juice, mineral water, light canapé & sweets) for 50 participants

## Project management

### Responsible body

City of Zrenjanin, Mayor

### Management structure

Contracting Authority’s management structure regarding this contract:

1. Legal representative / Authorized Person, for signing the contract and related decisions

2. Project Manager, responsible and authorized for 1st level of communication with the Contractor and for submitting decisions for approval to the Legal representative.

### Facilities to be provided by the Contracting Authority and/or other parties

Not applicable

# LOGISTICS AND TIMING

## Location

Operational base for the project will be in City of Zrenjanin, Republic of Serbia. Locations of activities are determined in point 4.2. Specific work.

## Start date & Period of implementation of tasks

The intended start date is March 10th 2020 and the period of implementation of the contract will be 9 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Not applicable.

## Facilities to be provided by the Contractor

The Contractor must ensure that is adequately supported and equipped in order to ensure smooth implementation of contract and fulfil contractual obligations.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original:

- Interim Report of maximum 5 pages to be produced after 1 month from the start of implementation. In the report the Contractor will describe initial findings, progress in collecting data and results of the 1st event - Project Launching Seminar,

- II interim report after finishing 3-days training of maximum 5 pages (main text, excluding annexes) in free format.

- III Interim report after International scientific conference will be realised. feedback questionnares, photo galleries and all other published and recorded material). The final report must be provided along with the corresponding invoice as well as documents and materials for each event as evidence of work done (e.g attendance sheets,

- Final report after completing the contract after realisation of Project Closing Seminar

- The reports must be provided along with the corresponding invoice as well as documents and materials for each event as evidence of work done.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Provided successful organisation of the events for the needs of project CLINSIM - Integrated management of relationship climate - insect migration in Srednjebanatski district and Timis County, RORS-380, as defined within activities determined in point 4.2. Specific work.

## Special requirements

Not applicable.