ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania and Republic of Serbia (the eligible area of the Interreg - IPA Cross-border Cooperation Romania-Serbia Programme).

## Contracting Authority

Deta Municipality

## Country background

Based on UNICEF data: Population drops in 86% of Serbia’s villages; every other rural child (45.1%) faces deprivation, and 76% of unemployed women in rural areas have never heard of any active labor market measures. For decades, young people are migrating from rural to urban areas. However, for the last 10 years, there is a large number of youth which are leaving the country, searching for better jobs. The same situation is in Romania, where youth are leaving their countries, especially rural areas, and moving to more developed European countries or even USA and Canada.

## Current situation in the sector

Through this project, both partner’s municipalities are expecting to provide necessary conditions for youth to stay in their birthplaces, to establish their businesses and to build their families there. Also, to enable other unemployed (women, hardly employable categories) to start some businesses, as major or additional jobs. Dealing with the outflow of population is not a new story, but the way we were dealing with is totally new and innovative. So, instead to forbid young people to leave, we will offer them great conditions for staying – access to well-paid jobs, education, necessary infrastructure. To achieve our goals and results we are planning we will have to take cross-border approach. With this approach we will involve Romanian and Serbian institutions, companies, schools and unemployed persons cooperating on the mutual goal: establishing pre-conditions for employment opportunities in the rural area of cross-border region. Municipality of Coka and Municipality of Deta are similar in number of inhabitant, also they are both rural agricultural area with most population acting in this field. Taking into account that those two municipalities are similar in many ways, it was natural that they have similar problems. All these lead to the joint project proposal and establishment of partnership between these two municipalities. By establishing Regional Employment Center, with offices in both municipalities, we will implement several different sets of trainings in order to provide conditions for new jobs in our municipalities.

## Related programmes and other donor activities

It is not the case.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is follow:

Creating environment for joint initiatives, cooperation and coordination for removing of obstacles to the keeping of youth in the rural area of cross-border region Romania – Serbia, by practical usage of Nudge theory. Through this project, both partner’s municipalities are expecting to provide necessary conditions for youth to stay in their birthplaces, to establish their businesses and to build their families there. Also, to enable other unemployed (women, hardly employable categories) to start

some businesses, as major or additional jobs. Dealing with the outflow of population is not a new story, but the way we were dealing with is totally new and innovative.

## Purpose

The purposes of this contract are to organize the following types of trainings:

LOT 1 – English language training

LOT 2 – IT trainings

LOT 3 – Web trainings

LOT 4 – How to establish SME training

LOT 5 – Old crafts training

LOT 6 – Education in rural tourism training

LOT 7 – Train the Trainers for PCM training

## Results to be achieved by the Contractor

Providing in the best conditions of all the trainings services that are described in detail in point 4.2 Specific work.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The places of development will be Deta local REC and the days in which the trainings program take place will be communicated to the Contractor in due time before the starting. The Contracting Authority will provide premises with equipment at REC local office for the realization of training programs in good conditions.

## Risks

Shifting the training events data for reasons not related to the Contracting Authority.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Contractor/s must provide training services for the following types of training programs: English language training, IT trainings, Web trainings, How to establish SME training, Old crafts training, Education in rural tourism training and Train the Trainers for PCM training. All training sessions will be held at the Regional Employment Center from Deta.

### Geographical area to be covered

Romanian side eligible area of the Interreg-IPA CBC Romania-Serbia Programme.

### Target groups

The target public is made up of unemployed young people in rural areas, women from rural areas, and people with disabilities from Deta  and from neighboring localities in the eligible area of the Interreg-IPA CBC Romania-Serbia Programme.

## Specific work

The Contractor is tasked to ensure the following services:

LOT 1 – English language training

Description of expected outputs / results to be achieved

3 English language trainings will be organised (beginners, intermediary, advanced), each training having minimum 36 days for groups of minimum 10 people each,  144 hours each

Required inputs

For expected outputs the Contractor must ensure qualified and sufficient staff to provide all services.

The Contractor must have relevant experience in the field required by the activities described below.

Contractor will prepare methodology and content for trainings in line with the identified training needs.

Developed training will be approved by the Project Manager from Contracting Authority.

At the end of the Training the Contractor will provide to the Contracting Authority the list of participants together with other outputs of the training.

Required time frame

Estimated period: 12-18 weeks starting from February 2020

Specific dates to be communicated by the Contracting Authority in due time.

LOT 2 – IT trainings

Description of expected outputs / results to be achieved

1 IT training for beginners to be organised (MS Office - MS Word, MS Excel, MS Power Point) having minimum 36 days for a group of minimum 20 people, 144 hours

Required inputs

For expected outputs the Contractor must ensure qualified and sufficient staff to provide all services.

The Contractor must have relevant experience in the field required by the activities described below.

Contractor will prepare methodology and content for trainings in line with the identified training needs.

Developed training will be approved by the Project Manager from Contracting Authority.

At the end of the Training the Contractor will provide to the Contracting Authority the list of participants together with other outputs of the training.

Required time frame

Estimated period: 12-18 weeks starting from February 2020

Specific dates to be communicated by the Contracting Authority in due time.

LOT 3 – Web trainings

Description of expected outputs / results to be achieved

- 2 trainings will be organised (Web developer, web design), each training having minimum 96 days for a group of minimum 10 people each,  384 hours each

- 1 training will be organised for IT jobs (blogger, vlogger, youtuber) having minimum 36 days for a group of minimum 15 people. 144 hours – online mentoring for 3 months, for 15 people

- Organising a one-day motivational seminar for a group of minimum 50 people 4 hours

- Ensuring online mentoring for the development of online applications for the participants from the trainings on web developer and web design. The mentoring will be offered for a group of minimum 10 people and will last minimum 36 days.

Required inputs

For expected outputs the Contractor must ensure qualified and sufficient staff to provide all services

The Contractor must have relevant experience in the field required by the activities described below.

Contractor will prepare methodology and content for trainings in line with the identified training needs.

Developed training will be approved by the Project Manager from Contracting Authority.

At the end of the Training the Contractor will provide to the Contracting Authority the list of participants together with other outputs of the training.

Required time frame

Estimated period:

- 32-48 weeks starting from February 2020 for the web developer and web design course

- 12-18 weeks starting from February 2020 for the IT jobs training

- one day motivational seminar organised between February 2020 and March 2020

- 12-18 weeks starting from February 2020 for the mentoring

Specific dates to be communicated by the Contracting Authority in due time.

LOT 4 – How to establish SME training

Description of expected outputs / results to be achieved

2 trainings sessions will be organised:

- one training lasting 4 days on entrepreneurship for a group of minimum 15 people 16 hours

- one training lasting 4 days on “how to establish SME in the IT field” for a group of minimum 15 people 16 hours

Required inputs

For expected outputs the Contractor must ensure qualified and sufficient staff to provide all services

The Contractor must have relevant experience in the field required by the activities described below.

Contractor will prepare methodology and content for trainings in line with the identified training needs.

Developed training will be approved by the Project Manager from Contracting Authority.

At the end of the Training the Contractor will provide to the Contracting Authority the list of participants together with other outputs of the training.

Required time frame

Estimated period: 4 days in May-June 2020

Specific dates to be communicated by the Contracting Authority in due time.

LOT 5 – Old crafts training

Description of expected outputs / results to be achieved

One old crafts training (handicrafts) will be organised having minimum 72 days for two groups of minimum 10 people each, 144 hours each

Required inputs

For expected outputs the Contractor must ensure qualified and sufficient staff to provide all services.

The Contractor must have relevant experience in the field required by the activities described below.

Contractor will prepare methodology and content for trainings in line with the identified training needs.

Developed training will be approved by the Project Manager from Contracting Authority.

At the end of the Training the Contractor will provide to the Contracting Authority the list of participants together with other outputs of the training.

Required time frame

Estimated period: 72 days: 24-36 weeks starting from February 2020

Specific dates to be communicated by the Contracting Authority in due time.

LOT 6 – Education in rural tourism training

Description of expected outputs / results to be achieved

One training in rural tourism will be organised having minimum 36 days for two groups of minimum 15 people each, 144 hours each

Required inputs

For expected outputs the Contractor must ensure qualified and sufficient staff to provide all services.

The Contractor must have relevant experience in the field required by the activities described below.

Contractor will prepare methodology and content for trainings in line with the identified training needs.

Developed training will be approved by the Project Manager from Contracting Authority.

At the end of the Training the Contractor will provide to the Contracting Authority the list of participants together with other outputs of the training.

Required time frame

Estimated period: 12-18 weeks starting from February 2020

Specific dates to be communicated by the Contracting Authority in due time.

LOT 7 – Train the Trainers for PCM training

Description of expected outputs / results to be achieved

One 10 days Project Cycle Management Training for Trainers will be organised for a group of minimum 10 people 40 hours

Required inputs

For expected outputs the Contractor must ensure qualified and sufficient staff to provide all services.

The Contractor must have relevant experience in the field required by the activities described below.

Contractor will prepare methodology and content for trainings in line with the identified training needs.

Developed training will be approved by the Project Manager from Contracting Authority.

At the end of the Training the Contractor will provide to the Contracting Authority the list of participants together with other outputs of the training.

Required time frame

Estimated period: 10 days between March-May 2020

Specific dates to be communicated by the Contracting Authority in due time.

## Project management

### Responsible body

The department of the Contracting Authority responsible for managing the contract / project is Grebeldinger Daniel.

### Management structure

The project team is responsible for the decisions taken during the implementation period. The project manager must discuss the decisions taken with the mayor of Deta Municipality.

### Facilities to be provided by the Contracting Authority and/or other parties

Not applicable.

# LOGISTICS AND TIMING

## Location

The location of the operational base for the project will be in Deta, Timis County, Romania.

## Start date & Period of implementation of tasks

The intended start date is the second period of February 2020 and the period of implementation of the contract will be until end of July 2020 from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation. A possibility of an extension should be if the project requires extension or further services upon satisfactory performance or if any influence by external elements. The final decision should be implement only if the Contracting Authority approve.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

### All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

LOT 1 – English language training

Key expert - English language teacher/ adult education trainer

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience in teaching/training field;

Specific professional experience

•	English language certificates;

LOT 2 – IT trainings

Key expert - IT teacher / IT expert

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience in IT field;

Specific professional experience

•	Recognised diploma who have also adult education training;

•	Diploma to certify the  specialization in the IT field;

LOT 3 – Web trainings

Key expert 1 and Key expert 2 - For the two trainings at least one IT teacher/ expert in the field having a diploma on web development/ web design for each training.

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience in IT teacher / expert field;

Specific professional experience

•	Diploma to certify the  specialization in IT field

•	Experience in training field

Key expert 3 - For the IT jobs training at least one IT teacher/ expert in the field having a diploma on social media communication, web development

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience social media communication or web development fields;

Specific professional experience

•	Diploma to certify the  specialization in the social media communication or web development

Key expert 4 and 5 - For the motivational seminar to ensure a team of two experts (sociologists/ psychologists) who to deliver this seminar

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience in sociology / psychology field;

Specific professional experience

•	Experience in organising and support of motivational seminars, at least one event in the last 2 years;

LOT 4 – How to establish SME training

Key expert 1 -   one expert in entrepreneurship experimented consultant/ teacher on business development/ expert accountant/ professional trainer for the entrepreneurship training.

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience in entrepreneurship field;

Specific professional experience

•	Experience in entrepreneurship consultancy field;

•	Experience in training field;

Key expert 2 - one IT entrepreneur/ IT business manager/ professional trainer for the training about how to establish SME in the IT field

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience in IT business;

Specific professional experience

•	Experience in training about how to establish SME in the IT field;

LOT 5 – Old crafts training

Key expert 1 - specialist in making baskets from woven wicker

Qualifications and skills

•	Very good planning and organisational skills;

General professional experience

•	At least 2 years of making baskets from woven wicker;

Specific professional experience

•	Experience in woven wicker;

Key expert 2 - specialist in the field of potter

Qualifications and skills

•	Very good planning and organisational skills;

General professional experience

•	At least 2 years of making objects specific to the potter;

Specific professional experience

•	Experience in making clay objects using traditional techniques;

LOT 6 – Education in rural tourism training

Key expert - One expert in tourism

Qualifications and skills

•	Very good planning and organisational skills;

General professional experience

•	At least 2 years of professional experience in tourism field;

Specific professional experience

•	Diploma that certifies the specialization in tourism;

•	Experience in training field in the last 2 years;

LOT 7 – Train the Trainers for Project Cycle Managament (PCM) training

Key expert - One professional trainer / expert in management/ project manager

Qualifications and skills

•	Very good planning and organisational skills;

•	English language fluency;

General professional experience

•	At least 2 years of professional experience in project management field;

Specific professional experience

•	Diploma that certifies the specialization in management;

•	Diploma that certifies the specialization in training;

Note: Evaluation of experts: there is no specific evaluation criterion for the key experts but the assessment is part of the strategy.

### Other experts, support staff & backstopping

The contractor will ensure sufficient number of qualified experts for quality and timely implementation of tasks planned by these Terms of References. These experts are considered as non-key experts therefore their CVs are not examined prior to the signature of the contract and should not be included in the tender.

The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor (if it is necessary) and will be included in the global price.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and 1 copy:

- Inception Report  - Not applicable

- Interim reports The contractor must prepare interim reports after providing the services for each training, according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments as indicated in the Special Conditions.

- Draft final report  - Not applicable

- Final report This report will be realized after the last training service realized during the period of implementation of the contract; as in the case of interim reports, the approval of final report by the Contracting Authority will be the basis for issuing the final invoice and making the final payment as indicated in the Special Conditions.

## Submission and approval of reports

The reports referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manner, as required in these Terms of Reference”.

## Special requirements

Not applicable.