ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia (the eligible area of the Interreg - IPA Cross-border Cooperation Romania-Serbia Programme).

## Contracting Authority

Municipality of Kladovo

## Country background

The main fields of the cross-border area and the Danube Region are: socio-economic development, mobility, energy, natural and cultural resources, risks of environmental catastrophes. Among these areas can be mentioned the preservation of environmental resources, biodiversity, landscape; development of renewable energy sources, increase of accessibility and connectivity, reduction of localized pollution sources, promotion of smart innovation initiatives.

Based on the project theme our analysis underlines the common territorial challenges that will be tackled by the project:

· In the project area the main potentials of action are identified in the fields of environment protection, SMART innovation, accessibility and renewable energy;

· Most of these areas can aim to a synergic interaction within the Danube Region;

· Regarding the economic sectors, energy sector is very important and main characteristics are: very large hydro electrical power capacity on the Danube centrals, and some small plants in the other rivers, some potential of development in renewable resources, in particular biomass in the central and south eastern areas.

· Education, research and innovation; The educational system is experiencing intensive structural changes in both countries; The eligible area presents an unequal distribution of higher education and research poles; Many research centres in the Romanian area, fewer on the Serbian side; Common needs of improvement of the effectiveness and quality results of education;

· Interreg IPA CBC Romania-Serbia defines certain conclusions that are closely associated with the project proposal and which our project entirely relies on:

1) In area existing potentials for renewable energy development on both side of the border;

2) Needs to protect of the environment and the elimination and mitigation of existing environmental hotspots and hazards and the adaptation for new risks is considered an absolute prerequisite for any development plan;

3) Highly relevant since it combines important conditions for the stabilisation of the population and the realisation of sustainable development by addressing attractive employment opportunities, provision of health and social services and inclusive society.

## Current situation in the sector

Today’s definition of a modern state is determinate by following aspects, Population, Territory, Sovereignty, and Government, in order to enable functionality of all four, indispensable aspect is establishment of strong economy.

Today there is a more than 30 countries in the world that are carrying epithet of a modern state, and their economic development as well as the tendency of the rest of the world, to acquire the mentioned level of a development, triggered new problems, which now are representing the biggest threat in mankind history. Global warming forced humanity to a moral radical change in a manner of identifying new energy sources which will satisfy needs of a modern societies and decrease the level of above-mentioned problem.

Danube region due to its natural resources has a great potential for development of renewable power centres and as well as to secure its environmental resources, biodiversity of flora and fauna.

Regarding the economic sectors, CBC region of Municipality of Kladovo and Drobeta-Turnu Severin are disposing with very large hydro electrical power capacities on the Danube centrals and some other smaller rivers in this region. Due to this renewable energy potentials, and the lack of education, research and innovation in this field especially on the Serbian side, created a need for improvement of this aspects.

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective: To stimulate an enabling environment for community development, as well as to empower public, business and civil sector to be effective and accountable actors in sustainable energy development, rational using natural resources and reduction climate changes, based on the partnership and implementation EU principals.

## Purpose

The purposes of this contract are as follows:

- Support to adequate realization of project activities

- Studies,experts,manuals and technical documentation

## Results to be achieved by the Contractor

- Building a cross-border networks of information and communications

- The identification and transfer local inovation in the use of renewable energy

- Preparation manual “Database of energy efficiency measures in small and medium-sized enterprises”

- Design and printing manual “Database of energy efficiency measures in small and medium-sized enterprises”

- Preparation energy passports and technical documentations for energy efficency improvement for 5 public buildings and 5 buildings for collective housing in Kladovo Municipality

- Expert support in Energy HUB establishment

- Prepared joint study about available wooden biomass energy potential in the region of Dobrota-Turn Severin and Kladovo

- Preparation feasibility study and technical documentation for using wooden biomass collected in dump of hydropower “Djerdap I” for heating

- Preparation Sustainable Energy Action Plans for Municipality of Kladovo

- Preparation technical documentation for using renewable energy (heat pumps) in 5 public institutions

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Contracting Authority provides tenderer with statistical data from their jurisdiction

## Risks

Communication issues.

COVID-19 issues

# SCOPE OF THE WORK

## General

### Description of the assignment

- Building a cross-border networks of information and communications

- The identification and transfer local innovation in the use of renewable energy

- Preparation manual “Database of energy efficiency measures in small and medium-sized enterprises”

- Design and printing manual “Database of energy efficiency measures in small and medium-sized enterprises”

- Preparation of energy passports and technical documentations for energy efficency improvement for 5 public buildings and 5 buildings for collective housing in Kladovo Municipality

- Expert support in Energy HUB establishment

- Prepared joint study about available wooden biomass energy potential in the region of Dobrota-Turn Severin and Kladovo

- Preparation feasibility study and technical documentation for using wooden biomass collected in dump of hydropower “Djerdap I” for heating

- Preparation Sustainable Energy Action Plans for Municipality of Kladovo

- Preparation technical documentation for using renewable energy (heat pumps) in 5 public institutions

### Geographical area to be covered

Municipality of Kladovo.

### Target groups

Local public authorities, general audience, employees from public enterprises, sectoral agencies, students from primary and secondary schools.

## Specific works

## The Contractor is tasked to ensure the following:

Contractor shall implement following types of tasks

- Building a cross-border networks of information and communications

Establishment a cross-border network of information and communications. The action will support establishing network of information and communication in environment sector and energy sector. The project partners will initiate networking process, but through participatory process will be animated other relevant stakeholders from all three sectors (public, civil and business) to join initiative. Expert 1 will be engaged for period of 20 days in total during the 6 month period in order to establish a cross-border network of information and communication. Expert will be responsible for development rules and procedures for functioning a cross-border network. Expert will attend on 4 meetings (2 in Serbia and 2 in Romania) in aim to collect needs of stakeholders and target group members related to establishment of cross-border network. Tenderer is obliged to organize abovementioned 4 meetings in accordance with schedule received from Contracting Authority at most 20 days upon Contract signature. Expert will present results of the engagement to project team members at the end of the period of 6 months.

- The identification and transfer local innovation in the use of renewable energy

Tenderer shall provide service for identification research about good practice and local innovative ideas related to use renewable energy. Identification research should not be bigger than 10 page A4 format document and shall contain all relevant information regarding good practice and local innovative ideas related to use renewable energy. Good practice and local innovative ideas should be shall be identified from regions with similar characteristics as cross-border region Romania-Serbia. Tenderer will present results of the engagement to project team members at the end of the period of 3 months

- Preparation manual “Database of energy efficiency measures in small and medium-sized enterprises”

Tenderer will produce manual “Database of energy efficiency measures in small and medium-sized enterprises” in the average volume of 20-30 pages A4 format. Manual will assist owners and managers in small and medium enterprises in order to implement new procedures and practices of energy efficiency measures on more effective way. Tenderer will present manual “Database of energy efficiency measures in small and medium-sized enterprises” to project team members at the end of the period of 4 months.

- Design and printing manual “Database of energy efficiency measures in small and medium-sized enterprises”

- Tenderer shall design and print  manual “Database of energy efficiency measures in small and medium-sized enterprises”. Tenderer shall prepare 750 copies of the manual  (350 in Serbian, 350 in Romanian and 50 in English). The Contracting Authority shall provide tenderer with text, pictures and diagrams for successful design and printing in electronic format. Tenderer will prepare draft version of designed document and send it to CA for approval. Upon CA approves the design, Tenderer shall print all 750 copies in A4 format. Tenderer will also deliver electronic version of the manual to Contracting Authority in format ready to publish on the CA web site. Activity shall be completed during the 3 months upon CA provides tenderer with all relevant documentation for design and printing.

- Preparation energy passports and technical documentations for energy efficency improvement for 5 public buildings and 5 buildings for collective housing in Kladovo Municipality

- Energy passport of the building is certificate which contains information about the energy class of the building and points to the final annual consumption of thermal energy for heating. Building energy passport shall contains 5 pages, but the most important are first, second and fourth. On the first page shall be general information about the object, such as the owner's name, particulars, location, name of architect, photos of the building, and to learn about its energy class. Building's energy class is determined on the basis of data on energy consumption for heating per year, calculated in accordance with the regulation governing the energy performance of buildings. On this basis, the building is classified into energy classes from A + with the lowest (≤15 kWh / m2a) to G with the highest energy consumption (> 250 kWh / m2a). The other side of passport shall contains climate data, information on systems and elements of the thermal layer, and data about the insulation, and windows that are set on the object. The third page shall contains a detailed budget of energy consumption, so that can be assumed what are the expected costs. The fourth side shall contains appropriate measures for improving the energy efficiency of the building. For each object that is not Class A, on this side there must be written recommendations by engineers, how to improve the situation in the future. Certificate, or the energy passport, are issued by engineers, persons who have passed the professional exam and who possess the license 381.

- Expert support in Energy HUB establishment

- The activity covering Expert 2 engagement for supporting Energy Hub development and also for his functioning in pilot phase. Engaged Expert 2 will be engaged  totally 75 working days. In cooperation with secondary schools from the project area will be established and equipped training center in Technical school Kladovo. The school will provide one room with 30 working places for installation equipment and necessary software. Also during establishing process Expert will developed curriculum for several educations, adapted to target groups: unemployed, youth and stakeholders with needs for extra education or professional prequalification. The training center also will be used by students of Technical school Kladovo and other professional schools from area. New Hub shall contributing to new technologies using and also support to transfer knowledge to unemployed and interested stakeholders. Also through this outputs it’s supported potential for employment and small business development. Expert 2 shall prepare procedures for establishing Energy Hub and develop program for Hub functioning. Activities and services of Energy Hub shall be defined by Expert 2 in aim to secure Hub sustainability.

- Prepared joint study about available wooden biomass energy potential in the region of Dobrota-Turn Severin and Kladovo

- Study shall be prepared by the tenderer in aim to establish procedures for local communities to prepare measures for reduction emission green-house gases and negative effects on climate changes in cross-border region. Joint study shall contains all relevant data based on research  about available biomass energy potential in municipalities Kladovo and Drobeta Turnu Severin. Experts engaged by tenderer shall include available existing data for biomass energy potential and level of current usage in those 2 municipalities. The study should provide guidance on the future use of biomass in the cross-border region as well as data on the reduction of emissions into the atmosphere. Tenderer will produce joint study about available wooden biomass energy potential in the region of Dobrota-Turn Severin and Kladovo in the average volume of 20-30 pages A4 format.

- Preparation feasibility study and technical documentation for using wooden biomass collected in dump of hydropower “Djerdap I” for heating

- A feasibility study for using wooden biomass collected in dump of hydropower “Djerdap I” for heating shall be an assessment of the practicality of a proposed plan or project. Study shall answer following questions: Is this project feasible? Do we have the people, tools, technology, and resources necessary for this project to succeed? Will the project get us the return on investment (ROI) that we need and expect?

- The goals of feasibility study are as follows:

- To understand thoroughly all aspects of a project, concept, or plan

- To become aware of any potential problems that could occur while implementing the project

- To determine if, after considering all significant factors, the project is viable—that is, worth undertaking

Feasibility study shall reflect a project's unique goals and needs, so each is different. Tenderer shall do the following:

- Get feedback about the new concept from the appropriate stakeholders

- Analyze and ask questions about data to make sure that it's solid

- Conduct a market survey or market research to enhance data collection

- Prepare a projected income statement

- Prepare an opening day balance sheet

- Make an initial "go" or "no-go" decision about moving ahead with the plan

- Tenderer shall include in the study:

- Executive summary: Formulate a narrative describing details of the project, product, service, plan.

- Technological considerations: What will it take. Do you have it? If not, can you get it? What will it cost?

- Existing marketplace: Examine the local and broader markets for the product, service, plan, or business.

- Marketing strategy: Describe it in detail.

- Required staffing (including an organizational chart): What are the human capital needs for this project?

- Schedule and timeline: Include significant interim markers for the project's completion date.

- Project financials.

- Findings and recommendations: Break down into subsets of technology, marketing, organization, and financials.

- Preparation Sustainable Energy Action Plans for Municipality of Kladovo

- The action plan (both SEAP and SECAP) is the key document which shows how the Covenant signatory will reach its vision and target. The plan includes an assessment of the current situation, i.e. a Baseline Emission Inventory for the climate mitigation part (both SEAP and SECAP) and a Risk and Vulnerability Assessment for the adaptation part (For SECAP only); clearly identified goals and targets; and the measures planned together with time frames, assigned responsibilities and estimated impacts.

Scope of action:

The Covenant of Mayors concerns the action at local level within the competence of the local authorities involved. Hence, it is expected that the Covenant signatories will take action in several or all of their possible roles:

- Consumer and model: All local authorities are responsible for their own energy consumption. At the same time, they play an exemplary role by encouraging citizens and other stakeholders to use energy more efficiently.

- Planner, developer and regulator: All local authorities are usually responsible for building, transport and land use planning policies. They have the power to: optimize the energy performance of new facilities, integrate sustainable transport measures and adaptation strategies in local planning practice. They shape transport/energy performance by legal decisions and regulatory instruments.

- Producer and supplier: Local authorities may also act as a local utility or service provider promoting local energy production and using renewable energy sources (e.g. Combined Heat and Power/CHPs, district heating systems etc.).

- Advisor and motivator: Awareness-raising activities are important to engage the whole community to support sustainable energy and climate policies. Local authorities can act as advisor and educator for citizens and other stakeholders (e.g. architects, planners or craftsmen).

Since the Covenant's commitments concern the whole geographical area of the local authority, the action plan should include actions that cover the sectors of activity from both public and private actors. Covenant signatories are free to choose their main areas of action. In principle, it is anticipated that most action plans will cover the sectors that are taken into account within the emission inventory and risk and vulnerability assessment (for SECAP only). For the mitigation part (both SEAP and SECAP): It should include actions targeting the Covenant key sectors:

- Municipal buildings, equipment/facilities;

- Tertiary (non municipal) buildings, equipment/facilities

- Residential buildings

- Transport.

- Actions should also be included for other sectors such as:

- Industry;

- Local electricity production;

- Local heat/cold production;

- Others (e.g. Agriculture, Forestry, Fisheries).

For the adaptation part (For SECAP only):

Identification of the sectors to increase the resilience in a city is highly contextual. A solid and comprehensive climate adaptation strategy therefore involves thinking adaptation into all aspects of municipal services affected by climate change. Some of the main sectors that can improve the resilience of cities include:

- Infrastructure

- Public Services

- Land Use Planning

- Environment & Biodiversity

- Agriculture & Forestry

- Economy.

- Preparation of technical documentation for using renewable energy (heat pumps) in 5 public institutions

- A technical documentation for using heat pumps in 5 public institutions shall be developed by tenderer. 2 sets of technical documentation shall be prepared for public buildings in Drobeta Turnu Severin and 3 sets of technical documentation shall be developed for public buildings in Kladovo.

- Activity shall be implemented in a 5 month period in accordance with schedule communicated with Contracting Authority.

## Project management

### Responsible body

The Project management team will be responsible to manage the contract.

### Management structure

The responsible person is President of the Municipality. The Project is managed by the appointed Project team, consisted of team members from both beneficiaries.

### Facilities to be provided by the Contracting Authority and/or other parties

Not applicable.

# LOGISTICS AND TIMING

## Location

The location of the operational base for the project will be in Municipality of Kladovo.

The locations of each events will be communicated to the Contractor in a timely manner by the Contracting Authority.

## Start date & Period of implementation of tasks

The intended start date is 25.11.2020 and the period of implementation of the contract will be 5 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1

- University or Master Degree in Mechanical engineering or equivalent.

General professional experience

- At least 10 years of professional experience in fields related to environmental protection.

Specific professional experience

- At least 5 years of specific experience in the relevant field of renewable energy and/or energy efficiency;

- Energy efficiency in building licence or similar

- Prepared at least 1 feasibility study in energy efficiency field

- Participated in at least 3 projects in energy efficiency field

- Experience in the relevant field of designing of at least 2 strategic documents for last 3 years;

Key expert 2

- University or Master Degree in energy and energy efficiency

General professional experience

- At least 10 years of professional experience in fields related to renewable energy or environmental protection.

Specific professional experience

- At least 5 years of specific experience in the relevant field of renewable energy and/or energy efficiency;

- Participated in at least 2 projects in energy efficiency field

- Proven knowledge of EU public policies in the relevant field

- Experience in preparing of energy efficiency programs and/or action plans

### Other experts, support staff & backstopping

The contractor will ensure sufficient number of qualified experts for quality and timely implementation of tasks planned by these Terms of References. These experts are considered as non-key experts therefore their CVs are not examined prior to the signature of the contract and should not be included in the tender.

The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor (if it is necessary) and will be included in the global price.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original:

- Interim reports the contractor must prepare interim reports after providing the services for events, according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments as indicated in the Special Conditions.

- First interim report at the end 1st month of the contract implementation

- Second interim report in 3 month

- Final report in the 5th month.

- This report will be realized after the last event realized during the period of implementation of the contract; as in the case of interim reports, the approval of final report by the Contracting Authority will be the basis for issuing the final invoice and making the final payment as indicated in the Special Conditions.

- The reports should cover the implementation of the activities where the description of the realized activities should be provided alongside with the deliverables (outputs, photos, etc.).

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manner, as required in these Terms of Reference”.

## Special requirements

Not applicable.