PART A: INFORMATION FOR THE TENDERER

Name and address of the contracting authority: Provincial Secretariat for Regional Development, Interregional Cooperation and Local Self-Government Title of the tender: Development of the Detailed Regulation Plan for the Srpski Itebej-Otelek cross border point Reference number: 141-404-60/2021-04 Date of launching: 06/05/2021

- INFORMATION ON SUBMISSION OF THE TENDERS

Subject of the contract:

The subject of this tender is:

The contract includes development of the Detailed Regulation Plan for the Srpski Itebej-Otelek cross border point in the region of the Serbian-Romanian border. The service provider should prepare documentation and participate as a plan processor in the plan development procedure or to do as follows:

- prepare a Study - Conceptual framework of the plan that will be presented for early public inspection,

- participate in the early public inspection procedure, i.e. consider the objections received during the early public inspection, over the course of the preparation of the draft planning document,

-develop the draft plan, in accordance with the abovementioned acts,

- make a report on the performed public inspection and participate in the public session, after the conducted public inspection,

- prepare all stages of the document, in accordance with the received conditions of the competent public companies and the prescribed procedure and send them for final adoption.

Deadline for submission of the tenders:

The deadline for submission of tenders is 17/05/2021 at 13:00 hours. Any tender received after this deadline will be automatically rejected.

* - The tenderer should have minimum 7 days from the date of launching of the procurement procedure for preparation of the offer (excluding the day of publishing and the date of submission deadline).

Financial information

The tenderers are reminded that the maximum available value of the contract is 20.000,00 EUR .

The Financial offer must be presented as an amount in EUR and must be submitted using the template for the global-price version of PART C: FORMAT OF FINANCIAL OFFER.

The applicable tax and customs arrangements are specified in the draft contract in Part A of this tender dossier.

Variant solutions

Tenderers are not authorised to tender for a variant in addition to this tender.

Subcontracting

Subcontracting is not allowed.

Award criteria:

In case more than one offer received: best value for money, weighting 80% technical quality, 20% price.

Evaluation criteria for technical offer:

- Organization and methodology: 30 points

- Proposed inputs: 40 points

- Time frame: 30 points

TOTAL: 100 points

In case one offer received: the Contracting Authority shall check whether the offer is administratively, technically and financially compliant with the requirements set by this tender documentation.

Interviews:

No interviews are foreseen.

Award notification:

The successful tenderer will be informed of the results of the evaluation procedure in written form.

Contract award notice will be published on the programme web site. The estimated time of publishing is 7 days from the deadline for submission of tenders.

Address and meanings for submission of the tenders:

The tenderers will submit their tenders using the standard set of submission forms available in the Part B – Technical offer and the Part C - Financial offer. Any other document supporting this invitation is sent for informational purposes only and is not to be modified nor submitted by the tenderer. The tender will be submitted in 1 original. Any tenders not using the prescribed form may be rejected by the contracting authority.

In addition to the offer the tenderer is required to provide the following supporting documentation:

- Copy of legal registration

- Copies or valid expert licences

- Contract(s) or Certificate of reference

The tenders will be submitted in sealed envelopes, containing the following information:

- Name and address of the tenderer

- Title of the tender: Development of the Detailed Regulation Plan for the Srpski Itebej-Otelek cross border point

- Reference number: 141-404-60/2021-04

- The words: “Not to be opened before the tender opening session” (and “A nu se deschide inainte de sesiunea de deschidere”, “Ne otvarati pre sastanka za otvaranje ponuda”)

Tenders must be submitted using double envelope system, in an outer parcel or envelope containing two separate, sealed envelopes, one bearing the words "Technical offer”- part B and "Financial offer" - Part C.  Any infringement of this rule (e.g. unsealed envelopes or references to price in the technical offer) is to be considered a breach of the rule, and will lead to rejection of the tender.

The tenders will be submitted in person, by post or courier service to the following address:

Pokrajinski sekretarijat za regionalni razvoj, međuregionalnu saradnju i lokalnu samoupravu - Provincial Secretariat for Regional Development, Interregional Cooperation and Local Self-Government

Bulevar Mihajla Pupina 16

21000 Novi Sad

Republic of Serbia

The tenderers are reminded that in order to be eligible the tenders need to be received by the contracting authority by the deadline indicated above.

- TECHNICAL INFORMATION

The tenderers are required to provide services as indicated below. In the tenderer’s technical offer, the tenderers might indicate more details on the deliveries, referring back to the requirements below.

Title of activity: Development of the Detailed Regulation Plan for the Srpski Itebej-Otelek cross border point

Preparation of a Study for an early public inspection

  - Current situation analysis: Field data collection: Verification and compliance of obtained bases, the actual infrastructure, photo documentation, property and legal status of the lots in question. If needed create cadastral topographic plan.

  - Preparation of the study for an early public inspection and the preparation of the material for the collection of technical information from the holder of public authorisation.

Early public inspection

- It is announced in the media and lasts for 15 days.

- All remarks and suggestions of legal and natural persons are recorded by the planning document holder, and they can impact the planning solutions.

- Conditions and other important information for the preparation of a planning document are obtained from authorities, specific organisations, holders of public authorisation and other institutions.

Planning Commission - Report on the completed early public inspection

Drafting a Plan

- Drafting a textual and graphic part of the plan with precisely defined areas for public and other purposes, as well as defining rules for regulation and construction.

Planning Commission - Report on the completed expert inspection of the draft plan.

Public inspection

- The presentation of the planning document for public inspection is announced in daily and local newspapers and lasts for 30 days from the day of the announcement.

- All remarks and suggestions of legal and natural persons are recorded by the planning document holder, and they can impact the planning solutions.

Planning Commission - public discussion and the Report on the completed early public inspection of the draft plan

Final phase

- Synthesis of the final Draft Plan with all changes after the Planning Commission and public discussion following the public inspection of the Draft Plan.

- Packaging the Plan for the adoption by the Assembly.

Detailed Regulation Plan should be done in accordance with the Rulebook on content, manner and procedure of drafting spatial and urban planning documents (“Official Gazette of the RS”, no.  32/2019) and should contain a textual and a graphic part.

By the Decision on the development of the Detailed Zoning Plan for the Border Crossing Srpski Itebej – Otelek of the Assembly of Žitište Municipality, the approximate boundaries of the scope of the Plan were determined, while the final boundaries of the scope of the plan shall be defined by the Draft Plan.

The approximate boundaries of the scope of the Plan shall be defined by whole cadastral plots: 10827/1, 10827/2, 10828/1, 10828/2, 10829, 10830, 10826, 10831 and 10834 as well as by parts of the cadastral plots: 2027 and 10825.

The location of the said Plan is in the cadastral municipality of Srpski Itebej.

The total surface of the area covered by the approximate boundaries of the scope of the Plan shall be 46.83 ha.

According to Article 40 of the Law on Planning and Construction, at the request of the Ministry, APV and LSU and for the purposes of making the plan, cadastral, topographic and other substrates shall be provided free of charge. The municipality will give the power of attorney to the tenderer for submitting the request for substrates.

Pursuant to the Rulebook on content, manner and procedure of drafting spatial and urban planning documents (“Official Gazette of the RS”, no. 32/2019) consultant will prepare the Detailed Regulation Plan with textual and a graphic part.

Detailed Regulation Plan for the Srpski Itebej-Otelek cross border point must be written in English, Serbian and Romanian languages.

The Plan shall be done in 6 (six) copies in analogue format and 6 (six) copies in digital format in all the above languages, out of which one copy of the signed Plan in analogue format and one copy in digital format shall be kept by the Municipal Administration of Žitište Municipality, one copy of the signed Plan in analogue format and one copy in digital format shall be kept by the tenderers in their archives, one copy of the signed Plan in analogue format and one copy in digital format shall be kept by the contracting authority and the remaining copies shall be kept by the competent authorities of the Municipality.

The Consultant will be required to present the document on the Closing conference organized by the Contracting Authority.

Actitvity output:

- I Prepare a Study - Conceptual framework of the plan that will be presented for early public inspection,

- II Participate in the early public inspection procedure, i.e. consider the objections received during the early public inspection, over the course of the preparation of the draft planning document,

- III Develop the draft plan, in accordance with the abovementioned acts,

- IV Make a report on the performed public inspection and participate in the public session, after the conducted public inspection,

- V Prepare all stages of the document, in accordance with the received conditions of the competent public companies and the prescribed procedure and send them for final adoption.

Required inputs

The following selection criteria will be applied to the tenderers. In the case of tenders submitted by a consortium, these selection criteria will be applied to the consortium as a whole:

1)      Economic and financial capacity of the tenderer In case of tenderer being a public body, equivalent information should be provided. The reference period which will be taken into account will be the last three financial years for which accounts have been closed.

Legal persons:

· the average annual turnover of the tenderer must exceed the annualised maximum budget of the contract (ie, the maximum budget stated in the contract notice divided by the initial contract duration in years, where this exceeds 1 year);

2)  Professional capacity of the tenderer

Legal persons:

- The candidate has presently minimum 3 engaged or employed staff:

- Urban designer for managing the development of urban plans with relevant licence;

- Urban designer for managing the development of urban road plans with relevant licence;

- Urban designer for managing the development of urban infrastructure plans with relevant licence;

3)  Technical capacity of candidate

Legal persons:

-  The candidate has provided services under minimum one up to maximum three contracts with a cumulated budget of at least that of this contract in the fields related to this contract which were implemented at any moment during the reference period: 3 years from the submission deadline.

An economic operator may, where appropriate and for a particular contract, rely on the capacities of other entities, regardless of the legal nature of the links which it has with them. It must in that case prove to the Contracting Authority that it will have at its disposal the resources necessary for performance of the contract, for example by producing an undertaking on the part of those entities to place those resources at its disposal. Such entities, for instance the parent company of the economic operator, must respect the same rules of eligibility and notably that of nationality, as the economic operator.

- ADDITIONAL INFORMATION

The unsuccessful/successful tenderers will be informed of the results of the evaluation procedure.  In this sense the CA shall send a notification to the successful tenderer and post an announcement on the website with the name of the successful tenderer followed by the mentioning that “all other tenders were not administratively /technically/ financially compliant”

Confidentiality

The entire evaluation procedure is confidential, subject to the Contracting Authority’s legislation on access to documents. The Evaluation Committee’s decisions are collective and its deliberations are held in closed session. The members of the Evaluation Committee are bound to secrecy. The evaluation reports and written records are for official use only and may be communicated neither to the tenderers nor to any party other than the Contracting Authority, the European Commission, the European Anti-Fraud Office and the European Court of Auditors.

NOT TO BE FILED IN BEFORE CONTRACT SIGNING NOT TO BE SUBMITTED WITHIN THE OFFER!!!

FORMAT OF THE CONTRACT BETWEEN THE CONTRACTOR AND THE CONTRACTING AUTHORITY

CONTRACT TITLE: Development of the Detailed Regulation Plan for the Srpski Itebej-Otelek cross border point

REF: 141-404-60/2021-04

Concluded between:

Provincial Secretariat for Regional Development, Interregional Cooperation and Local Self-Government

Mihajlo Pupin Boulevard, 16

21000 Novi Sad

(Contracting Authority)

AND

<Title>

<Address of the contractor>

<Official registration number/VAT number>

(Contractor)

Article 1: Subject of the contract

The subject of the contract is the “Development of the Detailed Regulation Plan for the Srpski Itebej-Otelek cross border point” as indicated in the contractor’s offer – ‘’Part B: Format of offer to be provided by the tenderer’’

Article 2: Contract value

The total contract value for implementation of services indicated in the Article 1 is: XXX EUR and payments are made in national currencies, applicable exchange rate will be InforEuro exchange rate for the month of the issuing of invoice or pre-invoice in case of VAT exemption.

For Serbian partners:

The contract shall be exempt from all duties and taxes, including VAT.

Article 3: Contracting documents

The documents which form the part of this contract are (by the order of precedence):

- Contract agreement

- Contractor’s offer as provided in the tendering phase – ‘’Part B: Format of offer to be provided by the tenderer’’

- Contractor’s financial offer –“ Part C:Format of financial offer”

- Any other supporting documentation if applicable (* - in case of asking for registration of company or other information)

For any issues not defined in this contract agreement the rules of General conditions will be applied (Annex B8d  of PRAG b8d_annexigc_en.pdf)

http://ec.europa.eu/europeaid/prag/previousVersions/annex.do?num=2015.0&lang=en

Article 4: Deliveries and payments

The contractor will deliver without reservation the services indicated in the contractor’s offer ‘’Part B: Format of offer to be provided by the tenderer’’. The deliveries will be implemented within the indicated dates.

The contracting authority will pay to the contractor for the services in the amount indicated in the Article 2 of this contract document.

In case the contract is concluded in EUR, and payments are made in RSD, applicable exchange rate must be InforEuro exchange rate for the month of the issuing of invoice or pre-invoice in case of VAT exemption.

The payments will be issued by the following time schedule.

| Month |  | EUR |
| --- | --- | --- |
| 6th Month | Balance final payment - The approval of the final report will be the basis for issuing balance payment | 100 % of the contract value |
|  | Total | Total contract value |

* - The contractor will provide contracting authority with the brief report on execution of the services, which will represent the basis for issuing interim and balance final payment

Article 5: Duration of the contract

The duration of the contract is 6 months.

Commencement date is <dd/mm/yyyy>

Article 6: Cancellation of the contract

The contract can be suspended by the Contractor due to one of the following reasons:

- Contracting Authority not fulfilling payment and other obligations.

The contract can be terminated by the Contracting Authority due to one of the following reasons:

- The Contractor is in serious breach of the contract, failing to meet contractual obligations;

The Contractor is bankrupted or being wound up, is having its affairs administrated by courts, has entered into arrangements with creditors, has suspended business activities, is the subject of proceedings concerning those matters, or is in any analogous situations arising from a similar situation provided for in national legislation or regulations.

Article 7: Resolving of disputes

Any disputes arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of relevant court in accordance with the national legislation of the state of the Contracting Authority.

| For the Contractor |  | For the Contracting Authority |  |
| --- | --- | --- | --- |
| Name: |  | Name: | Aleksandar Sofić |
| Title: |  | Title: | Provincial Secretary |
| Signature: |  | Signature: |  |
| Date: |  | Date: |  |

Where applicable. For individuals, mention their ID card or passport or equivalent document - number