ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

Opština Senta

## Country background

The project is implemented within the Interreg-IPA Cross-border Cooperation Romania-Serbia Programme. It lays the foundations for using EU funds under the cross-border component of the IPA Regulation, to support cross-border cooperation on the Romanian-Serbian border.

This contract runs between the main locations as Senta and Otelec, but the main result of the project: the created joint touristic cycling route will incorporate destinations such as Senta, Kikinda, Zrenjanin, Otelec and Timisoara. Natural, historical and cultural heritages and attractions will be on focus throughout the route.

International context in which this project takes place is dominated by relations between Serbia and the EU. Romania supports Serbia's actions to become an EU member. At the regional level the project is in competition with other projects developed by Romania-Serbia IPA.

These communities aim to successfully develop upon each side. Given the international and domestic situation of the two countries, CBC Programme offers a chance to solve the some of the problems they face. With an implementation time frame of 18 months, the probability of successful implementation of the activities proposed in the project is very high. This project will contribute to the development of relations between these communities and will increase and utilise the touristic potentials of the region.

## Current situation in the sector

The Banat region is a single region either in natural-geographic, cultural and historical respect, but it is divided by the borderline. Project focuses on common territorial challenges and intends to tackle such as connectedness of two country region, facilitating better communication and cooperation between population and communities on both sides of the border.

Romania and Serbia border region now is not an outstanding, favorite tourist destination because the region has no individually designed image, in addition to this, tourism supported marketing activities are missing as well. Considering the rural nature of the region, it abounds in variety of natural and cultural sites, built heritages, landscapes, religious monuments, traditional buildings and settlements, historical and archaeological sites etc. The assistive tourist services largely fall short of its potential and they also are built by haphazard onto the tourist attractions. Between tourism stakeholders, the partnership and the cooperation initiatives are deficient. Due to this disorganization, joint touristic packages are missing and the inherent turnover growth.

The shortcoming may be linked to the above is that the tourist services do not follow the achievements of IT, that is to say they are not in accordance with the expectations and requirements of tourists and travelers.

Project is an innovative solution for raising touristic demand of natural and cultural attractions in the border region. It combines in a unique way two approaches. At first, through cycling route, it included in the cycling network Eurovelo, Timișoara - Zrenjanin, which will attract population who are committed to travel freely at open air. It is environmental feature of the project, including promotion of healthy living. Second, it will be created a thematic route which merge all natural, historical and cultural heritages on the path, and that way offer a joint package to tourists and visitors of the region.

The main objective of the project is to enhance demand for cross-border tourist region by development of thematic cycling route package and through joint branding and marketing activities. Thematic routes, integrated tourism stakeholders and marketing contributes to increase of attractiveness of the region for domestic and foreign tourists.

To achieve the defined objectives and results, we have to treat a cross border territory as a coherent area. Many landmarks, sites and other attractions are linked to each other. The integrated approach is needed to develop a joint tourism image and to create a successful network between key actors in the region.

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

Enhance demand for cross-border tourist region by development of thematic cycling route package and through joint branding and marketing activities. Thematic routes, integrated tourism stakeholders and marketing contributes to increase of attractiveness of the region for domestic and foreign tourists.

Created touristic cycling route package (eco, ethno, cultural, gastro and leisure) has to foster the recognition and sustainable utilization of tourist attractions in the region. This touristic cycling route presents a common touristic product which integrate the major touristic potentials in the CB area.

## Purpose

The purposes of this contract are as follows:

- Elaborate a touristic thematic cycling route in 5 topics

- Develop a marketing strategy and action plan in order to promote tourism attractions in the RO-RS border region

- Create a common brand for the joint cycling route and special images for each thematic routes.

## Results to be achieved by the Contractor

- Elaborated study about the route (cycling path and attractions) in 5 topics (eco, ethno, cultural, gastro and leisure).

- Developed marketing strategy and action plan for tourism promotion

- Created a common brand and special image for each thematic cycling routes

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The Consultant has to assume the tasks under the project according to the present Terms of Reference and according to the best practices in the field.

## Risks

Risk 1: Lack of relevant information, data, documents to create a study.

Risk 2: Time frame and dynamic of realization of specific activity.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Consultant should cover the lack of capacity and experience in the field of organization and implementing the following activities, provide administrative, technical, logistical and HR support for organization, as well as bares the related costs for:

- Touristic thematic cycling routes

- Marketing strategy and action plan

- Common brand and special images for thematic cycling routes

For details, see point 4.2. Specific work (below).

### Geographical area to be covered

Mainly activities and tasks should be organized and implemented in cross-border region (Timis county and North Banat district).

### Target groups

Senta and Otelec municipality will participate in project as direct beneficiaries. (2)

Cyclists of sport clubs and members of other organizations will use, and be the users of physical and virtual results of project. (100)

Tourism operators and ancillary service providers from two countries will be involved in training (basic language, professional, marketing and QMS). (40)

Domestic and foreign tourists and visitors of the sites and CB region. (10000)

## Specific work

The Contractor shall provide / organize the following types of activities:

A) Elaboration of touristic thematic cycling routes

Thematic cycling routes have to be elaborated in 5 topics (eco, ethno, cultural, gastro and leisure), in more difficulties and distances. The elaborated joint study about the route (cycling path and attractions) should cover North Banat district. The route(s) should include mayor points on the axis: Zrenjanin, Kikinda and Senta, and its surroundings.

Identification of relevant tourism operators and ancillary service providers will also be a crucial part of this database.

It will incorporate identification, mapping and database making about the existing natural, historical and cultural heritages and attractions, as well as various tourism operators and ancillary service providers (accommodation, meals, technical assistance) on the 5 marked bicycle routes. It will include at least 5 settlements, at least 50 sights (points) and 100 service providers from the both side.

These will be the major components of the touristic cycling route and be linked to the Eurovelo 13.

For each involved settlement, sights (points) and service providers the Consultant should prepare at least 5 photo documents, and data about the location and address of the identified points. Furthermore, the Consultant have to write a short text, description about these points.

The 5 thematic cycling routes: eco, ethno, cultural, gastro and leisure, and the points have to be presented on map. Maps have to be in high resolution including the compulsory visibility elements defined by Interreg-IPA CBC Romania-Serbia Programme.

The elaborated database and the document have to be written in Serbian language in the average volume of 40-50 pages A4 format.

The prepared outputs must be delivered in electronic format too.

Time frame for completion of this task is 6 months, by the end of December 2021 at the latest.

B) Development of marketing strategy for the promotion of tourism attractions

Strategy and action plan for the promotion of tourism attractions in Timis county and North Banat district.

Development of marketing strategy for the promotion of tourism attractions. Marketing strategy will go in two strands:

1 According to the listed trademarks and tourism operators in the CB area, promotion the tourism with the most effective methods and instruments (tools),

2 Strong marketing activities to inform the public and foreign potential tourist about the new developed tourism package generator application. In that strategy, action plans and applicable solutions will be proposed too.

Identification of relevant tourism operators and ancillary service providers will also be a crucial part of this database. The elaboration of joint marketing strategy for all tourism stakeholders in the region contribute to choose and use of different instruments to link to other providers and to entering to market uniformly, complement each other.

The elaborated Strategy and action plan have to be written in Serbian language in the average volume of 20-30 pages A4 format.

The prepared outputs must be delivered in electronic format too.

Time frame for completion of this task is 3 months, by the end of September 2021 at the latest.

C) Creation of common brand and special image for each thematic cycling routes

On bases of developed of marketing strategy realization of marketing activities. Common brand and special images for each thematic cycling routes.

Creation of common brand and special images (icons) for each thematic cycling routes. Design and elaboration of common brand for Banat touristic cycling routes and 5 special images for each thematic routes (eco, ethno, cultural, gastro and leisure).

In addition to the designed and created common brand and special images the Consultant should to prepare a visual identity manual in Serbian language in the volume between 15 and 20 pages A4 format.

The prepared outputs must be delivered in electronic format too.

Brand and the icons have to be in jpg and tif format, high resolution and be delivered in electronic format.

Time frame for completion of this task is 3 months, by the end of September 2021 at the latest.

## Project management

### Responsible body

The Consultant is responsible for all the activities regarding this contract. From the other side, Senta Municipality as a Contracting Authority will be responsible for the management.

### Management structure

The responsible person for the overall implementation of the tasks related to this contract, in the Contracting Authority is Andraš Košicki, the project manager.

### Facilities to be provided by the Contracting Authority and/or other parties

Not appropriate.

# LOGISTICS AND TIMING

## Location

Senta, North Banat district, Serbia.

## Start date & Period of implementation of tasks

The intended start date is 22.06.2021 and the period of implementation of the contract will be 6 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

The contractor will ensure sufficient number of qualified experts for quality and timely implementation of tasks planned by these Terms of References. These experts are considered as non-key experts therefore their CVs are not examined prior to the signature of the contract and should not be included in the tender.

The Consultant shall select and hire other experts as required according to the needs.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Not appropriate.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

- The Contractor will submit the following reports in English in one original:

- The contractor will prepare 1 brief interim reports after the closure of each specific activities (according to 29.1 Article of the Special Conditions of the Contract), and the final report on the implementation of the tasks, at the end of this contract. The approval of interim reports and the final report by the Contracting Authority will be the basis for issuing respective interim and final payments as indicated in the Special Conditions.

- The required formats of the reports will be communicated to the Contractor by the Contracting Authority after the signature of the contract.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference” and defined within activities determined in point 4.2. Specific work.

## Special requirements

Not applicable.