ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

Municipality of Novi Knezevac, Kralja Petra I Karadjordjevica 1, 23330 Novi Knezevac, Serbia

## Country background

The project is implemented within the cross-border Programme between Romania - Serbia for the period 2014 - 2020. It lays the foundations for using EU funds under the cross - border component of the IPA Regulation, to support cross - border cooperation on the Romanian - Serbian border.

## Current situation in the sector

Tourism is an important tool to develop culture and generate income that contributes to the preservation and conservation of cultural heritage. Strengthening the relationship between tourism and

culture can turn potential touristic destinations in attractive and competitive locations to be visiting, living, to work and to invest. Moreover, cultural tourism is particularly financially viable, knowing that, on average, tourists spend considerably more on a cultural trip than other categories of tourists. Because the region is not very rich in natural attractions, the development the use of cultural attractions is even more important. Capacity building initiatives for the improvement of quality and innovation of tourism services and products using cultural traditions from Valcani-Novi Knezevac region for the promotion of tourism in historical Banat is the background for this project. The project tries to realize the development of the tourism in the Valcani-Novi Knezevac border region by inventorying and establishing the present situation, developing a new cultural tourism route integrating the existing attractions and to develop a flagship cultural event in both localities which can give a boost to the local cultural tourism. All the project activities will be part of a powerful marketing campaign. Also the partners will establish the infrastructural base of the cultural events. Valcani Commune will develop a new outdoor stage with all the necessary facilities; Novi Knezevac will purchase a mobile stage.

## Related programmes and other donor activities

This project is in agreement with European and national trends. It will create a collaborative environment where participants included in the project will show the ability to achieve national and international competitiveness of the cross - border region.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The main Project objective is an increase of the tourism offer in Project partners communities in the aspect of cultural tourism for all ages with the respect to all ethnic groups living in the CB region and  promotion of cultural heritage of CB region and historical Banat traditions through flagship cultural events.

## Purpose

The purpose of this contract is as follows:

- Organization of 4 events necessary for Project implementation

## Results to be achieved by the Contractor

- 3 Conferences organized

- 1 Flagship Event organized

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

n/a

## Risks

COVID-19 measures affecting the implementation. The need for additional logistics if the events cannot be public and will be forced to be realized online.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Contractor will be responsible for the following tasks:

1. Organization of 3 (three) Conferences in Novi Knezevac, Republic of Serbia, as listed above to promote project, objectives, activities and results, in venue chosen by Contracting Authority, presentation equipment, material, translation from Serbian to Romanian and Romanian to Serbian, catering and refreshment for 50+10+10 participants and documenting events with high quality photographs and list of participants.

2. Organization of Flagship cultural event/festival  in the municipality of Novi Knezevac, Republic of Serbia, at location chosen by Contracting Authority (Old park in Novi Knezevac or nearby location) minimum 3 (three) days prior to flagship event (Contracting Authority will provide stage with lighting and sound system), material, 6 high quality artistic programmes in the thematic of the event, providing children’s animators/surveillance and programme,  accommodation and transportation for 25 participants from Romania (from Valcani to Novi Knezevac and back) including transfers from accommodation unit to event place and back, translation from Serbian to Romanian and Romanian to Serbian, catering/refreshment for 500 participants, providing the security services for the whole event.

The Program is designed to enable all people to enjoy mutual cultural heritage and access to cultural events with respect for their cultural traditions.

All the Project activities are designed to ensure equality between men and women. The sex equality in project stuff is ensured. All the Project activities are designed to be achievable both by men and women on equal basis.

### Geographical area to be covered

The Republic of Serbia, AP Vojvodina, North Banat district, Municipality of Novi Knezevac

### Target groups

This project targets local communities from both sides of border (public authorities, interest groups including NGOs and general public). They will be affected by our project actions and as well encouraged throughout specially tailored events (flagship cultural events) to increase inclusion into the community. Also, this group is targeted because there is a lack of specific tourism offer in the CB region for them where all this groups are connected at the same time. People living in rural areas of the CB region will be targeted to achieve decentralization of tourism events in whole region and positively influence sustainable tourism development in less developed rural areas. All of them will be actively involved in the implementation of certain project activities; therefore they are also a secondary target group. The whole community living in the CB region will be also involved into realization of project activities providing the support for the people incorporation into the society ensuring social sustainability.

## Specific work

I CONFERENCES

Organization of 3 (three) conferences including

Conference for local public authorities, NGO’s and general public The target group will be involved on more level. The representatives of the public local authorities and the NGO`s from the region will be invited to a conference, where they can propose changes in the tourism route, propose future activities, which can boost the result of the project and better promote the tourism offer of the region. Also all the target group will be involved in the organization of the cultural event.

Press Conference 1 (press conference) for promoting flagship cultural event in Novi Knezevac before the festival and announcing date of the event.

Press Conference 2 (project closing conference) for summing project results, promoting project and achievements done in mutual partnership.

The place of the conferences will be in Novi Knezevac and precise location will be determined by Contracting Authority minimum 3 (three) days before each.

Target groups and press will be contacted by the Contracting Authority, the registration of the participants on the events has to be realized by the Contractor.

It is the Contractor obligation to provide the presentation equipment (laptop, projector, projector screen), sound equipment for all events during the course of the conferences and also paper package for the participants: notebooks, pens, flipcharts.

TRANSLATION in Serbian (from Romanian) and Romanian (from Serbian) has to be organized by the Contractor: working hours per event min. 1,5 hours max. 2 hours. The translator can do either simultaneous or consecutive translation. The topics of the curriculum is cultural traditions of Banat region, festivals, cultural heritage of CB region.

CATERING for cca. 70 in total (50+10+10) participants The Catering should replicate usual smorgasbord (hot and cold dishes of various foods representing heritage of the CB region served with ceramic plates, metallic forks, spoons, knives, glass containers), mineral water (still and sparkling water), soft drinks, coffee and tea (with condiments).

It is the Contractors obligation to lead the registration of the participants, archive the events via a professional photographer or in case of strict COVID regulations to organize online event/ live stream is an option).

NOTE: All related travel and VAT expenses related to the realization of the contract are the costs of the Contractor and part of the final value of the contract.

COVID-19 MEASURES

It is the obligation of the Contractor to provide enough a number of hand sterilizing lotion and to put them approachable on several places at the conferences. The Contractor will also have to organize every aspect of the work by respecting the current COVID-19 regulations determined by the relevant authorities of the Republic of Serbia at the time of the realization of events.

II PROVIDING TECHNICAL SUPPORT FOR ORGANIZATION OF THE FLAGSHIP

CULTURAL EVENT/FESTIVAL

Planned place of the realization of the event: Old park in Novi Knezevac or nearby location. It will be determined by Contracting Authority minimum 3 (three) days prior to flagship event.

PROGRAMME:

The Contractor should perform organization of cultural entertainment programme including at least  at least 6 artistic programmes in the thematic of the event replicating local cultural heritage from places marked on touristic route including minimum: Novi Knezevac, Coka, Kikinda and Valcani. The programmes will be chosen after consultation with the Contracting Authority. The artistic programme needs to be high quality. The Contractor needs to pay all costs linked to the artistic programme (transportation, fees of artists, meals, accommodation if needed, copyright fees, etc.). The stage and the technical equipment will be offered by the Contracting Authority.

PROGRAMME FOR CHILDREN:

The Contractor should organize minimum of 2 hours children’s animation activities on the event (staff and material).

ACCOMODARTION, TRAVEL AND MEALS:

The Contractor should provide accommodation for participants from Romania, 25 persons. The accommodation should be offered in 3* hotel or similar pension in single/double rooms for one night, breakfast included. The accommodation place will be at most at 20 km distance from Novi Knezevac, the Contractor will offer transportation to the place of accommodation and back.

Also the Contractor should provide 3 meals to the participants from Romania, 25 persons. The meal will include at least the following products: soup, 2 main courses (1 with meat, 1 without meat, with side dish), salad, dessert, sparking and still mineral water, soft drinks, coffee and tea with milk and sugar, bread and fruits. The meal can be organised in a restaurant (not more than 500 m away from the venue) in accommodation unit or as catering. If the Contractor chooses to organize a catering, it has to provide the cutlery and porcelain plates, also the Contractor will provide the necessary table decorations and the arrangement of the venue. The final menu will be discussed between the parties in 3 days before the event. In case there are some special dietary needs, the Contracting Authority will inform the Contractor 3 days before the event.

Provide transportation for 25 persons from and to Valcani to respect timeframe of the event.

TRANSLATION in Serbian (from Romanian) and Romanian (from Serbian) has to be organized by the Contractor: working hours on the event from 12:00-23:00h. The translator can do either simultaneous or consecutive translation. The topics of the curriculum is cultural traditions of Banat region, festivals, cultural heritage of CB region.

CATERING-Provision of catering for the cultural flagship event/festival:

Catering and refreshment for 500 participants (portions) should be obligation of the Contractor which will have to delegate staff for the serving of the catering to participants in any of the chosen premises for lunch, dinner and breakfast.

The exact time and method of the delivery of the catering will later be determined but the planned timeframe is that the catering should be set from 12:00 – 14:00h (lunch), 17:00-19:30h (dinner) on the day of the event and 08:00-09:00h (breakfast) day after the event (for participants from Romania). Serving of the portions should be realized respecting social distancing. The refreshments should be available to participants when needed (water and soft drinks during performance).

Document the event. The contractor will provide at least 50 high quality photos and short videos which will be used to document the event and for promotional purposes.

SPECIAL ENGAGEMENT OF EXPERTS

The Contractor will be in charge to supervise the later payment of all artists, animators, security, and technical crew. The Contractor has to follow the Laws of payment of fees of the Republic of Serbia. The Contractors team leader will be in charge of all financial issues related to this contract and he/she has to supervise all paperwork related to these activities.

PROVIDING A PROFESSIONAL IN CHARGE OF THE MAINTENANCE OF PUBLIC SAFETY AND SECURITY OF EXPOSED GOODS AND NECESSARY INFRASTRUCTURE

The security services will have to cover territory of the event in Novi Knezevac determined by Contracting Authority 3 (three) days before stage setup and has to include minimum 1 person after stage setup for overnight watch prior to the event and to beginning of the event next day, minimum 3 people from 12h to 22:30h on event day and minimum 1 person delegated for night watch after the event until the stage is dissembled and safely transferred to Contracting Authority facilities on the next day. The security service in conduct and licences has to follow the law and regulations set by the Republic of Serbia.

PLANNED TIMEFRAME OF THE EVENT

Day 1.

11.00-12.00h Registration of participants – lead by the Contractor

12.00-14.00h Children’s programme, lunch and transfer to accommodation unit and back to the event

place for participants staying at Novi Knezevac over night

14.00-17.00h Cultural tradition programme (artist groups from touristic route - folk dance and music)

17.00-20.00h Sightseeing, dinner and refreshment of participants at event spot, nearby restaurant or

accommodation unit

20.00-22:30h Concert (supporting act and famous singer at national level)

Important note: tenderers need to name singer or list of possible singers from which will Contracting Authority choose from in their offer. This will be scored by evaluators in technical evaluation phase.

22.30h           Closing of the event and transfer of participants to accommodation unit

Day 2.

8.00-9.00h     Early breakfast or lunch package and transfer of participants to Romania

COVID-19 MEASURES

It is the obligation of the Consultant to provide enough a number of hand sterilizing lotion and to put them approachable on several places at the Flagship cultural event. The Consultant will also have to organize every aspect of the work by respecting the current COVID-19 regulations determined by the relevant authorities of the Republic of Serbia at the time of the realization of events.

NOTE: All related travel and VAT expenses related to the realization of the contract are the costs of the Contractor and part of the final value of the contract.

In case of stricter COVID-19 measures the event is planned to be realized at the earliest the possible when public gatherings will be allowed.

TIMEFRAME OF THE IMPLEMENTATION

| ACTIVITY | MONTH OF REALIZATION* |
| --- | --- |
| Conference for cca. 50 persons | April 2022 |
| Press conference 1 for 10 persons | July 2022 |
| Press conference 2 for 10 persons | February 2023 |
| Flagship cultural event/festival for cca. 500 participants | July – August 2022 |

*depending on the COVID-measures and force majeure

## Project management

### Responsible body

The Contractor is responsible for all activities regarding the contract.

### Management structure

The responsible person for implementation of the tasks related to this contract in the Contracting Authority is Project Manager.

### Facilities to be provided by the Contracting Authority and/or other parties

n/a

# LOGISTICS AND TIMING

## Location

Novi Kneževac, North Banat District, AP Vojvodina, Republic of Serbia

## Start date & Period of implementation of tasks

The intended start date is the date of signing of the contract by both parties (planned date: March 15th 2022.) and the period of implementation of the contract will be 11 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English and in Serbian Language in one original:

• Interim Report after Conference for 50 persons is finished in 2nd month of implementation, after Press Conference 1 is finished and after Flagship cultural event/festival is finished in 6th month of implementation. The reports shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. Report must be provided along with the corresponding invoice.

- • Final report after Press Conference 2 and effectively entire service is finished. The report shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality

and quantity manor as required in these Terms of reference.

## Special requirements

Not applicable.