ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

Citizen’s Association Leader + Banatski Karlovac, Nemanjina 58/1, Serbia

## Country background

The project is implemented within the cross-border Programme between Romania - Serbia for the period 2014 - 2020. It lays the foundations for using EU funds under the cross - border component of the IPA Regulation, to support cross - border cooperation on the Romanian - Serbian border.

## Current situation in the sector

The Romanian Local Action Groups have more advanced practical knowledge from the past 8 years, and their experience, knowledge and advices will be precious for Serbian LAGs. On the other hand, Serbian potential LAGs have innovative solutions for some of the local problems, which are common to both Romanian and Serbian local communities in eligible territory, and can be transferred as best practice in Romania.

The case is that Romania had very similar situation to Serbian situation, during establishing and developing phase of LEADER-methodology-based Local Action Groups: at the beginning, Romania started establishing LAGs on the whole Romania territory, and local actors were delighted and very motivated to start implementing LEADER methodology and function as a LAG. LAGs were established, and Romanian Ministry was supposed to launch the LEADER Program and start with financial support, as in member states. This process took longer than expected, from various reasons, and LAGs in Romania were forced to turn to alternate financing sources in order for LAG to survive until official Program starts. This period of “survival and resilience”, maintaining enthusiasm, activism and local actions, is “gold mine of experience” for Serbian LAGs at this moment, because the situation is very similar in Serbia in this period.

## Related programmes and other donor activities

This project is in agreement with European and national trends. It will create a collaborative environment where participants included in the project will show the ability to achieve national and international competitiveness of the cross - border region.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The overall objective is to prepare Serbian LAGs for maximizing impact, performance and innovation for IPA Rural Development Programme, through sharing Romanian LAGs’ practical experience and knowledge on EU LEADER Approach to rural development with fellow Serbian LAG initiatives.

## Purpose

The purpose of this contract is development and design of Mapping the potential support structures, Needs assessment for LAGs and development of Non-Financial Support (NFS) plan and Development of Pitches for applying for VP and CSR funding

## Results to be achieved by the Contractor

- Needs assessment for LAGs developed

- Non-Financial Support (NFS) plan developed

- Development of Pitches for applying for VP and CSR funding

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

n/a

## Risks

Potential pandemics measures affecting the implementation. The need for additional logistics if the cannot be public and will be forced to be realized online.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Contractor will be responsible for the organization of following tasks:

Mapping the potential support structures, Needs assessment for LAGs and development of Non-Financial Support (NFS) plan and Development of Pitches for applying for VP and CSR funding

### Geographical area to be covered

The Republic of Serbia, AP Vojvodina, South Banat district, Municipality of Banatski Karlovac

### Target groups

This project targets Potential Local Action Groups - pLAGs-Serbia from target regions Banat,Podunavski, Braničevski, Borski, Local authorities: self-governments involved in LAGs, Ministry of Agriculture, Forestry and Water Management of Serbia, Networks of LAGs, professional rural associations, such as beekeepers associations, social care services associations, cultural heritage, Entrepreneurs from rural areas and general public as a target groups.

## Specific work

The subject of procurement is following:

1.	Mapping the potential support structures - Benchmarking of the EU trends in LEADER/CLLD

2.	Mapping the potential support structures for the Serbian LAGs in the target area

3.	Assessment of the needs of each specific LAG Initiative

4.	Developing the Non-Financial Support (NFS) plan (12 old LAGs+6 new LAGs)

5.	Development of 12 Pitches

1.	Mapping the potential support structures - Benchmarking of the EU trends in LEADER/CLLD

Study has to present the research on the latest trends in the EU regarding LEADER Approach and Community Led Local Development (CLLD), in order to be sure that all the parties involved have the same understanding of the scope, role and contribution of the cross-border cooperation on rural development in reaching goals of the EU 2021-2027 Programming period. Study has to present a potential external support structures on the EU level for effective development of LAG initiatives in Serbia.

The result: Study: Potential support structures for effective development of LAG initiatives in Serbia based on Romanian and EU experiences on LEADER/CLLD

2.	Mapping the potential support structures for the Serbian LAGs in the target area

Update/In-depth research, analysis and mapping of current status and next steps of the LAGs, networks and support structures available for the Serbian LAGs: the subcontractor will research the latest trends and the next steps in eligible CBC area.

The subcontractor will research the latest trends and the next steps in the six Serbian regions (North, Middle and South Banat, Braničevski, Borski and Podunavski) regarding LEADER Approach and Community Led Local Development (CLLD), at the moment of project deployment. Same as for Romania, situation is fluctuating and developing constantly, so it is crucial for research to include very latest trends at the deployment, not year before or earlier, because that will not be fully relevant. Study will gather all the available knowledge and experience from the target region, for sharing it with fellow Serbian LAGs. This action will specifically focus on successful LAG management and project examples, networks and structures in Serbia, including possibilities for later Cross-Border Cooperation in LEADER/CLLD.

The sectors that need to be covered:

•	Public sector institutions that provide support to LAGs

•	Business sector institutions that provide support to LAGs

•	NGO sector institutions that provide support to LAGs

•	Educational institutions that provide support to LAGs

•	Media institutions that provide support to LAGs

•	Best examples of CBC of LAGs in EU

The topics that need to be covered:

•	What types of support are available?

•	Mapping the assets of support structures: who provides what type of support?

•	Matching the assets with core and non-core support.

•	How to monetise both financial and non-financial support?

•	How to finance the support?

•	Recommendations for managing support.

The result: Study - LEADER/CLLD and the EU LAGs Cross-Border Cooperation: Next practices for the LAGs of Serbia and Romania

3.	Assessment of the needs of each specific LAG Initiative

Needs Assessment of the LAGs in Serbia for the 2023-2025 period for IPARD III

In-depth personalised assessment of the needs of each specific LAG Initiative on the Serbian side (12 existing and 6 new) to invest in for 2023-2025, along the three core areas of development (socio-economic impact, financial sustainability and organisational resilience)

The topics that need to be covered:

•	Understanding the needs of the LAGs: performing a needs’ assessment

•	Recommendations for managing non-financial support

•	The needs’ assessment tool

The result: 18 Personalized detailed Needs assessments (for the 12 existing and 6 new LAGs)

4.	Developing the Non-Financial Support (NFS) plan (12 old LAGs+6 new LAGs)

Using the respective personalized Needs Assessments from the activity 3.2.1, for each of the 12+6 Serbian LAGs, along each of the three core areas of development

(socio-economic impact, financial sustainability and organizational resilience), the plan should include the baseline, goal, milestones, and target outcomes for the

LAG/members, with the detailed specification of Non-Financial Support expected from the Project. In close cooperation with each LAG, selected organization/consultants will develop Plans, along with one-on-one consultative meetings.

The topics that need to be covered:

•	The non-financial support plan

•	Recommendations for managing non-financial support

•	The non-financial support plan tools

•	Donors Delivery Models

•	Delivery Models PROs and CONs tools

•	Strategic factors influencing delivery

•	Monitoring the delivery of non-financial support

•	Recommendations for managing non-financial

The result: 18 Non-financial Support (NFS) Plans for the LAGs/Initiatives on the Serbian side

5.	Development of 12 Pitches

There is a growing interest of Venture Philanthropy (VP) and Social Impact Investing (SII) for spreading to Central and Eastern Europe. This Activity aims to respond to this opportunity by supporting 12 most promising non-profit project proposals in the area of Social Innovation / Entrepreneurship - 9 Serbian and 3 Romanian - by "translating" the ideas and/or EU-format proposals to the presentation format requested by the VP/SII organizations: the "Pitches". These effective, clear and concise, 3-6 minutes presentations in most appropriate free-form, selected by the presenter as most appropriate for the given theme, aims at catching attention of the experienced philanthropists originated (mostly) from the venture capital, banking and corporate philanthropy sectors

The result: 12 Pitches developed for applying for Venture Philanthropy and Corporate Social Responsibility funding

## Project management

### Responsible body

The Contractor is responsible for all activities regarding the contract.

### Management structure

The responsible person for implementation of the tasks related to this contract in the Contracting Authority is Project Manager.

### Facilities to be provided by the Contracting Authority and/or other parties

n/a

# LOGISTICS AND TIMING

## Location

Banatski Karlovac, South Banat District, AP Vojvodina, Republic of Serbia

## Start date & Period of implementation of tasks

The intended start date is the date of signing of the contract by both parties (planned date: July 05th 2023.) and the period of implementation of the contract will be 4 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English and in Serbian Language in one original:

• Interim Report in the 2nd  month of contract implementation. Report must be provided along with the corresponding invoice.

- • Final report after completing all planned tasks from this contract. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is Services provided in timely, quality

and quantity manor as required in these Terms of reference.

## Special requirements

Not applicable.