ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania

## Contracting Authority

Euroland Banat Association

## Country background

The project contributes to addressing key issues of rural development which are characteristic of the region on both sides of the border, and which would benefit from joint cross-border actions, in relation to key areas such as cultural and social integration in marginalized rural areas, agriculture, inclusive growth, rural tourism development.

## Current situation in the sector

The LEADER methodology is designed to support local businesses, farmers, foresters, community groups, those involved in tourism and a range of rural enterprises. The members of the LAG are self-governments, civil organizations and private businesses from local territories.

Pre-accession period for Serbian LAGs was start in 2019, when first IPARD Program Leader become operative. The development of LAGs in Serbia could be helped and boosted by the neighbouring Romanian local communities.

## Related programmes and other donor activities

The project is financed from Interreg IPA CBC Romania-Serbia Programme

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To prepare Serbian LAGs for maximizing impact, performance and innovation for IPA Rural Development Programme, through sharing Romanian LAGs practical experience and knowledge on EU LEADER approach.

## Purpose

The purpose of this contract is as follows:

Research of LAGs situation and CLLD implementation impact in Romania and Serbia, to provide good practice examples and sustainable solution to Serbian LAGs. The aim is to encourage the LAG development in Serbia.

## Results to be achieved by the Contractor

The Contractor will provide 2 studies, 1 study per lot, in English language, between 30-50 pages each plus annexes.

LOT 1 – LAGs of Timis, Caras-Severin and Mehedinti County

LOT 2 – LEADER/CLLD and the EU LAGs cross-border cooperation

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

In both country the LEADER Programme will be functional in the next programming period.

## Risks

- changes in legislation

- force majeure

- lack of implication from local authorities

# SCOPE OF THE WORK

## General

### Description of the assignment

Research of LAGs situation and CLLD implementation impact in Romania and Serbia, to provide good practice examples and sustainable solution to Serbian LAGs. The aim is to encourage the LAG development in Serbia.

### Geographical area to be covered

Romania – Caras-Severin, Mehedinti and Timis Counties

Serbia (for general/comparative data)

### Target groups

LAGs from Romania (from IPA program target area)

LAGs and/or LAGs initiatives (potential LAGs) from Serbia (from IPA program target area)

LAGs management and members (from IPA program target area)

Communities where LAGs/LAGs initiatives exist (from the Serbian side of the IPA program target area). Potential Local Action Groups - pLAGs- Serbia from target regions: Banat, Podunavski, Braničevski, Borski.

Local Action Groups in Romania from target region Caras-Severin, Mehedinti, Timis.

Target group consists of some of the existing LAGs from this target regions, which are consisted of representatives from local self-governments, private local businesses and civil society.

Local authorities (self-governments involved in LAGs), interest groups including NGOs (Networks of LAGs, professional rural associations, such as beekeepers’ associations, social care services associations, cultural heritage, etc.), SMEs (rural entrepreneurs-existing and potential- from target area, including SMEs in agriculture, tourism and services providers), general public.

## Specific work

The service provider will present 2 studies, as follows:

The studies will map the potential support structures, networking and best practice exchange resources from Romania and EU, in order to be able to support the Serbian LAG initiatives in the target area for the coming EU Rural Development programmes.

LOT 1 - LAGs of Timis, Caras-Severin and Mehedinti County

The study will analyse and present best practice from target Romanian territories for the LAGs initiatives, to be replicated in Serbia. The analyse will include references to number of citizens involved in civic activities/cultural/social health care services/disadvantaged persons involved in the project’s activities. Also, the number of actions targeting smart (green growth)/gender equality/equal opportunities and social inclusion across borders. The research will focus on successful LAG management and project examples, networks and structures in Romania, including possibilities for later Cross-Border Cooperation in LEADER/CLLD.

Benchmarking Romania: research, analysis and mapping of current status and next steps of the LAGs, networks and support structures in the Romanian side of the target area. Also, research on the latest trends and the next steps in the three Romanian regions (Timis, Caras-Severin and Mehedinti), regarding LEADER Approach and Community Led Local Development (CLLD). It is important for research to include the latest trends (at the moment of project deployment).

The minimum structure of the study is:

- Best practices in implementing the for LEADER program in Romania 2014-2020

- Best practices in strategic planning for LAGs of Timis, Caras-Severin and Mehedinti Counties

- Best practices in management for LAGs of Timis, Caras-Severin and Mehedinti Counties

- Best practices in promoting cooperation for LAGs of Timis, Caras-Severin and Mehedinti Counties

- Best practices in promoting inclusion for LAGs of Timis, Caras-Severin and Mehedinti Counties

- Best practices in developing the agricultural sector for LAGs of Timis, Caras-Severin and Mehedinti Counties

LOT 2 – LEADER/CLLD and the EU LAGs cross-border cooperation

The study will reveal some of the best examples of CBC LAGs cooperation in EU. It will present the research on the latest trends in the EU regarding LEADER Approach and Community Led Local Development (CLLD).

Benchmarking EU: In-depth desk research, analysis and mapping of the EU trends in LEADER/CLLD, and relevant networks and support structures in the rest of the EU.

The study will reveal next practices for the LAG of Serbia and Romania (best examples of CBC LAGs cooperation in EU). The analyse will include references to number of citizens involved in civic activities/cultural/social health care services/disadvantaged persons involved in the project’s activities. Also, the number of actions targeting smart (green) growth opportunities, promoting gender equality/equal opportunities and social inclusion across borders.

The minimum structure of the study is:

- presentation of Leader and the evolution of CLLD

- actual status of LEADER policies in Europe and Romania

- National policies versus European policies on CLLD in Romania and Serbia

- Implementation of Leader and CLLD in the cross-border area Romania-Serbia

- 2014-2020 benefits for local communities using CLLD

- Each study will be presented in English, in an electronic version. The study must be between 30-50 pages plus annexes (e.g. bibliography, photos).

- The service provider will cease the copyrights to Contracting Authority.

The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. >

## Project management

### Responsible body

Euroland Banat Association

### Management structure

The project structure consists in a Joint Steering Committee. EBA has 2 representatives in JSC.

### Facilities to be provided by the Contracting Authority and/or other parties

Not the case.

# LOGISTICS AND TIMING

## Location

The Contractor could operate from any location.

## Start date & Period of implementation of tasks

The intended start date is 18.07.2023 and the period of implementation of the contract will be 2 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability. The key experts must meet the following requirements for each individual lot.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: LEADER/CLLD and LAG Expert

Qualifications and skills

Proven skills in local development, such as local development facilitator/LAG manager or expert/member in focus groups for developing Local Development Strategy, or similar.

General professional experience

- Minimum 5 years working experience

Specific professional experience

- Minimum 3 years experience as LAG manager/LAG expert/ LAG member/LAG consultant for developing and/or implementation of Local Development Strategy/expert for elaborating LEADER programme and/or strategies/ expert for elaborating CLLD programme and/or strategies

- English language, written and spoken

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

Other experts, support staff & backstopping

Not required.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor, if the case.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and 1copy.

- Interim report – max 3 pages, if an intermediate payment is foreseen

- Final report, maximum 5 pages. The deadline for sending the final report is 2 days after receiving comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on Contracting Authority. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred above must be submitted to the Project Manager identified in the contract. The Project Manager of contracting authority is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Not the case

## Special requirements

Not the case