ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Relevant country background	2

1.4.	Current state of affairs in the relevant sector	2

1.5.	Related programmes and other donor activities:	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Consultant	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project intervention	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific activities	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Commencement date & Period of implementation of tasks	4

6.	REQUIREMENTS	4

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Consultant	6

6.4.	Equipment	6

7.	REPORTS	6

7.1.	Reporting requirements	6

7.2.	Submission & approval of reports	7

8.	MONITORING AND EVALUATION	7

8.1.	Definition of indicators	7

8.2.	Special requirements	7

# BACKGROUND INFORMATION

## Beneficiary country	Romania

## Contracting Authority	Euroland Banat Association

## Relevant country background

Romania joined European Union in 2007. One of the many tasks and challenges of the European Union is to encourage equilibrate development of the Member States regions. The IPA Cross Border Cooperation Program Romania – Serbia is one of these programs implemented in order to provide a better social and economic development of the border areas. The Programme is the result of a co-operative effort by the Romanian and Serbian national, regional and local authorities. In Romania Public Tender Law is OUG 34/2006, for the above mentioned contract the procurement will be made under PRAG regulations.

## Current state of affairs in the relevant sector

The project area is the development the tourism sector, including the strengthening of the regional identity of the border region as a tourist destination

The national, regional and local strategies consider tourism as a major sector that can have an important positive influence in developing the entire target area and providing new resources to the local communities.

## Related programmes and other donor activities:

Not the case.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

Achievement of an optimal usage of natural resources and increase of their economic value by improving tourism and promotion of Deliblato sand and Caras-Severin.

## Purpose

The purpose of this contract is as follows:

            - to organise five meetings on rural tourism awareness campaign in rural areas from Caras-Severn county  and

            - to organize the participation of the Romanian delegation at a weekend destinations fair to be organized in Alibunar by the Serbian partners

according to the approved budget.

## Results to be achieved by the Consultant

- The results to be achieved by the consultant are as follows: to organize five meetings on rural tourism awareness campaign in rural areas from Caras-Severn county and to organize the participation of the Romanian delegation at the weekend destinations fair to be organized in Alibunar by the Serbian partners

# ASSUMPTIONS & RISKS

## Assumptions underlying the project intervention

- Common historical background of the region;

- Stability in legislation;

- Financial resources provided by IPA Programme (85% from programme and 13% from Romanian state budget;

- EBA’s long term collaboration with the Serbian partners and previous successful implemented CBC projects;

- Positive cash-flow;

- No major differences between needs as lay down in project proposal and the actual project demands.

## Risks

- Force majeure (war, strikes, natural phenomenon, others)

- Exchange rate and tax changes

- Legislation changes on both sides of the border

- Personnel availability (sickness, resignation, accidents)

- Weather (for outdoor activities)

# SCOPE OF THE WORK

## General

### Description of the assignment

Among several activities organized during the project’s implementation, Euroland Banat Association has envisaged to organise five meetings on rural tourism awareness campaign in different areas from Caras-Severn county and the participation of the Romanian delegation at the weekend destinations fair to be organized in Alibunar by the Serbian partners. The participants will be local actors like SME’s, NGO’s, local administration, owners of private houses, tourism promoters, local producers and artisans, service providers, teachers, tourists, students etc. and they will be invited to open discussions, to share opinions and experiences.

### Geographical area to be covered

### Caras-Severin County, Romania, South Banat, Serbia

### Target groups

- Weekend house owners

- Local entrepreneurs and farm owners

- Tourist organization

- Local administration representatives

- Promoters - visitors and tourists

- Members of the LAG, etc.

## Specific activities

- Implementing “Organization of events” from Project proposal, as was drawn.

- The activities that will be performed by the Consultant are:

            - to organise five meetings on rural tourism awareness campaign in rural areas from Caras-Severn county  and

            - to organize the participation of the Romanian delegation at a weekend destinations fair to be organized in Alibunar by the Serbian partners

Rural tourism awareness campaign will take place in five different potential rural tourism destinations in Caras-Severin county with a rich offer regarding local resources, cultural heritage, and beautiful landscapes. The aim of the campaign is to inform the local communities and to bring together the local stakeholders about different possibilities for sustainable rural development in their communities and also to stimulate local awareness and interest for small businesses as an alternative income source.

The contracting authority will select five rural communities and will inform the consultant of the best suitable five rural destinations. Members from the target communities and the surrounding area, local SME’s, NGO’s, local administration, owners of private houses, artisans and local producers, teachers, students, tourists etc. will be invited to share experiences. The discussions will include topics such as: environment and sustainable development, local resources, tourism opportunities, local architecture and trademarks, funding resources, association of the community for a joint common effort. The Euroland Banat project team will lead the debates during the awareness campaign meetings. In order to provide support and additional expertise to the project team, the consultant will contract 2 specialists/lecturers in connected fields (e.g. sustainable rural development, local traditions, architecture, natural heritage and environment etc.).

The consultant will provide for each meeting the following services:

- provide location for the meetings with all the necessary equipment (laptop, video projector, screen, audio-video system etc.) capable of hosting 40 persons or more.

- coffee break/meeting which contains: coffee (with milk), tea (different flavours), mineral water (0,5 l/person), non-alcoholic drink (0,5 l/person), natural juice (0,5 l/person), finger food (like sandwiches/appetizers), salad, pastry (at least 250 g/person), sweets and cookies (at least 250 g/person), desert.  The coffee break will be prepared for minimum 35 persons.

- Specialists/lecturers: all cost for specialists/lecturers – fee, transportation, accommodation (if necessary) on minimum 3 star hotel or pension and meals etc. At every meeting a number of minimum one specialists/lecturers will attend. The person of the specialists/lecturers will be decided after consultation with the Contracting authority.

- Estimated duration of a meeting: 4 hours

The exact date of the awareness campaign meetings will be decided by the Contracting Authority with a 5 working day notice.

In order to promote a clean environment, housing, high quality food and beverage, services and related offers, two-days lasting fair in Alibunar Municipality (most likely in Girl’s Fountain/Devojački Bunar) will be organized by the Serbian partners.

The contracting authority will select 35 to 45 participants from the Romanian side of Banat who will take part at the fair from Alibunar Municipality and will inform the consultant of the exact number by mid-september.

The consultant will be responsible for providing the transport for the Romanian participants from Resita to Alibunar Municipality (Girl’s Fountain/Devojacki Bunar) and the transfer from the accommodation facilities to the fair, if and when necessary. For the Romanian delegation at the fair, the consultant will provide also: two nights accommodation, half board, single rooms, in weekend/guest houses in Alibunar and minimum 3* hotels in the surrounding area. Due to limited accommodation facilities available in Alibunar Municipality (limited number of guest/weekend houses, limited number of rooms), the consultant can find accommodation in the surrounding area, such as hotels from Pancevo and/or Vrsac, respecting the above mentioned requirements.

## Project management

### Responsible body

The beneficiary Project management team will be responsible for managing the contract

### Management structure

The management structure of the Contracting Authority includes:

- Project manager

- Assistant manager

- Financial manager

### Facilities to be provided by the Contracting Authority and/or other parties

- Not the case.

# LOGISTICS AND TIMING

## Location

Caras-Severin County, Romania, South Banat, Serbia

The information of the five rural communities where the meetings for the awareness campaign will take place will be communicated to the consultant by the managing authority in due time.

The fair will take place in Alibunar Municipality, most likely in Girl’s Fountain area (Devojacki Bunar).

## Commencement date & Period of implementation of tasks

The intended commencement date is date of signature of the contract by both parties and the period of implementation of the contract will be 2,5 months from this date, but no later than 15.11.2016. Please refer to Articles 4 and 5 of the Special Conditions for the actual commencement date and period of implementation.

# REQUIREMENTS

## Personnel

### Key experts

No key experts (those who have a crucial role in implementing the contract) are requested for this contract.

### Other experts, support staff & backstopping

The contractor will ensure sufficient number of qualified experts for quality and timely implementation of tasks planned by these Terms of References. These experts are considered as non-key experts therefore their CVs are not examined prior to the signature of the contract and should not be included in the tender.

The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Consultant.

## Facilities to be provided by the Consultant

The Consultant shall ensure any other facilities, including the transportation means, necessary for quality and timely implementation of the tasks described in these Terms of Reference.

If the Consultant is a consortium, the arrangements should allow for the maximum flexibility in project implementation. Arrangements offering each consortium member a fixed percentage of the work to be undertaken under the contract should be avoided.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority as part of this service contract.

The contractor will provide all the equipment necessary for timely and quality implementation of the tasks described in these Terms of Reference.

# REPORTS

## Reporting requirements

The consultant will submit one final report in English language in one original and two copies:

The contractor will prepare one final report on the implementation of the tasks, at the end of this contract. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions.

The required formats of the reports will be communicated to the Contractor by the Contracting Authority after the signature of the contract.

## Submission & approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Services provided in timely, quality and quantity manor, as required in these Terms of Reference.

            - Number of meetings to be organized on rural tourism awareness campaign in rural areas from Caras-Severn county – 5 meetings

            - Number of fairs related to weekend destinations to be organized in Alibunar Municipality by the Serbian partners where the Romanian delegation will take part – 1 fair.

## Special requirements

The awarded tenderer will have to provide to the Contracting Authority the following:

- evidence to avoid  the exclusion criteria mentioned in PRAG, article 2.3.3 (e.g. tax certificate issued by the city hall, tax certificate issued by the local Agency for Fiscal Administration/Ministry for Public Finance, copy of the single registration code etc.);

- documents in order to demonstrate the accordance of the tenderer with the selection criteria mentioned at point 16 in the Service procurement notice (e.g. copy of the balance sheet for the past three years, copies of previous similar contracts to prove technical capacity etc.).

* * *